## Project Backlog
Work Item | Priority | Story Point | Internal Due Date | External Due Date
Network Diagram | 1 | 26 | 2021-10-26 | 2021-10-27
Project Plan | 2 | 22 | 2021-10-26 | 2021-10-27
Roadmap | 3 | 2 | 2021-10-26 | 2021-10-27
Test Plan | 4 | 22 | 2021-10-26 | 2021-10-27
LL Desgin
UM
Logging
Project Proposal | Done | 30 | 2021-09-06 | 2021-09-06
BRD | Done | 37 | 2021-10-06 | 2021-10-06
Site Map | Done | 8.5 | 2021-10-06 | 2021-10-06
HL Design | Done | 7 | 2021-10-06 | 2021-10-06
Tech Spec | Done | 4 | 2021-10-06 | 2021-10-06
Test Cases | Done | 30 | 2021-10-18 | 2021-10-27

## Sprint Backlog
Task | Priority | Assigned | Story Point | Sprint | Status | Internal Due Date | External Due Date | Work Item Lead | Associated Work Item | 1 Story Point = 1 hour
Information gathering: aid, careers, schedule of classes | 1 | Joseph | 4 | 3 | Done | 2021-10-26 | 2021-10-27 | Albert | Network Diagram | current SP | 72
Network Diagram: Choose server provider | 2 | Brad | 4 | 3 | Done | 2021-10-26 | 2021-10-27 | Albert | Network Diagram
Test case data: student discounts, careers | 3 | Albert | 2 | 3 | Done | 2021-10-26 | 2021-10-27 | Michael | Test Plan | Albert | 14
Test case data: matching, messaging | 4 | Audrey | 2 | 3 | Done | 2021-10-26 | 2021-10-27 | Michael | Test Plan | Audrey | 14
Test case data: schedules, classes | 5 | Brad | 2 | 3 | Done | 2021-10-26 | 2021-10-27 | Michael | Test Plan | Brad | 14
Test case data: aid | 6 | Joseph | 2 | 3 | Done | 2021-10-26 | 2021-10-27 | Michael | Test Plan | Joseph | 14
Test case data: course rating, registration, login, logout | 7 | Michael | 2 | 3 | Done | 2021-10-26 | 2021-10-27 | Michael | Test Plan | Michael | 16
Network Diagram: Node system specs | 8 | Joseph | 2 | 3 | Done | 2021-10-26 | 2021-10-27 | Albert | Network Diagram | total | 72
Network Diagram: IPs/URLs of external servers | 9 | Albert | 4 | 3 | Done | 2021-10-26 | 2021-10-27 | Albert | Network Diagram
Network Diagram: Requests | 10 | Audrey | 4 | 3 | Done | 2021-10-26 | 2021-10-27 | Albert | Network Diagram
Network Diagram: Responses | 11 | Michael | 4 | 3 | Done | 2021-10-26 | 2021-10-27 | Albert | Network Diagram
Network Diagram: 3rd party services & servers | 12 | Albert | 4 | 3 | Done | 2021-10-26 | 2021-10-27 | Albert | Network Diagram
Determine feature development order | 13 | Brad | 4 | 3 | Done | 2021-10-26 | 2021-10-27 | Brad | Project Plan
Determine critical path tasks | 14 | Audrey | 4 | 3 | Done | 2021-10-26 | 2021-10-27 | Brad | Project Plan
Plan deployment process | 15 | Michael | 4 | 3 | Done | 2021-10-26 | 2021-10-27 | Brad | Project Plan
Risk Identification | 16 | Brad | 3 | 3 | Done | 2021-10-26 | 2021-10-27 | Brad | Project Plan
Risk Mitigation | 17 | Michael | 2 | 3 | Done | 2021-10-26 | 2021-10-27 | Brad | Project Plan
Schedule Project Milestones | 18 | Joseph | 2 | 3 | Done | 2021-10-26 | 2021-10-27 | Brad | Project Plan
Schedule Sprints | 19 | Albert | 2 | 3 | Done | 2021-10-26 | 2021-10-27 | Brad | Project Plan
Validate schedule with team | 20 | Brad | 1 | 3 | Done | 2021-10-26 | 2021-10-27 | Brad | Project Plan
Generate Roadmap from schedule | 21 | Albert | 2 | 3 | Done | 2021-10-26 | 2021-10-27 | Brad | Project Plan
Test plan: testing schedule | 22 | Audrey | 4 | 3 | Done | 2021-10-26 | 2021-10-27 | Michael | Test Plan
Detail testing environment | 23 | Michael | 4 | 3 | Done | 2021-10-26 | 2021-10-27 | Michael | Test Plan
Progression and Regression Testing details | 24 | Joseph | 4 | 3 | Done | 2021-10-26 | 2021-10-27 | Michael | Test Plan
LL Desgin |  |  |  | 4 | Todo |  |  |  | LL Desgin
UM |  |  |  | 4 | Todo |  |  |  | UM
Logging |  |  |  | 4 | Todo |  |  |  | Logging
Introduction | Done | Audrey | 1 | 0 | Done | 2021-09-06 | 2021-09-06 | Audrey | Project Proposal
Needs and Problems | Done | Michael | 2 | 0 | Done | 2021-09-06 | 2021-09-06 | Audrey | Project Proposal
Goals and Objective | Done | Joseph | 1 | 0 | Done | 2021-09-06 | 2021-09-06 | Audrey | Project Proposal
Feature: Schedule Builder | Done | Brad | 3 | 0 | Done | 2021-09-06 | 2021-09-06 | Audrey | Project Proposal
Feature: Schedule Comparison | Done | Brad | 3 | 0 | Done | 2021-09-06 | 2021-09-06 | Audrey | Project Proposal
Feature: Course Difficulty | Done | Michael | 3 | 0 | Done | 2021-09-06 | 2021-09-06 | Audrey | Project Proposal
Feature: Matching | Done | Audrey | 3 | 0 | Done | 2021-09-06 | 2021-09-06 | Audrey | Project Proposal
Feture: Student Discounts | Done | Albert | 3 | 0 | Done | 2021-09-06 | 2021-09-06 | Audrey | Project Proposal
Feature: Aid | Done | Joseph | 3 | 0 | Done | 2021-09-06 | 2021-09-06 | Audrey | Project Proposal
Feature: Career Opps | Done | Albert | 3 | 0 | Done | 2021-09-06 | 2021-09-06 | Audrey | Project Proposal
Feature: Schedule of Classes | Done | Michael | 3 | 0 | Done | 2021-09-06 | 2021-09-06 | Audrey | Project Proposal
Feature: Messaging | Done | Brad | 3 | 0 | Done | 2021-09-06 | 2021-09-06 | Audrey | Project Proposal
Obstacles and Solutions | Done | Albert | 2 | 0 | Done | 2021-09-06 | 2021-09-06 | Audrey | Project Proposal
Executive Summary | Done | Joseph | 0.5 | 1 | Done | 2021-10-06 | 2021-10-06 | Albert | BRD
Project Description | Done | Joseph | 0.5 | 1 | Done | 2021-10-06 | 2021-10-06 | Albert | BRD
In Scope | Done | Audrey | 1 | 1 | Done | 2021-10-06 | 2021-10-06 | Albert | BRD
Out of Scope | Done | Michael | 1 | 1 | Done | 2021-10-06 | 2021-10-06 | Albert | BRD
Process - Builder | Done | Brad | 2 | 1 | Done | 2021-10-06 | 2021-10-06 | Albert | BRD
Process - Course Difficulty | Done | Michael | 2 | 1 | Done | 2021-10-06 | 2021-10-06 | Albert | BRD
Process - Matching | Done | Audrey | 2 | 1 | Done | 2021-10-06 | 2021-10-06 | Albert | BRD
Process - Career Opportuinty | Done | Albert | 2 | 1 | Done | 2021-10-06 | 2021-10-06 | Albert | BRD
Process - Aid | Done | Joseph | 2 | 1 | Done | 2021-10-06 | 2021-10-06 | Albert | BRD
Process - Student Discount | Done | Albert | 2 | 1 | Done | 2021-10-06 | 2021-10-06 | Albert | BRD
Process - Comparison | Done | Brad | 2 | 1 | Done | 2021-10-06 | 2021-10-06 | Albert | BRD
Requirements - Builder | Done | Brad | 2 | 1 | Done | 2021-10-06 | 2021-10-06 | Albert | BRD
Requirements - Course Difficulty | Done | Michael | 2 | 1 | Done | 2021-10-06 | 2021-10-06 | Albert | BRD
Requirements - Matching | Done | Audrey | 2 | 1 | Done | 2021-10-06 | 2021-10-06 | Albert | BRD
Requirements - Career Opportuinty | Done | Albert | 2 | 1 | Done | 2021-10-06 | 2021-10-06 | Albert | BRD
Requirements - Aid | Done | Joseph | 2 | 1 | Done | 2021-10-06 | 2021-10-06 | Albert | BRD
Requirements - Student Discount | Done | Albert | 2 | 1 | Done | 2021-10-06 | 2021-10-06 | Albert | BRD
Requirements - Comparison | Done | Brad | 2 | 1 | Done | 2021-10-06 | 2021-10-06 | Albert | BRD
Reuquirements - Messaging | Done | Brad | 2 | 1 | Done | 2021-10-06 | 2021-10-06 | Albert | BRD
Requirements - Schedule of Classes | Done | Michael | 2 | 1 | Done | 2021-10-06 | 2021-10-06 | Albert | BRD
Requirements - Core | Done | Michael | 1 | 1 | Done | 2021-10-06 | 2021-10-06 | Albert | BRD
Glossary | Done | Audrey | 0.5 | 1 | Done | 2021-10-06 | 2021-10-06 | Albert | BRD
Document History | Done | Audrey | 0.5 | 1 | Done | 2021-10-06 | 2021-10-06 | Albert | BRD
Error Handling | Done | Audrey | 4 | 1 | Done | 2021-10-06 | 2021-10-06 | Audrey | Site Map
View - Builder | Done | Brad | 0.5 | 1 | Done | 2021-10-06 | 2021-10-06 | Audrey | Site Map
View Comparison | Done | Brad | 0.5 | 1 | Done | 2021-10-06 | 2021-10-06 | Audrey | Site Map
View - Course Difficulty | Done | Michael | 0.5 | 1 | Done | 2021-10-06 | 2021-10-06 | Audrey | Site Map
View - Matching | Done | Audrey | 0.5 | 1 | Done | 2021-10-06 | 2021-10-06 | Audrey | Site Map
View - Student Discount | Done | Albert | 0.5 | 1 | Done | 2021-10-06 | 2021-10-06 | Audrey | Site Map
View - Aid | Done | Joseph | 0.5 | 1 | Done | 2021-10-06 | 2021-10-06 | Audrey | Site Map
View - Career Opportunity | Done | Albert | 0.5 | 1 | Done | 2021-10-06 | 2021-10-06 | Audrey | Site Map
View - Schedule of Classes | Done | Michael | 0.5 | 1 | Done | 2021-10-06 | 2021-10-06 | Audrey | Site Map
View - Messaging | Done | Brad | 0.5 | 1 | Done | 2021-10-06 | 2021-10-06 | Audrey | Site Map
Software | Done | Brad | 3 | 1 | Done | 2021-10-06 | 2021-10-06 | Brad | HL Design
Hardware | Done | Brad | 3 | 1 | Done | 2021-10-06 | 2021-10-06 | Brad | HL Design
Choose Software and Hardware | Done | Brad | 1 | 1 | Done | 2021-10-06 | 2021-10-06 | Brad | HL Design
OS Requirements | Done | Albert | 1 | 1 | Done | 2021-10-06 | 2021-10-06 | Michael | Tech Spec
Project Requirements | Done | Audrey | 1.5 | 1 | Done | 2021-10-06 | 2021-10-06 | Michael | Tech Spec
Product Requirements | Done | Michael | 1.5 | 1 | Done | 2021-10-06 | 2021-10-06 | Michael | Tech Spec
Phone calls: career center | Done | Joseph | 1 | 2 | Done | 2021-10-18 |  | Joseph
Phone calls: financial aid | Done | Joseph | 1 | 2 | Done | 2021-10-18 |  | Joseph
Phone calls: David Brown (schedule of classes) | Done | Joseph | 1 | 2 | Done | 2021-10-18 |  | Joseph
Test cases: Schedule Building | Done | Brad | 3 | 2 | Done | 2021-10-18 | 2021-10-27 | Joseph | Test Plan
Test cases: Discounts | Done | Albert | 3 | 2 | Done | 2021-10-18 | 2021-10-27 | Joseph | Test Plan
Test cases: Matching | Done | Audrey | 3 | 2 | Done | 2021-10-18 | 2021-10-27 | Joseph | Test Plan
Test cases: Aid | Done | Joseph | 3 | 2 | Done | 2021-10-18 | 2021-10-27 | Joseph | Test Plan
Test cases: Course Difficulty | Done | Michael | 3 | 2 | Done | 2021-10-18 | 2021-10-27 | Joseph | Test Plan
Test cases: Careers | Done | Albert | 3 | 2 | Done | 2021-10-18 | 2021-10-27 | Joseph | Test Plan
Test cases: Schedule of Classes | Done | Brad | 3 | 2 | Done | 2021-10-18 | 2021-10-27 | Joseph | Test Plan
Test cases: Messaging | Done | Audrey | 3 | 2 | Done | 2021-10-18 | 2021-10-27 | Joseph | Test Plan
Test cases: Registration | Done | Michael | 1 | 2 | Done | 2021-10-18 | 2021-10-27 | Joseph | Test Plan
Test cases: Login | Done | Michael | 1 | 2 | Done | 2021-10-18 | 2021-10-27 | Joseph | Test Plan
Test cases: Logout | Done | Michael | 1 | 2 | Done | 2021-10-18 | 2021-10-27 | Joseph | Test Plan

## Sprint Planning
Sprint 0 | 2021-09-21
| WI | Assigned | SP | Task Breakdown | SP | Assigned | Team Capacity | Team Member | Capacity
| Project Plan | Audrey | 33 | Introduction | 1 | Audrey | 50 | Albert | 10
|  |  |  | Needs and Problems | 2 | Michael | In Capacity | Audrey | 10
|  |  |  | Goals and Objective | 1 | Joseph |  | Brad | 10
|  |  |  | Feature: Schedule Builder | 3 | Brad |  | Joseph | 10
|  |  |  | Feature: Schedule Comparison | 3 | Brad |  | Michael | 10
|  |  |  | Feature: Course Difficulty | 3 | Michael
|  |  |  | Feature: Matching | 3 | Audrey
|  |  |  | Feture: Student Discounts | 3 | Albert
|  |  |  | Feature: Aid | 3 | Joseph
|  |  |  | Feature: Career Opps | 3 | Albert
|  |  |  | Feature: Schedule of Classes | 3 | Michael
|  |  |  | Feature: Messaging | 3 | Brad
|  |  |  | Obstacles and Solutions | 2 | Albert
|  | TOTAL SP Value | 33
Sprint 1 | 2021-09-28
| WI | Assigned | SP | Task Breakdown | SP | Assigned | Team Capacity | Team Member | Capacity
| BRD | Albert | 37 | Executive Summary | 0.5 | Joseph | 73 | Albert | 16
|  |  |  | Project Description | 0.5 | Joseph | In Capacity | Audrey | 15
|  |  |  | In Scope | 1 | Audrey |  | Brad | 20
|  |  |  | Out of Scope | 1 | Michael |  | Joseph | 10
|  |  |  | Process - Builder | 2 | Brad |  | Michael | 12
|  |  |  | Process - Course Difficulty | 2 | Michael
|  |  |  | Process - Matching | 2 | Audrey
|  |  |  | Process - Career Opportuinty | 2 | Albert
|  |  |  | Process - Aid | 2 | Joseph
|  |  |  | Process - Student Discount | 2 | Albert
|  |  |  | Process - Comparison | 2 | Brad
|  |  |  | Requirements - Builder | 2 | Brad
|  |  |  | Requirements - Course Difficulty | 2 | Michael
|  |  |  | Requirements - Matching | 2 | Audrey
|  |  |  | Requirements - Career Opportuinty | 2 | Albert
|  |  |  | Requirements - Aid | 2 | Joseph
|  |  |  | Requirements - Student Discount | 2 | Albert
|  |  |  | Requirements - Comparison | 2 | Brad
|  |  |  | Reuquirements - Messaging | 2 | Brad
|  |  |  | Requirements - Schedule of Classes | 2 | Michael
|  |  |  | Requirements - Core | 1 | Michael
|  |  |  | Glossary | 0.5 | Audrey
|  |  |  | Document History | 0.5 | Audrey
| Site Map | Audrey | 8.5 | Error Handling | 4 | Audrey
|  |  |  | View - Builder | 0.5 | Brad
|  |  |  | View Comparison | 0.5 | Brad
|  |  |  | View - Course Difficulty | 0.5 | Michael
|  |  |  | View - Matching | 0.5 | Audrey
|  |  |  | View - Student Discount | 0.5 | Albert
|  |  |  | View - Aid | 0.5 | Joseph
|  |  |  | View - Career Opportunity | 0.5 | Albert
|  |  |  | View - Schedule of Classes | 0.5 | Michael
|  |  |  | View - Messaging | 0.5 | Brad
| HL Design | Brad | 7 | Software | 3 | Brad
|  |  |  | Hardware | 3 | Brad
|  |  |  | Choose Software and Hardware | 1 | Brad
| Tech Spec | Michael | 4 | OS Requirements | 1 | Albert
|  |  |  | Project Requirements | 1.5 | Audrey
|  |  |  | Product Requirements | 1.5 | Michael
|  | TOTAL SP Value | 56.5
Sprint 2 | 2021-10-12
| WI | Assigned | SP | Task Breakdown | SP | Assigned | Team Capacity | Team Member | Capacity
| Test Cases | Joseph | 30 | Phone calls: career center | 1 | Joseph | 40 | Albert | 8
|  |  |  | Phone calls: financial aid | 1 | Joseph | In Capacity | Audrey | 8
|  |  |  | Phone calls: David Brown (schedule of classes) | 1 | Joseph |  | Brad | 8
|  |  |  | Test cases: Schedule Building | 3 | Brad |  | Joseph | 8
|  |  |  | Test cases: Discounts | 3 | Albert |  | Michael | 8
|  |  |  | Test cases: Matching | 3 | Audrey
|  |  |  | Test cases: Aid | 3 | Joseph
|  |  |  | Test cases: Course Difficulty | 3 | Michael
|  |  |  | Test cases: Careers | 3 | Albert
|  |  |  | Test cases: Schedule of Classes | 3 | Michael
|  |  |  | Test cases: Messaging | 3 | Audrey
|  |  |  | Test cases: Registration | 1 | Michael
|  |  |  | Test cases: Login | 1 | Michael
|  |  |  | Test cases: Logout | 1 | Michael
|  | TOTAL SP Value | 30
Sprint 3 | 2021-10-20
| WI | Assigned | SP | Task Breakdown | SP | Assigned | Team Capacity | Team Member | Capacity
| Test Plan | Michael | 22 | Test case data: student discounts, careers | 2 | Albert | 90 | Albert | 18
|  |  |  | Test case data: matching, messaging | 2 | Audrey | In Capacity | Audrey | 18
|  |  |  | Test case data: schedules, classes | 2 | Brad |  | Brad | 18
|  |  |  | Test case data: aid | 2 | Joseph |  | Joseph | 18
|  |  |  | Test case data: course rating, registration, login, logout | 2 | Michael |  | Michael | 18
|  |  |  | Test plan: testing schedule | 4 | Audrey
|  |  |  | Detail testing environment | 4 | Michael
|  |  |  | Progression and Regression Testing details | 4 | Joseph
| Network Diagram | Albert | 26 | Information gathering: aid, careers, schedule of classes | 4 | Joseph
|  |  |  | Network Diagram: Choose server provider | 4 | Brad
|  |  |  | Network Diagram: Node system specs | 2 | Joseph
|  |  |  | Network Diagram: IPs/URLs of external servers | 4 | Albert
|  |  |  | Network Diagram: Requests | 4 | Audrey
|  |  |  | Network Diagram: Responses | 4 | Michael
|  |  |  | Network Diagram: 3rd party services & servers | 4 | Albert
| Project Plan | Brad | 22 | Determine feature development order | 4 | Brad
|  |  |  | Determine critical path tasks | 4 | Audrey
|  |  |  | Plan deployment process | 4 | Michael
|  |  |  | Risk Identification | 3 | Brad
|  |  |  | Risk Mitigation | 2 | Michael
|  |  |  | Schedule Project Milestones | 2 | Joseph
|  |  |  | Schedule Sprints | 2 | Albert
|  |  |  | Validate schedule with team | 1 | Brad
| Roadmap | Brad | 2 | Generate Roadmap from schedule | 2 | Albert
|  | TOTAL SP Value | 72

## Sprint 0
Sprint 0 | proposal | [5 empty] | Day of Sprint | Forecast | Actual Effort
| Start Date | 2021-09-22 |  | Day of Sprint | Actual Effort |  | 0 | 33 | 33
| End Date | 2021-09-27 |  | 0 | 33 |  | 1 | 27.5 | 29
| Sprint Length | 6 |  | 1 | 29 |  | 2 | 22 | 29
| Team Size | 5 |  | 2 | 29 |  | 3 | 16.5 | 19
| Team Capacity | 50 |  | 3 | 19 |  | 4 | 11 | 16
| Total Sprint SP | 33 |  | 4 | 16 |  | 5 | 5.5 | 10
| SP/Day | 5.5 |  | 5 | 10 |  | 6 | 0 | 5
|  |  |  | 6 | 5
Who | Tasks | SP | Day of Sprint (hours worked)
|  |  | 0 | 1 | 2 | 3 | 4 | 5 | 6
Albert
| Obstacles & Solutions | 2 | 0 | 2 | 0 | 1 | 1 | 0 | 1
| Feature: Class Opp | 3 | 0 | 0 | 0 | 0 | 0 | 2 | 2
| Featue: Student Discounts | 3 | 0 | 0 | 0 | 0 | 3 | 1 | 0
SP Decrement |  |  | 0 | 1 | 0 | 0 | 3 | 1.5 | 2.5
Audrey
| Introduction | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 1
| Feature: Matching | 3 | 0 | 0 | 1 | 4 | 1 | 4 | 4
SP Decrement |  |  | 0 | 1 | 0 | 2 | 0 | 0.5 | 0.5
Brad
| Feature: Builder | 3 | 0 | 2 | 0 | 2 | 1 | 2 | 2
| Feature: Comparison | 3 | 0 | 0 | 0 | 2 | 2 | 2 | 2
| Feaure: Matching | 3 | 0 | 0 | 0 | 2 | 0 | 0 | 1
SP Decrement |  |  |  | 1 | 0 | 3 | 0 | 2 | 3
Joseph
| Goals/Solution | 1 | 0 | 1 | 0 | 2 | 0 | 1 | 0
| Feature: Aid | 3 | 0 | 0 | 0 | 4 | 1 | 4 | 5
SP Decrement |  |  | 0 | 0 | 0 | 2 | 2 | 0 | 0
Michael
| Needs/Problems | 2 | 0 | 0 | 0 | 1 | 0 | 0 | 1
| Feature: Course Diff | 3 | 0 | 1 | 0 | 4 | 0 | 2 | 2
| Feature: Schedule of Class | 3 | 0 | 0 | 0 | 1 | 1 | 2 | 2
SP Decrement |  |  | 0 | 1 | 0 | 3 | 0 | 2 | 2

## Sprint 1
Sprint 1 | milestone 1
| Start Date | 2021-09-29 |  | Day of Sprint | Actual Effort |  | Day of Sprint | Forecast | Actual Effort
| End Date | 2021-10-05 |  | 0 | 56.5 |  | 0 | 56.5 | 56.5
| Sprint Length | 7 |  | 1 | 53 |  | 1 | 48.4286 | 52
| Team Size | 5 |  | 2 | 53 |  | 2 | 40.3571 | 52
| Team Capacity | 60 |  | 3 | 45 |  | 3 | 32.2857 | 44
| Total Sprint SP | 56.5 |  | 4 | 40 |  | 4 | 24.2143 | 38
| SP/Day | 8.0714 |  | 5 | 26 |  | 5 | 16.1429 | 25
|  |  |  | 6 | 15 |  | 6 | 8.0714 | 14
|  |  |  | 7 | 0 |  | 7 | 0 | 0
Who | Tasks | SP | Day of Sprint (hours worked)
|  |  | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7
Albert
| Process - Student Discounts | 2 | 0 | 1 | 0 | 1 | 0 | 0 | 1 | 0
| Process - Career Opp | 2 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1
| Requirements - Student Discounts | 2 | 0 | 1 | 0 | 0 | 2 | 2 | 1 | 1
| Requirements - Career Opps | 2 | 0 | 0 | 0 | 1 | 1 | 2 | 0 | 1.5
| View - Student Discounts | 0.5 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0.5
| View - Career Opps | 0.5 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0
| OS Requirement | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2
SP Decrement |  |  | 0 | 1 | 0 | 2 | 1 | 2 | 1 | 3
Audrey
| Glossary | 0.5 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0
| Document Version | 0.5 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0
| In Scope | 1 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 0
| Process - Matching | 2 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1
| Requirements - Matching | 2 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1
| View - Matching | 0.5 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1
| Error Hangling | 4 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 2
| Project Requirements | 1.5 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1
SP Decrement |  |  | 0 | 1 | 0 | 2 | 1 | 3 | 3 | 2
Brad
| Process - Comparison | 2 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0
| Process - Builder | 2 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0
| Requirements - Comparison | 2 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 1
| Requirements - Builder | 2 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 2
| Requirements - Messaging | 2 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0
| View - Comparison | 0.5 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1
| View - Messaging | 0.5 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0
| View - Builder | 0.5 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1
| Hardware | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1
| Software | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1
| Choosing Hardware and Software | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0
SP Decrement |  |  | 0 | 1 | 0 | 1 | 2 | 5 | 4 | 5.5
Joseph
| Executive Summary | 0.5 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0
| Project Description | 0.5 | 0 | 0.5 | 0 | 0.5 | 0 | 0 | 0 | 0
| Process - Aid | 2 | 0 | 1 | 0 | 1.5 | 1 | 2 | 2 | 2
| Requirement - Aid | 2 | 0 | 1 | 0 | 0 | 2 | 1 | 2 | 2
| View - Aid | 0.5 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 2
SP Decrement |  |  | 0 | 0.5 | 0 | 1 | 1 | 1 | 1 | 1
Michael
| Out of Scope | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1
| Process - Course Difficulty | 2 | 0 | 2 | 0 | 1 | 1 | 0 | 1 | 1
| Requirements - Course Difficulty | 2 | 0 | 1 | 0 | 2 | 1 | 0 | 1 | 2
| Requirements - Schedule of Classes | 2 | 0 | 0 | 0 | 2 | 1 | 2 | 0 | 0
| Requirements - Core | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0
| View - Schule of Classes | 0.5 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0
| View - Course Difficulty | 0.5 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 1
| Product Requirements | 1.5 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0
SP Decrement |  |  | 0 | 1 | 0 | 2 | 1 | 2 | 2 | 2.5

## Sprint 2
Sprint 2 | test plan
| Start Date | 2021-10-13 |  | Day of Sprint | Actual Effort |  |  | Day of Sprint | Forecast | Actual Effort
| End Date | 2021-10-18 |  | 0 | 30 |  |  | 0 | 30 | 30
| Sprint Length | 6 |  | 1 | 30 |  |  | 1 | 25 | 30
| Team Size | 5 |  | 2 | 30 |  |  | 2 | 20 | 30
| Team Capacity | 30 |  | 3 | 22 |  |  | 3 | 15 | 22
| Total Sprint SP | 30 |  | 4 | 16 |  |  | 4 | 10 | 16
| SP/Day | 5 |  | 5 | 6 |  |  | 5 | 5 | 6
|  |  |  | 6 | 0 |  |  | 6 | 0 | 0
|  |  |  | w | th | f | s | s | m
Who | Tasks | SP | Day of Sprint (hours worked)
|  |  | 0 | 1 | 2 | 3 | 4 | 5 | 6
Albert
| Test cases: Discounts | 3 | 0 | 0 | 0 | 0 | 2 | 1 | 0
| Test cases: Careers | 3 | 0 | 0 | 0 | 0 | 1 | 2 | 3
SP Decrement |  |  | 0 | 0 | 0 | 0 | 2 | 2 | 2
Audrey
| Test cases: Matching | 3 | 0 | 0 | 0 | 4 | 1 | 1 | 1
| Test cases: Messaging | 3 | 0 | 0 | 0 | 0 | 2 | 1 | 1
SP Decrement |  |  | 0 | 0 | 0 | 3 | 2 | 1 | 0
Brad
| Test cases: Schedule Building | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 1
| Test cases: Schedule of Classes | 3 | 0 | 0 | 0 | 0 | 0 | 1 | 1
SP Decrement |  |  | 0 | 0 | 0 | 1 | 0 | 3 | 2
Joseph
| Phone calls: career center | 1 | 0 | 0 | 0 | 2 | 0 | 0 | 1
| Phone calls: financial aid | 1 | 0 | 0 | 0 | 2 | 0 | 0 | 1
| Phone calls: David Brown (SoC) | 1 | 0 | 0 | 0 | 3 | 0.5 | 0 | 1
| Test cases: Aid | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 1
SP Decrement |  |  | 0 | 0 | 0 | 3 | 1 | 1 | 1
Michael
| Test cases: Course Difficulty | 3 | 0 | 0 | 0 | 0 | 0 | 2 | 1
| Test cases: Registration | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0
| Test cases: Login | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0
| Test cases: Logout | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
SP Decrement |  |  | 0 | 0 | 0 | 1 | 1 | 3 | 1
Daily Scrum Meeting
Day of Sprint | Who | What did you work on Yesterday? |  |  | What are you working on today? |  |  | Are You Blocked?
Day 1 | Albert | n/a |  |  | n/a |  |  | no
| Audrey | n/a |  |  | n/a |  |  | no
| Brad | n/a |  |  | n/a |  |  | no
| Joseph | n/a |  |  | n/a |  |  | no
| Michael | n/a |  |  | n/a |  |  | no
Day 2 | Albert | n/a |  |  | n/a |  |  | no
| Audrey | n/a |  |  | n/a |  |  | no
| Brad | n/a |  |  | n/a |  |  | no
| Joseph | n/a |  |  | n/a |  |  | no
| Michael | n/a |  |  | n/a |  |  | no
Day 3 | Albert | n/a |  |  | n/a |  |  | no
| Audrey | n/a |  |  | match test cases |  |  | no
| Brad | n/a |  |  | schedule builder test cases |  |  | no
| Joseph | n/a |  |  | phone calls, aid test cases |  |  | yes
| Michael | n/a |  |  | registration test cases |  |  | no
Day 4 | Albert | n/a |  |  | career opps, student discounts test cases |  |  | no
| Audrey | match test cases |  |  | messaging, matching test cases |  |  | no
| Brad | schedule builder test cases |  |  | n/a |  |  | no
| Joseph | phone calls, aid test cases |  |  | phone calls |  |  | yes
| Michael | registration test cases |  |  | login test cases |  |  | no
Day 5 | Albert | career opps, student discounts test cases |  |  | discounts, careers test cases |  |  | yes
| Audrey | messaging, matching test cases |  |  | messaging, matching test cases |  |  | no
| Brad | n/a |  |  | schedule building, schedule of classes test cases |  |  | no
| Joseph | phone calls |  |  | aid test cases |  |  | yes
| Michael | login test cases |  |  | course reviews, logout test cases |  |  | no
Day 6 | Albert | discounts, careers test cases |  |  | careers test cases |  |  | no
| Audrey | messaging, matching test cases |  |  | messaging, matching test cases |  |  | no
| Brad | schedule building, schedule of classes test cases |  |  | schedule building, schedule of classes test cases |  |  | no
| Joseph | aid test cases |  |  | aid test cases, phone calls |  |  | no
| Michael | course reviews, logout test cases |  |  | course reviews test cases |  |  | no

## Sprint 3
Sprint 3 | milestone 2
| Start Date | 2021-10-21 |  | Day of Sprint | Actual Effort |  |  | Day of Sprint | Forecast | Actual
| End Date | 2021-10-26 |  | 0 | 72 |  |  | 0 | 72 | 72
| Sprint Length | 6 |  | 1 | 70 |  |  | 1 | 60 | 70
| Team Size | 5 |  | 2 | 60 |  |  | 2 | 48 | 60
| Team Capacity | 90 |  | 3 | 53.5 |  |  | 3 | 36 | 53.5
| Total Sprint SP | 72 |  | 4 | 37.5 |  |  | 4 | 24 | 37.5
| SP/Day | 12 |  | 5 | 20 |  |  | 5 | 12 | 20
|  |  |  | 6 | 0 |  |  | 6 | 0 | 0
|  |  |  | th | f | s | s | m | t
Who | Tasks | SP | Day of Sprint (hours worked)
|  |  | 0 | 1 | 2 | 3 | 4 | 5 | 6
Albert
| Test case datastudent discounts, careers | 2 | 0 | 0 | 0 | 0 | 4 | 1 | 0
| IPs/URLs of external servers | 4 | 0 | 0 | 2 | 3 | 2 | 2 | 0
| Network Diagram: 3rd party services & servers | 4 | 0 | 0 | 0 | 0 | 2 | 2 | 0
| Schedule Sprints | 2 | 0 | 0 | 0 | 0 | 0 | 1 | 0
| Generate Roadmap from schedule | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 4
SP Decrement |  |  | 0 | 0 | 1 | 1 | 4 | 4 | 4
Audrey
| Test case data: matching, messaging | 2 | 0 | 0 | 2 | 1 | 2 | 0 | 0
| Network Diagram: Requests | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 3
| Determine critical path tasks | 4 | 0 | 0 | 0 | 1 | 2 | 2 | 3
| Test plan: testing schedule | 4 | 0 | 0 | 0 | 0.5 | 0 | 1.5 | 2
SP Decrement |  |  | 0 | 0 | 1 | 2 | 4 | 3 | 4
Brad
| Choose server provider | 4 | 0 | 1.5 | 1 | 0 | 0 | 0 | 0
| Test case data: schedules, classes | 2 | 0 | 0 | 2 | 0.5 | 2.75 | 0 | 0
| Determine feature development order | 4 | 0 | 0 | 0 | 0 | 2 | 2 | 0.5
| Validate schedule with team | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0.5
| Risk Identification | 3 | 0 | 0 | 0.5 | 0 | 0 | 0.75 | 0
| Other | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2
SP Decrement |  |  | 0 | 2 | 3 | 0.5 | 3 | 4.5 | 1
Joseph
| Information gathering: aid, careers, schedule of classes | 4 | 0 | 0 | 4 | 1.5 | 1 | 0 | 0
| Test case data: aid | 2 | 0 | 0 | 2 | 2 | 1.5 | 1.5 | 2
| Network Diagram: Node system specs | 2 | 0 | 0 | 0.5 | 1.5 | 1 | 1.5 | 2
| Schedule Project Milestones | 2 | 0 | 0 | 0 | 0 | 0.5 | 0.5 | 1.5
| Progression and Regression Testing details | 4 | 0 | 0 | 0 | 0 | 0 | 1.5 | 2
SP Decrement |  |  | 0 | 0 | 4 | 2 | 2 | 2 | 4
Michael
| Test case data: course rating, registration, login, logout | 2 | 0 | 0 | 2 | 1 | 0 | 2 | 0
| Network Diagram: Responses | 4 | 0 | 0 | 0 | 0 | 2 | 2 | 0
| Plan deployment process | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 4
| Detail testing environment | 4 | 0 | 0 | 0 | 0 | 0 | 2 | 3
| Risk Mitigation | 2 | 0 | 0 | 0 | 0 | 2 | 0 | 3
SP Decrement |  |  | 0 | 0 | 1 | 1 | 3 | 4 | 7
Daily Scrum Meeting
Day of Sprint | Who | What did you work on Yesterday? |  |  | What are you working on today? |  |  | Are You Blocked?
Day 1 | Albert | n/a |  |  | n/a |  |  | no
| Audrey | n/a |  |  | n/a |  |  | no
| Brad | n/a |  |  | choose service provider |  |  | no
| Joseph | n/a |  |  | n/a |  |  | no
| Michael | n/a |  |  | n/a |  |  | no
Day 2 | Albert | n/a |  |  | ip/urls |  |  | no
| Audrey | n/a |  |  | test cases |  |  | no
| Brad | choose service provider |  |  | choose service provider, test cases, risk identification |  |  | no
| Joseph | n/a | [5 empty] | no
| Michael | n/a |  |  | test cases |  |  | no
Day 3 | Albert | ip/urls |  |  | test cases, network diagram |  |  | no
| Audrey | test cases |  |  | test cases, gnatt chart |  |  | no
| Brad | choose service provider, test cases, risk identification |  |  | test cases |  |  | no
| Joseph | [6 empty] | no
| Michael | test cases |  |  | test cases |  |  | no
Day 4 | Albert | test cases, network diagram |  |  | test cases, network diagram |  |  | no
| Audrey | test cases, gnatt chart |  |  | test cases, critical path |  |  | no
| Brad | test cases |  |  | test cases, feature development order |  |  | no
| Joseph |  |  |  | test cases, phone call, emails, research specs |  |  | no
| Michael | test cases |  |  | test cases, looking at risk identification |  |  | no
Day 5 | Albert | test cases, network diagram |  |  | schedule sprint, network diagram |  |  | yes
| Audrey | test cases, critical path |  |  | testing scedule, critical path, requests |  |  | no
| Brad | test cases, feature development order |  |  | more feature development order, risk, validate schedule |  |  | no
| Joseph | test cases, phone call, emails, research specs |  |  | test cases, specs, emails |  |  | yes
| Michael | test cases, looking at risk identification |  |  | test cases, risk mitagation |  |  | no
Day 6 | Albert | schedule sprint, network diagram |  |  | roadmap |  |  | no
| Audrey | testing scedule, critical path, requests |  |  | requests, critical path, testing schedule |  |  | no
| Brad | more feature development order, risk, validate schedule |  |  | feature development order, validate schedule, other |  |  | no
| Joseph | test cases, specs, emails | [5 empty] | no
| Michael | test cases, risk mitagation |  |  | plan deployment process, testing enviornment, risk mitagation |  |  | no

## Albert
Sprint 0 | proposal | [5 empty] | Sprint | SP | Hours Worked | Over/Under
| Start Date | 2021-09-22 | Day of Sprint | Forecast | Actual Effort | Hours Worked | 0 | 8 | 13 | 5
| End Date | 2021-09-27 | 0 | 8 | 8 | 0 | 1 | 10 | 24 | 14
| Sprint Length | 6 | 1 | 6.67 | 7 | 2 | 2 | 6 | 9 | 3
|  |  | 2 | 5.34 | 7 | 0 | 3 | 14 | 24 | 10
| Capacity | 10 | 3 | 4.01 | 7 | 1
| Total Sprint SP | 8 | 4 | 2.68 | 4 | 4
| SP/Day | 1.33 | 5 | 1.35 | 2.5 | 3
|  |  | 6 | 0 | 0 | 3
[5 empty] | Total = | 13
[5 empty] | Over effort = | 5
Sprint 1 | milestone 1
| Start Date | 2021-09-29 | Day of Sprint | Forecast | Actual Effort | Hours Worked
| End Date | 2021-10-05 | 0 | 10 | 10 | 0
| Sprint Length | 7 | 1 | 8.5714 | 9 | 3
|  |  | 2 | 7.1429 | 9 | 0
| Capacity | 16 | 3 | 5.7143 | 7 | 4
| Total Sprint SP | 10 | 4 | 4.2857 | 6 | 3
| SP/Day | 1.4286 | 5 | 2.8571 | 4 | 5
|  |  | 6 | 1.4286 | 3 | 3
|  |  | 7 | 0 | 0 | 6
[5 empty] | Total = | 24
[5 empty] | Over effort = | 14
Sprint 2 | test plan
| Start Date | 2021-10-13 | Day of Sprint | Forecast | Actual Effort | Hours Worked
| End Date | 2021-10-18 | 0 | 6 | 6 | 0
| Sprint Length | 6 | 1 | 5 | 6 | 0
|  |  | 2 | 4 | 6 | 0
| Capacity | 8 | 3 | 3 | 5 | 1
| Total Sprint SP | 6 | 4 | 2 | 4 | 3
| SP/Day | 1 | 5 | 1 | 2 | 3
|  |  | 6 | 0 | 0 | 3
[5 empty] | Total = | 10
[5 empty] | Over effort = | 4
Sprint 3 | milestone 2
| Start Date | 2021-10-21 | Day of Sprint | Forecast | Actual Effort | Hours Worked
| End Date | 2021-10-26 | 0 | 14 | 14 | 0
| Sprint Length | 6 | 1 | 11.6667 | 14 | 0
|  |  | 2 | 9.3333 | 13 | 2
| Capacity | 18 | 3 | 7 | 12 | 3
| Total Sprint SP | 14 | 4 | 4.6667 | 8 | 8
| SP/Day | 2.3333 | 5 | 2.3333 | 4 | 6
|  |  | 6 | 0 | 0 | 5
[5 empty] | Total = | 24
[5 empty] | Over effort = | 10

## Audrey
Sprint 0 | proposal | [5 empty] | Sprint | SP | Hours Worked | Over/Under
| Start Date | 2021-09-22 | Day of Sprint | Forecast | Actual Effort | Hours Worked | 0 | 4 | 16 | 12
| End Date | 2021-09-27 | 0 | 4 | 4 | 0 | 1 | 12 | 27 | 15
| Sprint Length | 6 | 1 | 3.33 | 3 | 1 | 2 | 6 | 11 | 5
|  |  | 2 | 2.66 | 3 | 1 | 3 | 14 | 20 | 6
| Capacity | 10 | 3 | 1.99 | 1 | 4
| Total Sprint SP | 4 | 4 | 1.32 | 1 | 1
| SP/Day | 0.67 | 5 | 0.65 | 0.5 | 4
|  |  | 6 | 0 | 0 | 5
[5 empty] | Total = | 16
[5 empty] | Over Effort = | 12
Sprint 1 | milestone 1
| Start Date | 2021-09-29 | Day of Sprint | Forecast | Actual Effort | Hours Worked
| End Date | 2021-10-05 | 0 | 12 | 12 | 0
| Sprint Length | 7 | 1 | 10.2857 | 11 | 2
|  |  | 2 | 8.5714 | 11 | 0
| Capacity | 15 | 3 | 6.8571 | 9 | 4
| Total Sprint SP | 12 | 4 | 5.1429 | 8 | 3
| SP/Day | 1.7143 | 5 | 3.4286 | 5 | 6
|  |  | 6 | 1.7143 | 2 | 6
|  |  | 7 | 0 | 0 | 6
[5 empty] | Total = | 27
[5 empty] | Over Effort = | 15
Sprint 2 | test plan
| Start Date | 2021-10-13 | Day of Sprint | Forecast | Actual Effort | Hours Worked
| End Date | 2021-10-18 | 0 | 6 | 6 | 0
| Sprint Length | 6 | 1 | 5 | 6 | 0
|  |  | 2 | 4 | 6 | 0
| Capacity | 8 | 3 | 3 | 3 | 4
| Total Sprint SP | 6 | 4 | 2 | 2 | 3
| SP/Day | 1 | 5 | 1 | 1 | 2
|  |  | 6 | 0 | 0 | 2
[5 empty] | Total = | 11
[5 empty] | Over Effort = | 5
Sprint 3 | project plan | network diagram
| Start Date | 2021-10-21 | Day of Sprint | Forecast | Actual Effort | Hours Worked
| End Date | 2021-10-26 | 0 | 14 | 14 | 0
| Sprint Length | 6 | 1 | 11.6667 | 14 | 0
|  |  | 2 | 9.3333 | 13 | 2
| Capacity | 18 | 3 | 7 | 11 | 2.5
| Total Sprint SP | 14 | 4 | 4.6667 | 7 | 4
| SP/Day | 2.3333 | 5 | 2.3333 | 4 | 3.5
|  |  | 6 | 0 | 0 | 8
[5 empty] | Total = | 20
[5 empty] | Over Effort = | 6

## Brad
Sprint 0 | proposal | [5 empty] | Sprint | SP | Hours Worked | Over/Under
| Start Date | 2021-09-22 | Day of Sprint | Forecast | Actual Effort | Hours Worked | 0 | 9 | 20 | 11
| End Date | 2021-09-27 | 0 | 9 | 9 | 0 | 1 | 18.5 | 33 | 14.5
| Sprint Length | 6 | 1 | 7.5 | 8 | 2 | 2 | 6 | 5 | -1
|  |  | 2 | 6 | 8 | 0 | 3 | 14 | 16 | 2
| Capacity | 10 | 3 | 4.5 | 5 | 6
| Total Sprint SP | 9 | 4 | 3 | 5 | 3
| SP/Day | 1.5 | 5 | 1.5 | 3 | 4
|  |  | 6 | 0 | 0 | 5
[5 empty] | Total = | 20
[5 empty] | Over Effort = | 11
Sprint 1 | milestone 1
| Start Date | 2021-09-29 | Day of Sprint | Forecast | Actual Effort | Hours Worked
| End Date | 2021-10-05 | 0 | 18.5 | 18.5 | 0
| Sprint Length | 7 | 1 | 15.8571 | 17.5 | 3
|  |  | 2 | 13.2143 | 17.5 | 0
| Capacity | 20 | 3 | 10.5714 | 16.5 | 4
| Total Sprint SP | 18.5 | 4 | 7.9286 | 14.5 | 6
| SP/Day | 2.6429 | 5 | 5.2857 | 9.5 | 6
|  |  | 6 | 2.6429 | 5.5 | 7
|  |  | 7 | 0 | 0 | 7
[5 empty] | Total = | 33
[5 empty] | Over Effort = | 14.5
Sprint 2 | test plan
| Start Date | 2021-10-13 | Day of Sprint | Forecast | Actual Effort | Hours Worked
| End Date | 2021-10-18 | 0 | 6 | 6 | 0
| Sprint Length | 6 | 1 | 5 | 6 | 0
|  |  | 2 | 4 | 6 | 0
| Capacity | 8 | 3 | 3 | 5 | 1
| Total Sprint SP | 6 | 4 | 2 | 5 | 0
| SP/Day | 1 | 5 | 1 | 3 | 2
|  |  | 6 | 0 | 1 | 2
[5 empty] | Total = | 5
[5 empty] | Over Effort = | -1
Sprint 3 | project plan | network diagram
| Start Date | 2021-10-21 | Day of Sprint | Forecast | Actual Effort | Hours Worked
| End Date | 2021-10-26 | 0 | 14 | 14 | 0
| Sprint Length | 6 | 1 | 11.6667 | 12 | 1.5
|  |  | 2 | 9.3333 | 9 | 3.5
| Capacity | 18 | 3 | 7 | 8.25 | 0.5
| Total Sprint SP | 14 | 4 | 4.6667 | 5.25 | 4.75
| SP/Day | 2.3333 | 5 | 2.3333 | 1 | 3.75
|  |  | 6 | 0 | 0 | 2
[5 empty] | Total = | 16
[5 empty] | Over Effort = | 2

## Joseph
Sprint 0 | proposal | [5 empty] | Sprint | SP | Hours Worked | Over/Under
| Start Date | 2021-09-22 | Day of Sprint | Forecast | Actual Effort | Hours Worked | 0 | 4 | 18 | 14
| End Date | 2021-09-27 | 0 | 4 | 4 | 0 | 1 | 5.5 | 24 | 18.5
| Sprint Length | 6 | 1 | 3.33 | 4 | 1 | 2 | 6 | 11 | 5
|  |  | 2 | 2.66 | 4 | 0 | 3 | 14 | 28 | 14
| Capacity | 10 | 3 | 1.99 | 2 | 6
| Total Sprint SP | 4 | 4 | 1.32 | 2 | 1
| SP/Day | 0.67 | 5 | 0.65 | 0 | 5
|  |  | 6 | 0 | 0 | 5
[5 empty] | Total = | 18
[5 empty] | Over Effort = | 14
Sprint 1 | milestone 1
| Start Date | 2021-09-29 | Day of Sprint | Forecast | Actual Effort | Hours Worked
| End Date | 2021-10-05 | 0 | 5.5 | 5.5 | 0
| Sprint Length | 7 | 1 | 4.7143 | 5 | 2
|  |  | 2 | 3.9286 | 5 | 0
| Capacity | 10 | 3 | 3.1429 | 4 | 2
| Total Sprint SP | 5.5 | 4 | 2.3571 | 3 | 3
| SP/Day | 0.78571 | 5 | 1.5714 | 2 | 5
|  |  | 6 | 0.78571 | 1 | 6
|  |  | 7 | 0 | 0 | 6
[5 empty] | Total = | 24
[5 empty] | Over Effort = | 18.5
Sprint 2 | test plan
| Start Date | 2021-10-13 | Day of Sprint | Forecast | Actual Effort | Hours Worked
| End Date | 2021-10-18 | 0 | 6 | 6 | 0
| Sprint Length | 6 | 1 | 5 | 6 | 0
|  |  | 2 | 4 | 6 | 0
| Capacity | 8 | 3 | 3 | 3 | 4
| Total Sprint SP | 6 | 4 | 2 | 2 | 3
| SP/Day | 1 | 5 | 1 | 1 | 2
|  |  | 6 | 0 | 0 | 2
[5 empty] | Total = | 11
[5 empty] | Over Effort = | 5
Sprint 3 | project plan | network diagram
| Start Date | 2021-10-21 | Day of Sprint | Forecast | Actual Effort | Hours Worked
| End Date | 2021-10-26 | 0 | 14 | 14 | 0
| Sprint Length | 6 | 1 | 11.6667 | 14 | 0
|  |  | 2 | 9.3333 | 13 | 6.5
| Capacity | 18 | 3 | 7 | 10 | 5
| Total Sprint SP | 14 | 4 | 4.6667 | 7 | 4
| SP/Day | 2.3333 | 5 | 2.3333 | 4 | 5
|  |  | 6 | 0 | 0 | 7.5
[5 empty] | Total = | 28
[5 empty] | Over Effort = | 14

## Michael
Sprint 0 | proposal | [5 empty] | Sprint | SP | Hours Worked | Over/Under
| Start Date | 2021-09-22 | Day of Sprint | Forecast | Actual Effort | Hours Worked | 0 | 4 | 18 | 14
| End Date | 2021-09-27 | 0 | 8 | 8 | 0 | 1 | 11.5 | 28 | 16.5
| Sprint Length | 6 | 1 | 6.67 | 7 | 1 | 2 | 6 | 11 | 5
|  |  | 2 | 5.33 | 7 | 0 | 3 | 16 | 23 | 7
| Capacity | 10 | 3 | 4 | 4 | 6
| Total Sprint SP | 8 | 4 | 2.66 | 4 | 1
| SP/Day | 0.67 | 5 | 1.33 | 2 | 4
|  |  | 6 | 0 | 0 | 5
[5 empty] | Total = | 17
[5 empty] | Over Effort = | 14
Sprint 1 | milestone 1
| Start Date | 2021-09-29 | Day of Sprint | Forecast | Actual Effort | Hours Worked
| End Date | 2021-10-05 | 0 | 10.5 | 10.5 | 0
| Sprint Length | 7 | 1 | 9 | 9.5 | 3
|  |  | 2 | 7.5 | 9.5 | 0
| Capacity | 12 | 3 | 6 | 7.5 | 7
| Total Sprint SP | 10.5 | 4 | 4.5 | 6.5 | 5
| SP/Day | 1.5 | 5 | 3 | 4.5 | 5
|  |  | 6 | 1.5 | 2.5 | 5
|  |  | 7 | 0 | 0 | 5
[5 empty] | Total = | 30
[5 empty] | Over Effort = | 19.5
Sprint 2 | test plan
| Start Date | 2021-10-13 | Day of Sprint | Forecast | Actual Effort | Hours Worked
| End Date | 2021-10-18 | 0 | 6 | 6 | 0
| Sprint Length | 6 | 1 | 5 | 6 | 0
|  |  | 2 | 4 | 6 | 0
| Capacity | 8 | 3 | 3 | 5 | 1
| Total Sprint SP | 6 | 4 | 2 | 4 | 1
| SP/Day | 1 | 5 | 1 | 1 | 3
|  |  | 6 | 0 | 0 | 1
[5 empty] | Total = | 6
[5 empty] | Over Effort = | 0
Sprint 3 | project plan | network diagram
| Start Date | 2021-10-21 | Day of Sprint | Forecast | Actual Effort | Hours Worked
| End Date | 2021-10-26 | 0 | 16 | 16 | 0
| Sprint Length | 6 | 1 | 13.3333 | 16 | 0
|  |  | 2 | 10.6667 | 15 | 2
| Capacity | 18 | 3 | 8 | 14 | 1
| Total Sprint SP | 16 | 4 | 5.3333 | 11 | 4
| SP/Day | 2.6667 | 5 | 2.6667 | 7 | 6
|  |  | 6 | 0 | 0 | 10
[5 empty] | Total = | 23
[5 empty] | Over Effort = | 7

## Error Chart
Sprint # | % Error | Expected Work Done | Actual Work Done | Capacity
0 | -15.1515 | 33 | 28 | 50
1 | -1.7699 | 56.5 | 55.5 | 73
2 | 0 | 30 | 30 | 40
3 | 0 | 72 | 72 | 90
4
5
6
7

## Retrospective
Sprint # | Date | Who | What did we do well? | What did we do wrong? | How can we improve next time?
0 | 2021-09-27 | Albert | As a team, we have good communcaiton | Didnt ask as many questions to professor as should have | Make sure we have priority on backlog
|  | Audrey | As a team, we have good communcaiton and meet when necessary. | Be more productive when waiting for feedback | Work on other items when waiting for feedback
|  | Brad | As a team, we have good communcaiton | Be more productive when waiting for feedback | send more emails to professor when need help, not jsut wait for office hours
|  | Joseph | As a team, we have good communcaiton. | Didnt complete tasks during sprint | work on other items when waiting for feedback
|  | Michael | As a team, we have good communcaiton | Didn't ask for help as much when needed | Make sure we have priority on backlog
1 | 2021-10-06 | Albert | met more as needed, communicated well | We didn't update the status of tasks as often as we should have. | assigning tasks before begining and continously marking when things are done
|  | Audrey | met more as needed, communicated well, got all tasks done during sprint | we worked on it a lot more then orginially planned | make better estimates of story point values
|  | Brad | met more as needed, communicated well | scrum wasnt to level of detail needed it to be at | make individual burndown charts, improve backlog
|  | Joseph | got all WI done, communicated well | we worked on it a lot more then orginially planned | plan the sprint accordingly, write down meeting inormation
|  | Michael | met more as needed, communicated well | didnt update keep track of how many hours worked each day | make nicer and easier way to see how long worked on each task each day
2 | 2021-10-19 | Albert | did better job on prioritizing items each sprint | not accurately keping track of hours | at the end of each day, update hours | 1 | what did we do well?
|  | Audrey | improved our use of scrum | didnt communicate as much as could have | Still have meetings on scheduled days, even if its just to say what were going to work on, and ask questions
|  | Brad | more clear view of who was doing what task | didnt communicate as much, started late | plan the next sprint ahead of time in order to begin working on the WI during the first day of the sprint
|  | Joseph | split of tasks more evenly | didnt specify who was in charge of what work item | Clearly note who is in charge of which work item
|  | Michael | actually used our backlog | need to update hours daily, not at the end | Update hours at the end of every day
3 | 2021-10-27 | Albert | updated hours on more daily basis, communciated well | Some tasks were not very clearly defined during sprint planning | make sure everyone understands what they are working on during sprint planning | 2 | what did we do wrong?
|  | Audrey | i think we communicated well, met as needed, and were all made clear on what we needed to do | people working on each others assigned tasks | swap tasks if both parties working more on each others task, make that adjustment during sprint planning
|  | Brad | communicated well and asked for help when needed it from each other | having larger crunch time, working more on tasks in beginning of sprint | work on tasks evenly thorughout sprint to avoid all piling up at end
|  | Joseph | made progress on finding information for our resoruces, asking for help when needed | didnt update backlog on where at in progress for a task | update hours on a daily basis
|  | Michael | helped each other out as needed, did more research | not asking as many questions even though still confuesed on what needs to be done | send more emails when have questions regarding whats due, update backlog when finish a task
4 | [5 empty] | 3 | how can we improve next time?
5
6
7
8
9
10

## Story Point Breakdown (hidden)
Sprint 0 | total = 30
SP
| Proposal |  |  | 30
|  | Features | 24
|  | Needs/Problems | 2
|  | Goals/Solution | 2
|  | Obstacles & Solutions | 2
30
Sprint 1 | total = 35
SP
| BRD |  |  | 37
|  | Summary, Glossary, Appendix | 3
|  | Requirements | 18
|  | Processes | 14
|  | In and out of scope | 2
| Tech Spec |  |  | 4
|  | OS | 1
|  | Product | 2
|  | Project | 1
| Site Map |  |  | 8
|  | Design | 5
|  | Errors | 3
| HL Design |  |  | 7
|  | Software | 3.5
|  | Hardware | 3.5
56
Sprint 2 | total =
SP

## Kanban Board
Sprint 2 | Assigned | To Do | In Progress | Blocked | Done
| Joseph |  |  |  | Phone calls: career center
| Joseph |  |  |  | Phone calls: financial aid
| Joseph |  |  |  | Phone calls: David Brown (schedule of classes)
| Brad |  |  |  | Test cases: Schedule Building
| Albert |  |  |  | Test cases: Discounts
| Audrey |  |  |  | Test cases: Matching
| Joseph |  |  |  | Test cases: Aid
| Michael |  |  |  | Test cases: Course Difficulty
| Albert |  |  |  | Test cases: Careers
| Michael |  |  |  | Test cases: Schedule of Classes
| Audrey |  |  |  | Test cases: Messaging
| Michael |  |  |  | Test cases: Registration
| Michael |  |  |  | Test cases: Login
| Michael |  |  |  | Test cases: Logout
Sprint 3 | Assigned | To Do | In Progress | Blocked | Done
| Albert |  |  |  | Test case data: student discounts, careers
| Audrey |  |  |  | Test case data: matching, messaging
| Brad |  |  |  | Test case data: schedules, classes
| Joseph |  |  |  | Test case data: aid
| Michael |  |  |  | Test case data: course rating, registration, login, logout
| Audrey |  |  |  | Test plan: testing schedule
| Michael |  |  |  | Detail testing environment
| Joseph |  |  |  | Progression and Regression Testing details
| Joseph |  |  |  | Information gathering: aid, careers, schedule of classes
| Brad |  |  |  | Network Diagram: Choose server provider
| Joseph |  |  |  | Network Diagram: Node system specs
| Albert |  |  |  | Network Diagram: IPs/URLs of external servers
| Audrey |  |  |  | Network Diagram: Requests
| Michael |  |  |  | Network Diagram: Responses
| Albert |  |  |  | Network Diagram: 3rd party services & servers
| Brad |  |  |  | Determine feature development order
| Audrey |  |  |  | Determine critical path tasks
| Michael |  |  |  | Plan deployment process
| Brad |  |  |  | Risk Identification
| Michael |  |  |  | Risk Mitigation
| Joseph |  |  |  | Schedule Project Milestones
| Albert |  |  |  | Schedule Sprints
| Brad |  |  |  | Validate schedule with team
| Albert |  |  |  | Generate Roadmap from schedule