## Project Backlog
Work Item | Priority | Story Point | Internal Due Date | External Due Date
LL Design | 1 | 31 | 2021-12-07 | 2021-12-08
Core Requirements | 2 | 32 | 2021-12-07 | 2021-12-08
UM | 3 | 19 | 2021-12-07 | 2021-12-08
Logging | 4 | 19 | 2021-12-07 | 2021-12-08
Unique Features | 5
Testing
Deployment
Project Proposal | Done | 30 | 2021-09-06 | 2021-09-06
BRD | Done | 37 | 2021-10-06 | 2021-10-06
Site Map | Done | 8.5 | 2021-10-06 | 2021-10-06
HL Design | Done | 7 | 2021-10-06 | 2021-10-06
Tech Spec | Done | 4 | 2021-10-06 | 2021-10-06
Test Cases | Done | 30 | 2021-10-18 | 2021-10-27
Network Diagram | Done | 26 | 2021-10-26 | 2021-10-27
Project Plan | Done | 22 | 2021-10-26 | 2021-10-27
Roadmap | Done | 2 | 2021-10-26 | 2021-10-27
Test Plan | Done | 22 | 2021-10-26 | 2021-10-27
LL Design | Done | 24.5 | 2021-11-12 | 2021-12-08
LL Design | 1 | 46.5 | 2021-11-24 | 2021-12-08
Core Requirements | 2 | 42 | 2021-11-24 | 2021-12-08

## Sprint Backlog
| Priority | Assigned | Story Point | Sprint | Status | Internal Due Date | External Due Date | Work Item Lead | Associated Work Item | 1 Story Point = 1 hour
UM Business Requirements | 1 | Joseph | 1 | 6 | Done | 2021-12-14 | 2021-12-15 | Audrey | BRD
Logging class diagram | 2 | Brad | 3.5 | 6 | Done | 2021-12-14 | 2021-12-15 | Audrey | LL Design
UM sequence diagram | 3 | Audrey | 4 | 6 | Done | 2021-12-14 | 2021-12-15 | Audrey | LL Design | 7 | Albert | 20 | UM
Tech approval: unit testing | 4 | Michael | 4 | 6 | Done | 2021-12-14 | 2021-12-15 | Audrey | LL Design | 7 | Audrey | 20 | UM
Logging behavioral diagram | 5 | Michael | 1 | 6 | Done | 2021-12-14 | 2021-12-15 | Audrey | LL Design | 5 | Brad | 20 | Logging
UM interfaces to other components | 6 | Albert | 2 | 6 | Done | 2021-12-14 | 2021-12-15 | Audrey | LL Design | 9 | Joseph | 19 | UM
Logging interfaces to other components | 7 | Brad | 0.5 | 6 | Done | 2021-12-14 | 2021-12-15 | Audrey | LL Design | 10 | Michael | 22 | Logging
UM Feature Pseudocode | 8 | Albert | 2 | 6 | Done | 2021-12-14 | 2021-12-15 | Audrey | LL Design | 42 | Actual Total | 101
Logging Feature Pseudocode | 9 | Michael | 2 | 6 | Done | 2021-12-14 | 2021-12-15 | Audrey | LL Design | 38
BRD: Authorize | 10 | Audrey | 1 | 6 | Done | 2021-12-14 | 2021-12-15 | Michael | Core Requirements |  | Expected Total | 101 | 20.2
Test: Authorize | 11 | Audrey | 1 | 6 | Done | 2021-12-14 | 2021-12-15 | Michael | Core Requirements
Site Map: Authorize | 12 | Audrey | 1 | 6 | Done | 2021-12-14 | 2021-12-15 | Michael | Core Requirements
BRD: Account Deletion | 13 | Joseph | 1 | 6 | Done | 2021-12-14 | 2021-12-15 | Michael | Core Requirements
Test Cases: Account Deletion | 14 | Joseph | 1 | 6 | Todo | 2021-12-14 | 2021-12-15 | Michael | Core Requirements
Tech approval: ORM | 15 | Joseph | 4 | 6 | Done | 2021-12-14 | 2021-12-15 | Audrey | LL Design
Tech Approval: Cron | 16 | Brad | 4 | 6 | Done | 2021-12-14 | 2021-12-15 | Audrey | LL Design
Implementation: Authorization | 17 | Albert | 2 | 6 | Done | 2021-12-14 | 2021-12-15 | Michael | Core Requirements
Implementation: Authenication | 18 | Audrey | 2 | 6 | Done | 2021-12-14 | 2021-12-15 | Michael | Core Requirements
UM Implementation: Model class: User Account | 19 | Audrey | 1 | 6 | Done | 2021-12-14 | 2021-12-15 | Audrey | UM
UM Implementation: Create accounts | 20 | Joseph | 1 | 6 | Done | 2021-12-14 | 2021-12-15 | Audrey | UM
UM Implementation: Update accounts | 21 | Albert | 1 | 6 | Done | 2021-12-14 | 2021-12-15 | Audrey | UM
UM Implementation: Delete accounts | 22 | Audrey | 1 | 6 | Done | 2021-12-14 | 2021-12-15 | Audrey | UM
UM Implementation: Enable and disable accounts | 23 | Joseph | 1 | 6 | Done | 2021-12-14 | 2021-12-15 | Audrey | UM
UM Implementation: Execute bulk operations | 24 | Albert | 4 | 6 | Done | 2021-12-14 | 2021-12-15 | Audrey | UM
Logging Implementation: Model class: Log | 25 | Brad | 1 | 6 | Done | 2021-12-14 | 2021-12-15 | Brad | Logging
Logging Implementation | 26 | Brad | 8 | 6 | Done | 2021-12-14 | 2021-12-15 | Brad | Logging
Archiving Implementation | 27 | Michael | 4 | 6 | Done | 2021-12-14 | 2021-12-15 | Brad | Logging
Tests: Authorization | 28 | Albert | 2 | 6 | Done | 2021-12-14 | 2021-12-15 | Michael | Core Requirements
Tests: Authentication | 29 | Audrey | 2 | 6 | Done | 2021-12-14 | 2021-12-15 | Michael | Core Requirements
UM Tests: Create | 30 | Joseph | 2 | 6 | Done | 2021-12-14 | 2021-12-15 | Audrey | UM
UM Tests: Update | 31 | Albert | 2 | 6 | Done | 2021-12-14 | 2021-12-15 | Audrey | UM
UM Tests: Delete | 32 | Audrey | 2 | 6 | Done | 2021-12-14 | 2021-12-15 | Audrey | UM
UM Tests: Enable/disable | 33 | Joseph | 2 | 6 | Done | 2021-12-14 | 2021-12-15 | Audrey | UM
UM Tests: Execute bulk operations | 34 | Albert | 2 | 6 | Done | 2021-12-14 | 2021-12-15 | Audrey | UM
Logging Tests | 35 | Michael | 4 | 6 | Done | 2021-12-14 | 2021-12-15 | Brad | Logging
Archiving Tests | 36 | Brad | 2 | 6 | Done | 2021-12-14 | 2021-12-15 | Brad | Logging
Update BRD (feedback) | 37 | Joseph | 2 | 6 | Done | 2021-12-14 | 2021-12-15 | Michael | BRD
Update Test Plan (feedback) | 38 | Michael | 2 | 6 | Done | 2021-12-14 | 2021-12-15 | Michael | Test Plan
Archiving (BRD) | 39 | Michael | 1 | 6 | Done | 2021-12-14 | 2021-12-15 | Michael | Core Requirements
Archiving (Test Plan) | 40 | Michael | 1 | 6 | Done | 2021-12-14 | 2021-12-15 | Michael | Core Requirements
User Access Control (BRD) | 41 | Audrey | 2 | 6 | Done | 2021-12-14 | 2021-12-15 | Michael | Core Requirements
User Access Control (Sitemap) | 42 | Joseph | 1.5 | 6 | Done | 2021-12-14 | 2021-12-15 | Michael | Core Requirements
User Access Control (Test Plan) | 43 | Joseph | 1.5 | 6 | Done | 2021-12-14 | 2021-12-15 | Michael | Core Requirements
Registration (BRD) | 44 | Albert | 1 | 6 | Done | 2021-12-14 | 2021-12-15 | Michael | Core Requirements
Registration (Test Plan) | 45 | Albert | 1 | 6 | Done | 2021-12-14 | 2021-12-15 | Michael | Core Requirements
Compile UM LL Design Document | 46 | Audrey | 2 | 6 | Done | 2021-12-14 | 2021-12-15 | Audrey | LL Design
Compile Logging LL Design Document | 47 | Michael | 2 | 6 | Done | 2021-12-14 | 2021-12-15 | Audrey | LL Design
Review BRD, Tech Spec | 48 | Albert | 1 | 6 | Done | 2021-12-14 | 2021-12-15 | Michael | Core Requirements
Review LL Design Logging, Project Plan | 49 | Audrey | 1 | 6 | Done | 2021-12-14 | 2021-12-15 | Michael | Core Requirements
Review LL Design UM, Network Diagram | 50 | Brad | 1 | 6 | Done | 2021-12-14 | 2021-12-15 | Michael | Core Requirements
Review Test Plan | 51 | Joseph | 1 | 6 | Todo | 2021-12-14 | 2021-12-15 | Michael | Core Requirements
Review Site Map, HL Design | 52 | Michael | 1 | 6 | Done | 2021-12-14 | 2021-12-15 | Michael | Core Requirements
Schedule of Classes
Messaging
Student Discounts
Schedule Builder
Schedule Comparison
Course Reviews
Matching
Career Opportunities
Aid Egilibility
Network Communication
Data Store Access
Logging/Archiving
Registration
Login
Logout
Error Handling
User Management
User Access Control
Usage Analysis Dashboard
Schedule of Classes
Messaging
Student Discounts
Schedule Builder
Schedule Comparison
Course Reviews
Matching
Career Opportunities
Aid Egilibility
Set up Web Server
Set up DataBase
Security Configuration
Deployment
Introduction | Done | Audrey | 1 | 0 | Done | 2021-09-06 | 2021-09-06 | Audrey | Project Proposal
Needs and Problems | Done | Michael | 2 | 0 | Done | 2021-09-06 | 2021-09-06 | Audrey | Project Proposal
Goals and Objective | Done | Joseph | 1 | 0 | Done | 2021-09-06 | 2021-09-06 | Audrey | Project Proposal
Feature: Schedule Builder | Done | Brad | 3 | 0 | Done | 2021-09-06 | 2021-09-06 | Audrey | Project Proposal
Feature: Schedule Comparison | Done | Brad | 3 | 0 | Done | 2021-09-06 | 2021-09-06 | Audrey | Project Proposal
Feature: Course Difficulty | Done | Michael | 3 | 0 | Done | 2021-09-06 | 2021-09-06 | Audrey | Project Proposal
Feature: Matching | Done | Audrey | 3 | 0 | Done | 2021-09-06 | 2021-09-06 | Audrey | Project Proposal
Feture: Student Discounts | Done | Albert | 3 | 0 | Done | 2021-09-06 | 2021-09-06 | Audrey | Project Proposal
Feature: Aid | Done | Joseph | 3 | 0 | Done | 2021-09-06 | 2021-09-06 | Audrey | Project Proposal
Feature: Career Opps | Done | Albert | 3 | 0 | Done | 2021-09-06 | 2021-09-06 | Audrey | Project Proposal
Feature: Schedule of Classes | Done | Michael | 3 | 0 | Done | 2021-09-06 | 2021-09-06 | Audrey | Project Proposal
Feature: Messaging | Done | Brad | 3 | 0 | Done | 2021-09-06 | 2021-09-06 | Audrey | Project Proposal
Obstacles and Solutions | Done | Albert | 2 | 0 | Done | 2021-09-06 | 2021-09-06 | Audrey | Project Proposal
Executive Summary | Done | Joseph | 0.5 | 1 | Done | 2021-10-06 | 2021-10-06 | Albert | BRD
Project Description | Done | Joseph | 0.5 | 1 | Done | 2021-10-06 | 2021-10-06 | Albert | BRD
In Scope | Done | Audrey | 1 | 1 | Done | 2021-10-06 | 2021-10-06 | Albert | BRD
Out of Scope | Done | Michael | 1 | 1 | Done | 2021-10-06 | 2021-10-06 | Albert | BRD
Process - Builder | Done | Brad | 2 | 1 | Done | 2021-10-06 | 2021-10-06 | Albert | BRD
Process - Course Difficulty | Done | Michael | 2 | 1 | Done | 2021-10-06 | 2021-10-06 | Albert | BRD
Process - Matching | Done | Audrey | 2 | 1 | Done | 2021-10-06 | 2021-10-06 | Albert | BRD
Process - Career Opportuinty | Done | Albert | 2 | 1 | Done | 2021-10-06 | 2021-10-06 | Albert | BRD
Process - Aid | Done | Joseph | 2 | 1 | Done | 2021-10-06 | 2021-10-06 | Albert | BRD
Process - Student Discount | Done | Albert | 2 | 1 | Done | 2021-10-06 | 2021-10-06 | Albert | BRD
Process - Comparison | Done | Brad | 2 | 1 | Done | 2021-10-06 | 2021-10-06 | Albert | BRD
Requirements - Builder | Done | Brad | 2 | 1 | Done | 2021-10-06 | 2021-10-06 | Albert | BRD
Requirements - Course Difficulty | Done | Michael | 2 | 1 | Done | 2021-10-06 | 2021-10-06 | Albert | BRD
Requirements - Matching | Done | Audrey | 2 | 1 | Done | 2021-10-06 | 2021-10-06 | Albert | BRD
Requirements - Career Opportuinty | Done | Albert | 2 | 1 | Done | 2021-10-06 | 2021-10-06 | Albert | BRD
Requirements - Aid | Done | Joseph | 2 | 1 | Done | 2021-10-06 | 2021-10-06 | Albert | BRD
Requirements - Student Discount | Done | Albert | 2 | 1 | Done | 2021-10-06 | 2021-10-06 | Albert | BRD
Requirements - Comparison | Done | Brad | 2 | 1 | Done | 2021-10-06 | 2021-10-06 | Albert | BRD
Reuquirements - Messaging | Done | Brad | 2 | 1 | Done | 2021-10-06 | 2021-10-06 | Albert | BRD
Requirements - Schedule of Classes | Done | Michael | 2 | 1 | Done | 2021-10-06 | 2021-10-06 | Albert | BRD
Requirements - Core | Done | Michael | 1 | 1 | Done | 2021-10-06 | 2021-10-06 | Albert | BRD
Glossary | Done | Audrey | 0.5 | 1 | Done | 2021-10-06 | 2021-10-06 | Albert | BRD
Document History | Done | Audrey | 0.5 | 1 | Done | 2021-10-06 | 2021-10-06 | Albert | BRD
Error Handling | Done | Audrey | 4 | 1 | Done | 2021-10-06 | 2021-10-06 | Audrey | Site Map
View - Builder | Done | Brad | 0.5 | 1 | Done | 2021-10-06 | 2021-10-06 | Audrey | Site Map
View Comparison | Done | Brad | 0.5 | 1 | Done | 2021-10-06 | 2021-10-06 | Audrey | Site Map
View - Course Difficulty | Done | Michael | 0.5 | 1 | Done | 2021-10-06 | 2021-10-06 | Audrey | Site Map
View - Matching | Done | Audrey | 0.5 | 1 | Done | 2021-10-06 | 2021-10-06 | Audrey | Site Map
View - Student Discount | Done | Albert | 0.5 | 1 | Done | 2021-10-06 | 2021-10-06 | Audrey | Site Map
View - Aid | Done | Joseph | 0.5 | 1 | Done | 2021-10-06 | 2021-10-06 | Audrey | Site Map
View - Career Opportunity | Done | Albert | 0.5 | 1 | Done | 2021-10-06 | 2021-10-06 | Audrey | Site Map
View - Schedule of Classes | Done | Michael | 0.5 | 1 | Done | 2021-10-06 | 2021-10-06 | Audrey | Site Map
View - Messaging | Done | Brad | 0.5 | 1 | Done | 2021-10-06 | 2021-10-06 | Audrey | Site Map
Software | Done | Brad | 3 | 1 | Done | 2021-10-06 | 2021-10-06 | Brad | HL Design
Hardware | Done | Brad | 3 | 1 | Done | 2021-10-06 | 2021-10-06 | Brad | HL Design
Choose Software and Hardware | Done | Brad | 1 | 1 | Done | 2021-10-06 | 2021-10-06 | Brad | HL Design
OS Requirements | Done | Albert | 1 | 1 | Done | 2021-10-06 | 2021-10-06 | Michael | Tech Spec
Project Requirements | Done | Audrey | 1.5 | 1 | Done | 2021-10-06 | 2021-10-06 | Michael | Tech Spec
Product Requirements | Done | Michael | 1.5 | 1 | Done | 2021-10-06 | 2021-10-06 | Michael | Tech Spec
Phone calls: career center | Done | Joseph | 1 | 2 | Done | 2021-10-18 |  | Joseph
Phone calls: financial aid | Done | Joseph | 1 | 2 | Done | 2021-10-18 |  | Joseph
Phone calls: David Brown (schedule of classes) | Done | Joseph | 1 | 2 | Done | 2021-10-18 |  | Joseph
Test cases: Schedule Building | Done | Brad | 3 | 2 | Done | 2021-10-18 | 2021-10-27 | Joseph | Test Plan
Test cases: Discounts | Done | Albert | 3 | 2 | Done | 2021-10-18 | 2021-10-27 | Joseph | Test Plan
Test cases: Matching | Done | Audrey | 3 | 2 | Done | 2021-10-18 | 2021-10-27 | Joseph | Test Plan
Test cases: Aid | Done | Joseph | 3 | 2 | Done | 2021-10-18 | 2021-10-27 | Joseph | Test Plan
Test cases: Course Difficulty | Done | Michael | 3 | 2 | Done | 2021-10-18 | 2021-10-27 | Joseph | Test Plan
Test cases: Careers | Done | Albert | 3 | 2 | Done | 2021-10-18 | 2021-10-27 | Joseph | Test Plan
Test cases: Schedule of Classes | Done | Brad | 3 | 2 | Done | 2021-10-18 | 2021-10-27 | Joseph | Test Plan
Test cases: Messaging | Done | Audrey | 3 | 2 | Done | 2021-10-18 | 2021-10-27 | Joseph | Test Plan
Test cases: Registration | Done | Michael | 1 | 2 | Done | 2021-10-18 | 2021-10-27 | Joseph | Test Plan
Test cases: Login | Done | Michael | 1 | 2 | Done | 2021-10-18 | 2021-10-27 | Joseph | Test Plan
Test cases: Logout | Done | Michael | 1 | 2 | Done | 2021-10-18 | 2021-10-27 | Joseph | Test Plan
Information gathering: aid, careers, schedule of classes | Done | Joseph | 4 | 3 | Done | 2021-10-26 | 2021-10-27 | Albert | Network Diagram
Network Diagram: Choose server provider | Done | Brad | 4 | 3 | Done | 2021-10-26 | 2021-10-27 | Albert | Network Diagram
Test case data: student discounts, careers | Done | Albert | 2 | 3 | Done | 2021-10-26 | 2021-10-27 | Michael | Test Plan
Test case data: matching, messaging | Done | Audrey | 2 | 3 | Done | 2021-10-26 | 2021-10-27 | Michael | Test Plan
Test case data: schedules, classes | Done | Brad | 2 | 3 | Done | 2021-10-26 | 2021-10-27 | Michael | Test Plan
Test case data: aid | Done | Joseph | 2 | 3 | Done | 2021-10-26 | 2021-10-27 | Michael | Test Plan
Test case data: course rating, registration, login, logout | Done | Michael | 2 | 3 | Done | 2021-10-26 | 2021-10-27 | Michael | Test Plan
Network Diagram: Node system specs | Done | Joseph | 2 | 3 | Done | 2021-10-26 | 2021-10-27 | Albert | Network Diagram
Network Diagram: IPs/URLs of external servers | Done | Albert | 4 | 3 | Done | 2021-10-26 | 2021-10-27 | Albert | Network Diagram
Network Diagram: Requests | Done | Audrey | 4 | 3 | Done | 2021-10-26 | 2021-10-27 | Albert | Network Diagram
Network Diagram: Responses | Done | Michael | 4 | 3 | Done | 2021-10-26 | 2021-10-27 | Albert | Network Diagram
Network Diagram: 3rd party services & servers | Done | Albert | 4 | 3 | Done | 2021-10-26 | 2021-10-27 | Albert | Network Diagram
Determine feature development order | Done | Brad | 4 | 3 | Done | 2021-10-26 | 2021-10-27 | Brad | Project Plan
Determine critical path tasks | Done | Audrey | 4 | 3 | Done | 2021-10-26 | 2021-10-27 | Brad | Project Plan
Plan deployment process | Done | Michael | 4 | 3 | Done | 2021-10-26 | 2021-10-27 | Brad | Project Plan
Risk Identification | Done | Brad | 3 | 3 | Done | 2021-10-26 | 2021-10-27 | Brad | Project Plan
Risk Mitigation | Done | Michael | 2 | 3 | Done | 2021-10-26 | 2021-10-27 | Brad | Project Plan
Schedule Project Milestones | Done | Joseph | 2 | 3 | Done | 2021-10-26 | 2021-10-27 | Brad | Project Plan
Schedule Sprints | Done | Albert | 2 | 3 | Done | 2021-10-26 | 2021-10-27 | Brad | Project Plan
Validate schedule with team | Done | Brad | 1 | 3 | Done | 2021-10-26 | 2021-10-27 | Brad | Project Plan
Generate Roadmap from schedule | Done | Albert | 2 | 3 | Done | 2021-10-26 | 2021-10-27 | Brad | Project Plan
Test plan: testing schedule | Done | Audrey | 4 | 3 | Done | 2021-10-26 | 2021-10-27 | Michael | Test Plan
Detail testing environment | Done | Michael | 4 | 3 | Done | 2021-10-26 | 2021-10-27 | Michael | Test Plan
Progression and Regression Testing details | Done | Joseph | 4 | 3 | Done | 2021-10-26 | 2021-10-27 | Michael | Test Plan
UM Business Requirements | 1 | Joseph | 3 | 4 | Done | 2021-11-12 | 2021-12-08 | Audrey | BRD
Logging Business Requirements | 2 | Brad | 3 | 4 | Done | 2021-11-12 | 2021-12-08 | Audrey | BRD
UM Site Map | 3 | Joseph | 1 | 4 | Done | 2021-11-12 | 2021-12-08 | Audrey | Site Map
UM test plan | 4 | Audrey | 4 | 4 | Done | 2021-11-12 | 2021-12-08 | Audrey | Test Plan
Logging test plan | 5 | Albert | 3.5 | 4 | Done | 2021-11-12 | 2021-12-08 | Audrey | Test Plan
UM class diagram (UML) | 6 | Joseph | 1 | 4 | Done | 2021-11-12 | 2021-12-08 | Audrey | LL Design
Logging class diagram | 7 | Brad | 1 | 4 | Done | 2021-11-12 | 2021-12-08 | Audrey | LL Design
UM sequence diagram | 8 | Audrey | 3 | 4 | Done | 2021-11-12 | 2021-12-08 | Audrey | LL Design
Logging behavioral diagram | 9 | Michael | 5 | 4 | Done | 2021-11-12 | 2021-12-08 | Audrey | LL Design
UM interfaces to other components | 10 | Albert | 0 | 4 | Done | 2021-11-12 | 2021-12-08 | Audrey | LL Design
Logging interfaces to other components | 11 | Brad | 1 | 4 | Done | 2021-11-12 | 2021-12-08 | Audrey | LL Design
UM Feature Pseudocode | 12 | Albert | 0 | 4 | Done | 2021-11-12 | 2021-12-08 | Audrey | LL Design
Logging Feature Pseudocode | 13 | Michael | 0 | 4 | Done | 2021-11-12 | 2021-12-08 | Audrey | LL Design
Compile UM LL Design Document | 14 | Audrey | 0 | 4 | Done | 2021-11-12 | 2021-12-08 | Audrey | LL Design
Compile Logging LL Design Document | 15 | Michael | 0 | 4 | Done | 2021-11-12 | 2021-12-08 | Audrey | LL Design
UM Business Requirements | 1 | Joseph | 1 | 5 | Done | 2021-11-24 | 2021-12-08 | Audrey | BRD
Logging Business Requirements | 2 | Brad | 1 | 5 | Done | 2021-11-24 | 2021-12-08 | Audrey | BRD
UM Site Map | 3 | Joseph | 2 | 5 | Done | 2021-11-24 | 2021-12-08 | Audrey | Site Map
Logging test plan | 4 | Albert | 0.5 | 5 | Done | 2021-11-24 | 2021-12-08 | Audrey | Test Plan
UM class diagram (UML) | 5 | Joseph | 8 | 5 | Done | 2021-11-24 | 2021-12-08 | Audrey | LL Design
Logging class diagram | 6 | Brad | 7 | 5 | Done | 2021-11-24 | 2021-12-08 | Audrey | LL Design
UM sequence diagram | 7 | Audrey | 5 | 5 | Done | 2021-11-24 | 2021-12-08 | Audrey | LL Design
Logging behavioral diagram | 8 | Michael | 3 | 5 | Done | 2021-11-24 | 2021-12-08 | Audrey | LL Design
UM interfaces to other components | 9 | Albert | 2 | 5 | Done | 2021-11-24 | 2021-12-08 | Audrey | LL Design
Logging interfaces to other components | 10 | Brad | 1 | 5 | Done | 2021-11-24 | 2021-12-08 | Audrey | LL Design
UM Feature Pseudocode | 11 | Albert | 6 | 5 | Done | 2021-11-24 | 2021-12-08 | Audrey | LL Design
Logging Feature Pseudocode | 12 | Michael | 6 | 5 | Done | 2021-11-24 | 2021-12-08 | Audrey | LL Design
Compile UM LL Design Document | 13 | Audrey | 2 | 5 | Done | 2021-11-24 | 2021-12-08 | Audrey | LL Design
Compile Logging LL Design Document | 14 | Michael | 2 | 5 | Done | 2021-11-24 | 2021-12-08 | Audrey | LL Design
Update BRD (feedback) | 15 | Joseph | 2 | 5 | Done | 2021-11-24 | 2021-12-08 | Michael | BRD
Update HL Design (feedback) | 16 | Brad | 2 | 5 | Done | 2021-11-24 | 2021-12-08 | Michael | HL Design
Update Network Diagram (feedback) | 17 | Albert | 2 | 5 | Done | 2021-11-24 | 2021-12-08 | Michael | Network Diagram
Update Project Plan (feedback) | 18 | Brad | 2 | 5 | Done | 2021-11-24 | 2021-12-08 | Michael | Project Plan
Update Site Map (feedback) | 19 | Audrey | 2 | 5 | Done | 2021-11-24 | 2021-12-08 | Michael | Site Map
Update Tech Spec (feedback) | 20 | Audrey | 2 | 5 | Done | 2021-11-24 | 2021-12-08 | Michael | Tech Spec
Update Test Plan (feedback) | 21 | Michael | 2 | 5 | Done | 2021-11-24 | 2021-12-08 | Michael | Test Plan
Archiving (BRD) | 22 | Michael | 2 | 5 | Done | 2021-11-24 | 2021-12-08 | Michael | Core Requirements
Archiving (Sitemap) | 23 | Michael | 2 | 5 | Done | 2021-11-24 | 2021-12-08 | Michael | Core Requirements
Archiving (Test Plan) | 24 | Michael | 2 | 5 | Done | 2021-11-24 | 2021-12-08 | Michael | Core Requirements
Error Handling (BRD) | 25 | Albert | 2 | 5 | Done | 2021-11-24 | 2021-12-08 | Michael | BRD
Error Handling (Sitemap) | 26 | Albert | 2 | 5 | Done | 2021-11-24 | 2021-12-08 | Michael | Site Map
Error Handling (Test plan) | 27 | Albert | 2 | 5 | Done | 2021-11-24 | 2021-12-08 | Michael | Test Plan
Logging (Sitemap) | 28 | Brad | 2 | 5 | Done | 2021-11-24 | 2021-12-08 | Michael | Core Requirements
Usage Analysis Dashboard (BRD) | 29 | Audrey | 2 | 5 | Done | 2021-11-24 | 2021-12-08 | Michael | Core Requirements
Usage Analysis Dashboard (Sitemap) | 30 | Brad | 2 | 5 | Done | 2021-11-24 | 2021-12-08 | Michael | Core Requirements
Usage Analysis Dashboard (Test Plan) | 31 | Audrey | 2 | 5 | Done | 2021-11-24 | 2021-12-08 | Michael | Core Requirements
User Access Control (BRD) | 32 | Joseph | 2 | 5 | Done | 2021-11-24 | 2021-12-08 | Michael | Core Requirements
User Access Control (Sitemap) | 33 | Joseph | 2 | 5 | Done | 2021-11-24 | 2021-12-08 | Michael | Core Requirements
User Access Control (Test Plan) | 34 | Joseph | 2 | 5 | Done | 2021-11-24 | 2021-12-08 | Michael | Core Requirements
User Management (Sitemap) | 35 | Audrey | 2 | 5 | Done | 2021-11-24 | 2021-12-08 | Michael | Core Requirements
Login (BRD) | 36 | Audrey | 1 | 5 | Done | 2021-11-24 | 2021-12-08 | Michael | Core Requirements
Login (Test Plan) | 37 | Audrey | 1 | 5 | Done | 2021-11-24 | 2021-12-08 | Michael | Core Requirements
Logout (BRD) | 38 | Brad | 1 | 5 | Done | 2021-11-24 | 2021-12-08 | Michael | Core Requirements
Logout (Test Plan) | 39 | Brad | 1 | 5 | Done | 2021-11-24 | 2021-12-08 | Michael | Core Requirements
Registration (BRD) | 40 | Albert | 1 | 5 | Done | 2021-11-24 | 2021-12-08 | Michael | Core Requirements
Registration (Test Plan) | 41 | Albert | 1 | 5 | Done | 2021-11-24 | 2021-12-08 | Michael | Core Requirements

## Sprint Planning
Sprint 0 | 2021-09-21
| WI | Assigned | SP | Task Breakdown | SP | Assigned | Team Capacity | Team Member | Capacity
| Project Plan | Audrey | 33 | Introduction | 1 | Audrey | 50 | Albert | 10
|  |  |  | Needs and Problems | 2 | Michael | In Capacity | Audrey | 10
|  |  |  | Goals and Objective | 1 | Joseph |  | Brad | 10
|  |  |  | Feature: Schedule Builder | 3 | Brad |  | Joseph | 10
|  |  |  | Feature: Schedule Comparison | 3 | Brad |  | Michael | 10
|  |  |  | Feature: Course Difficulty | 3 | Michael
|  |  |  | Feature: Matching | 3 | Audrey
|  |  |  | Feture: Student Discounts | 3 | Albert
|  |  |  | Feature: Aid | 3 | Joseph
|  |  |  | Feature: Career Opps | 3 | Albert
|  |  |  | Feature: Schedule of Classes | 3 | Michael
|  |  |  | Feature: Messaging | 3 | Brad
|  |  |  | Obstacles and Solutions | 2 | Albert
|  | TOTAL SP Value | 33
Sprint 1 | 2021-09-28
| WI | Assigned | SP | Task Breakdown | SP | Assigned | Team Capacity | Team Member | Capacity
| BRD | Albert | 37 | Executive Summary | 0.5 | Joseph | 73 | Albert | 16
|  |  |  | Project Description | 0.5 | Joseph | In Capacity | Audrey | 15
|  |  |  | In Scope | 1 | Audrey |  | Brad | 20
|  |  |  | Out of Scope | 1 | Michael |  | Joseph | 10
|  |  |  | Process - Builder | 2 | Brad |  | Michael | 12
|  |  |  | Process - Course Difficulty | 2 | Michael
|  |  |  | Process - Matching | 2 | Audrey
|  |  |  | Process - Career Opportuinty | 2 | Albert
|  |  |  | Process - Aid | 2 | Joseph
|  |  |  | Process - Student Discount | 2 | Albert
|  |  |  | Process - Comparison | 2 | Brad
|  |  |  | Requirements - Builder | 2 | Brad
|  |  |  | Requirements - Course Difficulty | 2 | Michael
|  |  |  | Requirements - Matching | 2 | Audrey
|  |  |  | Requirements - Career Opportuinty | 2 | Albert
|  |  |  | Requirements - Aid | 2 | Joseph
|  |  |  | Requirements - Student Discount | 2 | Albert
|  |  |  | Requirements - Comparison | 2 | Brad
|  |  |  | Reuquirements - Messaging | 2 | Brad
|  |  |  | Requirements - Schedule of Classes | 2 | Michael
|  |  |  | Requirements - Core | 1 | Michael
|  |  |  | Glossary | 0.5 | Audrey
|  |  |  | Document History | 0.5 | Audrey
| Site Map | Audrey | 8.5 | Error Handling | 4 | Audrey
|  |  |  | View - Builder | 0.5 | Brad
|  |  |  | View Comparison | 0.5 | Brad
|  |  |  | View - Course Difficulty | 0.5 | Michael
|  |  |  | View - Matching | 0.5 | Audrey
|  |  |  | View - Student Discount | 0.5 | Albert
|  |  |  | View - Aid | 0.5 | Joseph
|  |  |  | View - Career Opportunity | 0.5 | Albert
|  |  |  | View - Schedule of Classes | 0.5 | Michael
|  |  |  | View - Messaging | 0.5 | Brad
| HL Design | Brad | 7 | Software | 3 | Brad
|  |  |  | Hardware | 3 | Brad
|  |  |  | Choose Software and Hardware | 1 | Brad
| Tech Spec | Michael | 4 | OS Requirements | 1 | Albert
|  |  |  | Project Requirements | 1.5 | Audrey
|  |  |  | Product Requirements | 1.5 | Michael
|  | TOTAL SP Value | 56.5
Sprint 2 | 2021-10-12
| WI | Assigned | SP | Task Breakdown | SP | Assigned | Team Capacity | Team Member | Capacity
| Test Cases | Joseph | 30 | Phone calls: career center | 1 | Joseph | 40 | Albert | 8
|  |  |  | Phone calls: financial aid | 1 | Joseph | In Capacity | Audrey | 8
|  |  |  | Phone calls: David Brown (schedule of classes) | 1 | Joseph |  | Brad | 8
|  |  |  | Test cases: Schedule Building | 3 | Brad |  | Joseph | 8
|  |  |  | Test cases: Discounts | 3 | Albert |  | Michael | 8
|  |  |  | Test cases: Matching | 3 | Audrey
|  |  |  | Test cases: Aid | 3 | Joseph
|  |  |  | Test cases: Course Difficulty | 3 | Michael
|  |  |  | Test cases: Careers | 3 | Albert
|  |  |  | Test cases: Schedule of Classes | 3 | Michael
|  |  |  | Test cases: Messaging | 3 | Audrey
|  |  |  | Test cases: Registration | 1 | Michael
|  |  |  | Test cases: Login | 1 | Michael
|  |  |  | Test cases: Logout | 1 | Michael
|  | TOTAL SP Value | 30
Sprint 3 | 2021-10-20
| WI | Assigned | SP | Task Breakdown | SP | Assigned | Team Capacity | Team Member | Capacity
| Test Plan | Michael | 22 | Test case data: student discounts, careers | 2 | Albert | 90 | Albert | 18
|  |  |  | Test case data: matching, messaging | 2 | Audrey | In Capacity | Audrey | 18
|  |  |  | Test case data: schedules, classes | 2 | Brad |  | Brad | 18
|  |  |  | Test case data: aid | 2 | Joseph |  | Joseph | 18
|  |  |  | Test case data: course rating, registration, login, logout | 2 | Michael |  | Michael | 18
|  |  |  | Test plan: testing schedule | 4 | Audrey
|  |  |  | Detail testing environment | 4 | Michael
|  |  |  | Progression and Regression Testing details | 4 | Joseph
| Network Diagram | Albert | 26 | Information gathering: aid, careers, schedule of classes | 4 | Joseph
|  |  |  | Network Diagram: Choose server provider | 4 | Brad
|  |  |  | Network Diagram: Node system specs | 2 | Joseph
|  |  |  | Network Diagram: IPs/URLs of external servers | 4 | Albert
|  |  |  | Network Diagram: Requests | 4 | Audrey
|  |  |  | Network Diagram: Responses | 4 | Michael
|  |  |  | Network Diagram: 3rd party services & servers | 4 | Albert
| Project Plan | Brad | 22 | Determine feature development order | 4 | Brad
|  |  |  | Determine critical path tasks | 4 | Audrey
|  |  |  | Plan deployment process | 4 | Michael
|  |  |  | Risk Identification | 3 | Brad
|  |  |  | Risk Mitigation | 2 | Michael
|  |  |  | Schedule Project Milestones | 2 | Joseph
|  |  |  | Schedule Sprints | 2 | Albert
|  |  |  | Validate schedule with team | 1 | Brad
| Roadmap | Brad | 2 | Generate Roadmap from schedule | 2 | Albert
|  | TOTAL SP Value | 72
Sprint 4 | 2021-11-04
| WI | Assigned | SP | Task Breakdown | SP | Assigned | Team Capacity | Team Member | Capacity
| LL Desgin | Audrey | 71 | UM Business Requirements | 4 | Joseph | 80 | Albert | 16
|  |  |  | Logging Business Requirements | 4 | Brad | In Capacity | Audrey | 16
|  |  |  | UM Site Map | 3 | Joseph |  | Brad | 16
|  |  |  | UM test plan | 4 | Audrey |  | Joseph | 16
|  |  |  | Logging test plan | 4 | Albert |  | Michael | 16
|  |  |  | UM class diagram (UML) | 8 | Joseph
|  |  |  | Logging class diagram | 8 | Brad
|  |  |  | UM behavioral diagram | 8 | Audrey
|  |  |  | Logging behavioral diagram | 8 | Michael
|  |  |  | UM interfaces to other components | 2 | Albert
|  |  |  | Logging interfaces to other components | 2 | Brad
|  |  |  | UM Feature Pseudocode | 6 | Albert
|  |  |  | Logging Feature Pseudocode | 6 | Michael
|  |  |  | Compile UM LL Design Document | 2 | Audrey
|  |  |  | Compile Logging LL Design Document | 2 | Michael
|  | TOTAL SP Value | 71
Sprint 5 | 2021-11-14
| WI | Assigned | SP | Task Breakdown | SP | Assigned | Team Capacity | Team Member | Capacity
| LL Desgin | Audrey | 46.5 | UM Business Requirements | 1 | Joseph | 100 | Albert | 20
|  |  |  | Logging Business Requirements | 1 | Brad | In Capacity | Audrey | 20
|  |  |  | UM Site Map | 2 | Joseph |  | Brad | 20
|  |  |  | Logging test plan | 0.5 | Albert |  | Joseph | 20
|  |  |  | UM class diagram (UML) | 8 | Joseph |  | Michael | 20
|  |  |  | Logging class diagram | 7 | Brad
|  |  |  | UM sequence diagram | 5 | Audrey
|  |  |  | Logging behavioral diagram | 3 | Michael
|  |  |  | UM interfaces to other components | 2 | Albert
|  |  |  | Logging interfaces to other components | 1 | Brad
|  |  |  | UM Feature Pseudocode | 6 | Albert
|  |  |  | Logging Feature Pseudocode | 6 | Michael
|  |  |  | Compile UM LL Design Document | 2 | Audrey
|  |  |  | Compile Logging LL Design Document | 2 | Michael
| Core Components | Michael | 48 | Update BRD (feedback) | 2 | Joseph
|  |  |  | Update HL Design (feedback) | 2 | Brad
|  |  |  | Update Network Diagram (feedback) | 2 | Albert
|  |  |  | Update Project Plan (feedback) | 2 | Brad
|  |  |  | Update Site Map (feedback) | 2 | Audrey
|  |  |  | Update Tech Spec (feedback) | 2 | Audrey
|  |  |  | Update Test Plan (feedback) | 2 | Michael
|  |  |  | Archiving (BRD) | 2 | Michael
|  |  |  | Archiving (Sitemap) | 2 | Michael
|  |  |  | Archiving (Test Plan) | 2 | Michael
|  |  |  | Error Handling (BRD) | 2 | Albert
|  |  |  | Error Handling (Sitemap) | 2 | Albert
|  |  |  | Error Handling (Test Plan) | 2 | Albert
|  |  |  | Logging (Sitemap) | 2 | Brad
|  |  |  | Usage Analysis Dashboard (BRD) | 2 | Audrey
|  |  |  | Usage Analysis Dashboard (Sitemap) | 2 | Brad
|  |  |  | Usage Analysis Dashboard (Test Plan) | 2 | Audrey
|  |  |  | User Access Control (BRD) | 2 | Joseph
|  |  |  | User Access Control (Sitemap) | 2 | Joseph
|  |  |  | User Access Control (Test Plan) | 2 | Joseph
|  |  |  | User Management (Sitemap) | 2 | Audrey
|  |  |  | Registration (BRD) | 1 | Albert
|  |  |  | Registration (Test Plan) | 1 | Albert
|  |  |  | Login (BRD) | 1 | Audrey
|  |  |  | Login (Test Plan) | 1 | Audrey
|  |  |  | Logout (BRD) | 1 | Brad
|  |  |  | Logout (Test Plan) | 1 | Brad
|  | TOTAL SP Value | 94.5
Sprint 6 | 2021-11-28
| WI | Assigned | SP | Task Breakdown | SP | Assigned | Team Capacity | Team Member | Capacity
| LL Design | Audrey | 31 | Tech approval: unit testing | 4 | Michael | 112 | Albert | 22
|  |  |  | Tech approval: ORM | 4 | Joseph | In Capacity | Audrey | 22
|  |  |  | Tech Approval: Cron | 4 | Brad |  | Brad | 22
|  |  |  | Logging class diagram | 3.5 | Brad |  | Joseph | 22
|  |  |  | UM sequence diagram | 4 | Audrey |  | Michael | 24
|  |  |  | Logging behavioral diagram | 1 | Michael
|  |  |  | UM interfaces to other components | 2 | Albert
|  |  |  | Logging interfaces to other components | 0.5 | Brad
|  |  |  | UM Feature Pseudocode | 2 | Albert
|  |  |  | Logging Feature Pseudocode | 2 | Michael
|  |  |  | Compile UM LL Design Document | 2 | Audrey
|  |  |  | Compile Logging LL Design Document | 2 | Michael
| Core Components | Michael | 32 | UM Business Requirements | 1 | Joseph
|  |  |  | Update BRD (feedback) | 2 | Joseph
|  |  |  | Update Test Plan (feedback) | 2 | Michael
|  |  |  | BRD: Authorize | 1 | Audrey
|  |  |  | Test: Authorize | 1 | Audrey
|  |  |  | Site Map: Authorize | 1 | Audrey
|  |  |  | BRD: Account Deletion | 1 | Joseph
|  |  |  | Test Cases: Account Deletion | 1 | Joseph
|  |  |  | Implementation: Authorization | 2 | Albert
|  |  |  | Implementation: Authenication | 2 | Audrey
|  |  |  | Tests: Authorization | 2 | Albert
|  |  |  | Tests: Authentication | 2 | Audrey
|  |  |  | Archiving (BRD) | 1 | Michael
|  |  |  | Archiving (Test Plan) | 1 | Michael
|  |  |  | User Access Control (BRD) | 2 | Audrey
|  |  |  | User Access Control (Sitemap) | 1.5 | Joseph
|  |  |  | User Access Control (Test Plan) | 1.5 | Joseph
|  |  |  | Registration (BRD) | 1 | Albert
|  |  |  | Registration (Test Plan) | 1 | Albert
|  |  |  | Review BRD, Tech Spec | 1 | Albert
|  |  |  | Review LL Design Logging, Project Plan | 1 | Audrey
|  |  |  | Review LL Design UM, Network Diagram | 1 | Brad
|  |  |  | Review Test Plan | 1 | Joseph
|  |  |  | Review Site Map, HL Design | 1 | Michael
| UM | Audrey | 19 | UM Implementation: Model class: User Account | 1 | Audrey
|  |  |  | UM Implementation: Create | 1 | Joseph
|  |  |  | UM Implementation: Update | 1 | Albert
|  |  |  | UM Implementation: Delete | 1 | Audrey
|  |  |  | UM Implementation: Enable/disable | 1 | Joseph
|  |  |  | UM Implementation: Execute bulk operations | 4 | Albert
|  |  |  | UM Tests: Create | 2 | Joseph
|  |  |  | UM Tests: Update | 2 | Albert
|  |  |  | UM Tests: Delete | 2 | Audrey
|  |  |  | UM Tests: Enable/disable | 2 | Joseph
|  |  |  | UM Tests: Execute bulk operations | 2 | Albert
| Logging | Brad | 19 | Logging Implementation: Model class: Log | 1 | Brad
|  |  |  | Logging Implementation | 8 | Brad
|  |  |  | Archiving Implementation | 4 | Michael
|  |  |  | Logging Tests | 4 | Michael
|  |  |  | Archiving Tests | 2 | Brad
|  | TOTAL SP Value | 101

## Sprint 4
Sprint 4
| Start Date | 2021-11-05 |  | Day of Sprint | Actual Effort |  |  | Day of Sprint | Forecast | Actual
| End Date | 2021-11-12 |  | 0 | 71 |  |  | 0 | 71 | 71
| Sprint Length | 8 |  | 1 | 69 |  |  | 1 | 62.125 | 69
| Team Size | 5 |  | 2 | 69 |  |  | 2 | 53.25 | 69
| Team Capacity | 80 |  | 3 | 69 |  |  | 3 | 44.375 | 69
| Total Sprint SP | 71 |  | 4 | 65.5 |  |  | 4 | 35.5 | 65.5
| SP/Day | 8.875 |  | 5 | 63.5 |  |  | 5 | 26.625 | 63.5
|  |  |  | 6 | 57.5 |  |  | 6 | 17.75 | 57.5
|  |  |  | 7 | 53.5 |  |  | 7 | 8.875 | 53.5
|  |  |  | 8 | 46.5 |  |  | 8 | 0 | 46.5
|  |  |  | f | s | s | m | t | w | t | f
Who | Tasks | SP | Day of Sprint (hours worked)
|  |  | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8
Albert
| Logging test plan | 4 | 0 | 1 | 0 | 0 | 2 | 0 | 1.5 | 1 | 1
| UM interfaces to other components | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| UM Feature Pseudocode | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SP Decrement |  |  | 0 | 0.5 | 0 | 0 | 1 | 0 | 1 | 0.5 | 0.5
Audrey
| UM test plan | 4 | 0 | 1 | 0 | 0 | 1.5 | 0 | 1.5 | 2.5 | 1
| UM sequence diagram | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0.5 | 2.5
| Compile UM LL Design Document | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5
SP Decrement |  |  | 0 | 0.5 | 0 | 0 | 0.5 | 0 | 1 | 1.5 | 3.5
Brad
| Logging Business Requirements | 4 | 0 | 1 | 0 | 0.25 | 1 | 0 | 1 | 0 | 0
| Logging class diagram | 8 | 0 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 2.5
| Logging interfaces to other components | 2 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 1.75
SP Decrement |  |  | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 2
Joseph
| UM Business Requirements | 4 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0
| UM Site Map | 3 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1
| UM class diagram (UML) | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1
SP Decrement |  |  | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1
Michael
| Logging behavioral diagram | 8 | 0 | 0 | 0 | 0 | 3 | 2 | 3 | 2 | 0
| Logging Feature Pseudocode | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Compile Logging LL Design Document | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SP Decrement |  |  | 0 | 0 | 0 | 0 | 1 | 1 | 2 | 1 | 0
Daily Scrum Meeting
Day of Sprint | Who | What did you work on Yesterday? | Day of Sprint (hours worked) 2: What are you working on today?; Day of Sprint (hours worked) 5: Are You Blocked?
Day 1 | Albert | n/a | Day of Sprint (hours worked) 2: logging test plan; Day of Sprint (hours worked) 5: No
| Audrey | n/a | Day of Sprint (hours worked) 2: um test plan; Day of Sprint (hours worked) 5: no
| Brad | n/a | Day of Sprint (hours worked) 2: Logging business requirements; Day of Sprint (hours worked) 5: No
| Joseph | n/a | Day of Sprint (hours worked) 2: Um business requirements; Day of Sprint (hours worked) 5: no
| Michael | n/a | Day of Sprint (hours worked) 2: n/a; Day of Sprint (hours worked) 5: yes
Day 2 | Albert | logging test plan | Day of Sprint (hours worked) 2: n/a; Day of Sprint (hours worked) 5: No
| Audrey | um test plan | Day of Sprint (hours worked) 2: n/a; Day of Sprint (hours worked) 5: no
| Brad | Logging business requirements | Day of Sprint (hours worked) 2: n/a; Day of Sprint (hours worked) 5: No
| Joseph | Um business requirements | Day of Sprint (hours worked) 2: UM business requirements; Day of Sprint (hours worked) 5: No
| Michael | n/a | Day of Sprint (hours worked) 2: n/a; Day of Sprint (hours worked) 5: yes
Day 3 | Albert | n/a | Day of Sprint (hours worked) 2: n/a; Day of Sprint (hours worked) 5: Yes
| Audrey | n/a | Day of Sprint (hours worked) 2: n/a; Day of Sprint (hours worked) 5: no
| Brad | n/a | Day of Sprint (hours worked) 2: Logging business requirements; Day of Sprint (hours worked) 5: No
| Joseph | UM business requirements | Day of Sprint (hours worked) 2: UM Business Requirments; Day of Sprint (hours worked) 5: No
| Michael | n/a | Day of Sprint (hours worked) 2: Logging Behavioral Diagram; Day of Sprint (hours worked) 5: yes
Day 4 | Albert | n/a | Day of Sprint (hours worked) 2: logging test plan; Day of Sprint (hours worked) 5: No
| Audrey | n/a | Day of Sprint (hours worked) 2: um test plan; Day of Sprint (hours worked) 5: no
| Brad | Logging business requirements | Day of Sprint (hours worked) 2: Logging business requirements; Day of Sprint (hours worked) 5: No
| Joseph | UM Business Requirments | Day of Sprint (hours worked) 2: UM Business Requirments, UM site map; Day of Sprint (hours worked) 5: No
| Michael | Logging Behavioral Diagram | Day of Sprint (hours worked) 2: Logging Behavioral Diagram; Day of Sprint (hours worked) 5: no
Day 5 | Albert | logging test plan | bar: Day of Sprint (hours worked) 5
| Audrey | um test plan | Day of Sprint (hours worked) 2: n/a; Day of Sprint (hours worked) 5: no
| Brad | Logging business requirements | Day of Sprint (hours worked) 2: n/a; Day of Sprint (hours worked) 5: no
| Joseph | UM Business Requirments, UM site map | Day of Sprint (hours worked) 2: UM Business Requirments, UM site map; Day of Sprint (hours worked) 5: No
| Michael | Logging Behavioral Diagram | Day of Sprint (hours worked) 2: Logging Behavioral Diagram; Day of Sprint (hours worked) 5: no
Day 6 | Albert | n/a | Day of Sprint (hours worked) 2: logging test plan; Day of Sprint (hours worked) 5: no
| Audrey | n/a | Day of Sprint (hours worked) 2: um test plan, um sequence diagram; Day of Sprint (hours worked) 5: no
| Brad | n/a | Day of Sprint (hours worked) 2: logging: class info, LL design; Day of Sprint (hours worked) 5: no
| Joseph | UM Business Requirments, UM site map | Day of Sprint (hours worked) 2: UM site map, class design; Day of Sprint (hours worked) 5: no
| Michael | Logging Behavioral Diagram | Day of Sprint (hours worked) 2: logging behavioral diagram; Day of Sprint (hours worked) 5: no
Day 7 | Albert | logging test plan | Day of Sprint (hours worked) 2: logging test plan; Day of Sprint (hours worked) 5: no
| Audrey | um test plan, um sequence diagram | Day of Sprint (hours worked) 2: um test plan, um sequence diagram; Day of Sprint (hours worked) 5: yes
| Brad | logging: class info, LL design | Day of Sprint (hours worked) 2: n/a; Day of Sprint (hours worked) 5: no
| Joseph | UM site map, class design | Day of Sprint (hours worked) 2: UM site map, class design; Day of Sprint (hours worked) 5: no
| Michael | logging behavioral diagram | Day of Sprint (hours worked) 2: logging behavioral diagram; Day of Sprint (hours worked) 5: no
Day 8 | Albert | logging test plan | Day of Sprint (hours worked) 2: logging test plan; Day of Sprint (hours worked) 5: no
| Audrey | um test plan, um sequence diagram | Day of Sprint (hours worked) 2: um test plan, um sequence diagram, LL desgin; Day of Sprint (hours worked) 5: yes
| Brad | n/a | Day of Sprint (hours worked) 2: logging: LL design & class info; Day of Sprint (hours worked) 5: no
| Joseph | UM site map, class design | Day of Sprint (hours worked) 2: UM site map, class design; Day of Sprint (hours worked) 5: no
| Michael | logging behavioral diagram | Day of Sprint (hours worked) 2: n/a; Day of Sprint (hours worked) 5: no

## Sprint 5
Sprint 5
| Start Date | 2021-11-15 |  | Day of Sprint | Actual Effort |  |  | Day of Sprint | Forecast | Actual
| End Date | 2021-11-24 |  | 0 | 94.5 |  |  | 0 | 94.5 | 94.5
| Sprint Length | 10 |  | 1 | 88.5 |  |  | 1 | 85.05 | 88.5
| Team Size | 5 |  | 2 | 83.25 |  |  | 2 | 75.6 | 83.25
| Team Capacity | 100 |  | 3 | 75 |  |  | 3 | 66.15 | 75
| Total Sprint SP | 94.5 |  | 4 | 72.5 |  |  | 4 | 56.7 | 72.5
| SP/Day | 9.45 |  | 5 | 67.25 |  |  | 5 | 47.25 | 67.25
|  |  |  | 6 | 61.25 |  |  | 6 | 37.8 | 61.25
|  |  |  | 7 | 53.5 |  |  | 7 | 28.35 | 53.5
|  |  |  | 8 | 49.25 |  |  | 8 | 18.9 | 49.25
|  |  |  | 9 | 45.75 |  |  | 9 | 9.45 | 45.75
|  |  |  | 10 | 33 |  |  | 10 | 0 | 33
|  |  |  | m | t | w | th | f | s | s | m | t | w
Who | Tasks | SP | Day of Sprint (hours worked)
|  |  | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10
Albert
| Logging test plan | 0.5 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Error Handling (BRD) | 2 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Error Handling (Sitemap) | 2 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0
| Error Handling (Test Plan) | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0
| UM interfaces to other components | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| UM Feature Pseudocode | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Update Network Diagram (feedback) | 2 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1
| Registration (BRD) | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Registration (Test Plan) | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SP Decrement |  |  | 0 | 1.5 | 1.25 | 1.25 | 0 | 2 | 2 | 2 | 0.5 | 0.5 | 1.5
Audrey
| UM sequence diagram | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0
| Compile UM LL Design Document | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0
| Update Site Map (feedback) | 2 | 0 | 0.75 | 0.5 | 0.25 | 0 | 0 | 1 | 0 | 0 | 0 | 1
| Update Tech Spec (feedback) | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 2
| Usage Analysis Dashboard (BRD) | 2 | 0 | 0 | 0.5 | 0.5 | 0 | 0 | 0.5 | 0 | 0 | 0 | 0.5
| Usage Analysis Dashboard (Test Plan) | 2 | 0 | 0 | 0 | 0.25 | 0 | 0 | 0.5 | 1 | 0 | 0 | 0.5
| User Management (Sitemap) | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5
| Login (BRD) | 1 | 0 | 0.75 | 1 | 0.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Login (Test Plan) | 1 | 0 | 0 | 0 | 0.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SP Decrement |  |  | 0 | 0.5 | 1 | 2.5 | 0 | 0 | 1 | 1 | 0 | 1 | 6
Brad
| Logging Business Requirements | 1 | 0 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Logging class diagram | 7 | 0 | 0 | 0 | 0.5 | 1 | 0.5 | 0 | 0 | 0 | 0 | 0
| Logging interfaces to other components | 1 | 0 | 0 | 0 | 0.5 | 1 | 0.5 | 0 | 0 | 0 | 0 | 0
| Update HL Design (feedback) | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 0
| Update Project Plan (feedback) | 2 | 0 | 0 | 0 | 0.5 | 0 | 0 | 0.25 | 1 | 0 | 0 | 0
| Logging (Sitemap) | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0.25 | 0 | 0.25 | 0 | 0
| Usage Analysis Dashboard (Sitemap) | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0.5 | 0.5 | 0 | 0
| Logout (BRD) | 1 | 0 | 0 | 0.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Logout (Test Plan) | 1 | 0 | 0 | 0.25 | 0 | 0 | 0 | 0 | 0.25 | 0 | 0 | 0
SP Decrement |  |  | 0 | 0 | 2 | 3 | 2 | 2 | 1.5 | 2.25 | 2.25 | 0 | 0
Joseph
| UM Business Requirements | 1 | 0 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| UM Site Map | 2 | 0 | 0.5 | 0 | 0.5 | 0 | 0.5 | 0 | 0 | 0.25 | 0 | 0.5
| UM class diagram (UML) | 8 | 0 | 0.5 | 0 | 0.5 | 0 | 0.5 | 0 | 0 | 0.25 | 0.5 | 4
| Update BRD (feedback) | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| User Access Control (BRD) | 2 | 0 | 0 | 0 | 0 | 0 | 0.25 | 0 | 0.5 | 0 | 0 | 0
| User Access Control (Sitemap) | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0.25 | 0 | 0 | 0 | 0
| User Access Control (Test Plan) | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0.25 | 0 | 0.25 | 0.25 | 0
SP Decrement |  |  | 0 | 2 | 0.5 | 1 | 0 | 0.75 | 0.5 | 0.5 | 0.5 | 1 | 4.25
Michael
| Logging behavioral diagram | 3 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Logging Feature Pseudocode | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1
| Compile Logging LL Design Document | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Update Test Plan (feedback) | 2 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0
| Archiving (BRD) | 2 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Archiving (Sitemap) | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Archiving (Test Plan) | 2 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0
SP Decrement |  |  | 0 | 2 | 0.5 | 0.5 | 0.5 | 0.5 | 1 | 2 | 1 | 1 | 1
|  |  | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10
Daily Scrum Meeting
Day of Sprint | Who | What did you work on Yesterday? | 2: What are you working on today?; 5: Are You Blocked?
Day 1 | Albert | n/a | 2: logging test plan; 5: no
| Audrey | n/a | 2: feedback for site map, Login BRD; 5: no
| Brad | n/a | 2: n/a; 5: no
| Joseph | n/a | 2: UM site map, UM class diagram; 5: no
| Michael | n/a | 2: logging behavior diagram, archiving BRD; 5: no
Day 2 | Albert | logging test plan | 2: logging test plan, error handling BRD; 5: no
| Audrey | n/a | 2: feedback for site map, BRD for login and usage management dashboard; 5: no
| Brad | n/a | 2: BRD (Logging, logout), test plan (logout), logging class diagram; 5: no
| Joseph | UM site map, UM class diagram | 2: UM business requirements; 5: no
| Michael | logging behavior diagram, archiving BRD | 2: archiving BRD; 5: no
Day 3 | Albert | logging test plan, error handling BRD | 2: logging test plan, error handling site map; 5: no
| Audrey | feedback for site map, BRD for login and usage management dashboard | 2: feedback for site map, BRD for login and usage management dashboard, test cases for login and UMD; 5: no
| Brad | BRD (Logging, logout), test plan (logout), logging class diagram | 2: feedback (project plan); 5: no
| Joseph | UM business requirements | 2: UM site map, UM class diagram; 5: no
| Michael | archiving BRD | 2: archiving test plan; 5: no
Day 4 | Albert | logging test plan, error handling site map | 2: n/a; 5: no
| Audrey | feedback for site map, BRD for login and usage management dashboard, test cases for login and UMD | 2: n/a; 5: no
| Brad | feedback (project plan) | 2: logging class diagrams, logging to other interfaces; 5: no
| Joseph | UM site map, UM class diagram | 2: n/a; 5: no
| Michael | archiving test plan | 2: n/a; 5: no
Day 5 | Albert | n/a | 2: error handling site map, update network diagram; 5: no
| Audrey | n/a | 2: n/a; 5: no
| Brad | logging class diagrams, logging to other interfaces | 2: logging class diagrams, logging to other interfaces; 5: no
| Joseph | n/a | 2: UM site map, UM class diagram, user access control brd; 5: no
| Michael | n/a | 2: update test plan; 5: no
Day 6 | Albert | error handling site map, update network diagram | 2: error handling site map, update network diagram; 5: no
| Audrey | n/a | 2: update site map, usage analysis dashboard brd and test plan; 5: no
| Brad | logging class diagrams, logging to other interfaces | 2: update project plan, sitemap for looging and usage analysis dashboard; 5: no
| Joseph | UM site map, UM class diagram, user access control brd | 2: user access control test plan and sitemap; 5: no
| Michael | update test plan | 2: update test plan; 5: no
Day 7 | Albert | error handling site map, update network diagram | 2: error handling site map, update network diagram; 5: no
| Audrey | update site map, usage analysis dashboard brd and test plan | 2: update tech spec, usage analysis dashboard test plan; 5: no
| Brad | update project plan, sitemap for looging and usage analysis dashboard | 2: update project plan, sitemap for usage analysis dashboard, logout test plan; 5: no
| Joseph | user access control test plan and sitemap | 2: user access control brd; 5: no
| Michael | update test plan | 2: update test plan; 5: no
Day 8 | Albert | error handling site map, update network diagram | 2: update network diagram; 5: no
| Audrey | update tech spec, usage analysis dashboard test plan | 2: n/a; 5: no
| Brad | update project plan, sitemap for usage analysis dashboard, logout test plan | 2: update HL design, sitemap for logging and usage analysis dashboard; 5: no
| Joseph | user access control brd | 2: UM site map and class diagram, user access control test plan; 5: no
| Michael | update test plan | 2: logging pseudocode; 5: no
Day 9 | Albert | update network diagram | 2: update network diagram; 5: no
| Audrey | n/a | 2: UM sequence diagram, compile LL desgin UM; 5: no
| Brad | update HL design, sitemap for logging and usage analysis dashboard | 2: n/a; 5: no
| Joseph | UM site map and class diagram, user access control test plan | 2: UM class diagram, user access control test plan; 5: no
| Michael | logging pseudocode | 2: logging pseudocode; 5: no
Day 10 | Albert | update network diagram | 2: update network diagram; 5: no
| Audrey | UM sequence diagram, compile LL desgin UM | 2: update tech spec and site map, UAD test plan, BRD,UM site map; 5: no
| Brad | n/a | 2: n/a; 5: no
| Joseph | UM class diagram, user access control test plan | 2: UM site map and class diagram; 5: no
| Michael | logging pseudocode | 2: logging pseudocode; 5: no

## Sprint 6
Sprint 6
| Start Date | 2021-11-29 |  | Day of Sprint | Actual Effort |  |  | Day of Sprint | Forecast | Actual
| End Date | 2021-12-14 |  | 0 | 101 |  |  | 0 | 101 | 101
| Sprint Length | 16 |  | 1 | 98 |  |  | 1 | 94.6875 | 98
| Team Size | 5 |  | 2 | 92.5 |  |  | 2 | 88.375 | 92.5
| Team Capacity | 112 |  | 3 | 86.75 |  |  | 3 | 82.0625 | 86.75
| Total Sprint SP | 101 |  | 4 | 82.5 |  |  | 4 | 75.75 | 82.5
| SP/Day | 6.3125 |  | 5 | 81.5 |  |  | 5 | 69.4375 | 81.5
|  |  |  | 6 | 81.5 |  |  | 6 | 63.125 | 81.5
|  |  |  | 7 | 77.5 |  |  | 7 | 56.8125 | 77.5
|  |  |  | 8 | 74.5 |  |  | 8 | 50.5 | 74.5
|  |  |  | 9 | 68 |  |  | 9 | 44.1875 | 68
|  |  |  | 10 | 59.5 |  |  | 10 | 37.875 | 59.5
|  |  |  | 11 | 56.5 |  |  | 11 | 31.5625 | 56.5
|  |  |  | 12 | 49 |  |  | 12 | 25.25 | 49
|  |  |  | 13 | 42.5 |  |  | 13 | 18.9375 | 42.5
|  |  |  | 14 | 33.5 |  |  | 14 | 12.625 | 33.5
|  |  |  | 15 | 19 |  |  | 15 | 6.3125 | 19
|  |  |  | 16 | 0 |  |  | 16 | 0 | 0
|  |  |  | m | t | w | th | f | s | s | m | t | w | t | f | s | s | m | t
Who | Tasks | Day of Sprint (hours worked)
|  |  | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16
Albert
| UM interfaces to other components | 2 | 0 | 0 | 1 | 0 | 1.5 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0
| UM Feature Pseudocode | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0
| Registration (BRD) | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0
| Registration (Test Plan) | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0
| Review BRD, Tech Spec | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0
| UM Implementation: Update | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0
| UM Implementation: Execute bulk operations | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0
| Implemetation: Authorization | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0
| UM Tests: Bulk Operations | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3
| Tests: Authorization | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3
| Tests: Update | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0
SP Decrement |  |  | 0 | 0 | 0.5 | 1 | 1 | 0 | 0 | 0 | 0.5 | 1.5 | 1 | 0.5 | 3 | 3 | 3 | 3 | 3
Audrey
| UM sequence diagram | 4 | 0 | 2 | 0 | 2 | 2 | 0 | 0 | 0 | 4 | 3.5 | 0.5 | 1.5 | 0.5 | 0 | 0 | 0 | 0
| Compile UM LL Design Document | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 0 | 0 | 0.5 | 0 | 0 | 0 | 0
| Review LL Design Logging, Project Plan | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0.5
| UM Implementation: Model class: User Account | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0.25 | 0 | 0
| UM Implementation: Delete | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 2 | 1
| Implementation: Authentication | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 2 | 2 | 1
| Tests: Authenication | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
| BRD: User Access Control | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
| UM Tests: Delete | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
| BRD: Authorize | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0
| Test Cases: Authorize | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0
| Site Map: Authorize | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0
SP Decrement |  |  | 0 | 1 | 0 | 0.25 | 0.25 | 0 | 0 | 0 | 0.5 | 2 | 4 | 0.5 | 1.5 | 1.5 | 2 | 1.5 | 5
Brad
| Logging class diagram | 3.5 | 0 | 0 | 0 | 4 | 2 | 2 | 0 | 3 | 4 | 2 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0
| Tech Approval: Cron | 4 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Logging interfaces to other components | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Review LL Design UM, Network Diagram | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5
| Logging Implementation: Model class: Log | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0
| Logging Implementation | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 1
| Archiving Tests | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2
SP Decrement |  | 20 | 0 | 0 | 2 | 0.5 | 0.5 | 0.5 | 0 | 1 | 0.5 | 1 | 0 | 0 | 2 | 0 | 1 | 6 | 5
Joseph
| UM Business Requirements | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0
| Update BRD (feedback) | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0
| Tech Approval: ORM | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0
| UM Tests: Enable/disable | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 2
| User Access Control (Sitemap) | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 2
| User Access Control (Test Plan) | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 1 | 1 | 1 | 1 | 2
| Review Test Plan | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 0 | 1 | 1 | 0
| UM Implementation: Create | 1 | 0 | 3 | 2 | 3 | 1 | 3 | 0 | 3 | 2 | 0 | 2 | 0 | 2 | 0 | 1 | 1 | 2
| UM Implementation: Enable/disable | 1 | 0 | 2 | 2 | 3 | 1 | 3 | 0 | 3 | 2 | 0 | 1 | 1 | 2 | 0 | 1 | 0 | 2
| UM Tests: Create | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 1 | 2
| BRD: Account Deletion | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 1 | 2
| Test Cases: Acount Deletion | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
SP Decrement |  | 19 | 0 | 1 | 2 | 3 | 0.5 | 0 | 0 | 1 | 1 | 0 | 0.5 | 1 | 1 | 1 | 2 | 2 | 3
Michael
| Logging behavioral diagram | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Logging Feature Pseudocode | 2 | 0 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Compile Logging LL Design Document | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Update Test Plan (feedback) | 2 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Archiving (BRD) | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Archiving (Test Plan) | 1 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Review Site Map, HL Design | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0
| Archiving Implementation | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 2 | 0
| Logging Tests | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 5
| Tech Approval: Unit Tests | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 0
SP Decrement |  |  | 0 | 1 | 1 | 1 | 2 | 0.5 | 0 | 2 | 0.5 | 2 | 3 | 1 | 0 | 1 | 1 | 2 | 4
|  |  | 0 | 3 | 5.5 | 5.75 | 4.25 | 1 | 0 | 4 | 3 | 6.5 | 8.5 | 3 | 7.5 | 6.5 | 9 | 14.5 | 20
Daily Scrum Meeting
Day of Sprint | Who | What did you work on Yesterday? | 2: What are you working on today?; 5: Are You Blocked?
Day 1 | Albert | n/a | 2: UM interfaces to other components; 5: no
| Audrey | n/a | 2: UM sequence diagram; 5: no
| Brad | n/a | 2: n/a; 5: no
| Joseph | n/a | 2: UM Implementation: Create; 5: no
| Michael | n/a | 2: n/a; 5: no
Day 2 | Albert | UM interfaces to other components | 2: UM interfaces to other components; 5: no
| Audrey | UM sequence diagram | 2: n/a; 5: no
| Brad | n/a | 2: tech approval for unit testing; 5: no
| Joseph | UM Implementation: Create | 2: UM Implementation: Enable/disable; 5: yes
| Michael | n/a | 2: Archiving BRD; 5: no
Day 3 | Albert | UM interfaces to other components | 2: UM Feature Pseudocode; 5: no
| Audrey | n/a | 2: UM sequence diagram; 5: no
| Brad | tech approval for unit testing | 2: Logging design/tech research; 5: no
| Joseph | UM Implementation: Enable/disable | 2: UM Implementation: Create; 5: no
| Michael | Archiving BRD | 2: n/a; 5: no
Day 4 | Albert | UM Feature Pseudocode | 2: UM Feature Pseudocode; 5: no
| Audrey | UM sequence diagram | 2: UM sequence diagram; 5: no
| Brad | Logging design/tech research | 2: Logging tech research; 5: no
| Joseph | UM Implementation: Create | 2: UM Implementation: Enable/disable; 5: yes
| Michael | n/a | 2: Archiving Test Plan; 5: no
Day 5 | Albert | UM Feature Pseudocode | 2: Review BRD, Tech Spec
| Audrey | UM sequence diagram | 2: n/a; 5: no
| Brad | Logging tech research | 2: n/a; 5: no
| Joseph | UM Implementation: Enable/disable | 2: UM Implementation: Create; 5: no
| Michael | Archiving Test Plan | 2: Update Test Plan; 5: no
Day 6 | Albert | Review BRD, Tech Spec | 2: Review BRD, Tech Spec; 5: no
| Audrey | n/a | 2: n/a; 5: no
| Brad | n/a | 2: n/a; 5: no
| Joseph | n/a | 2: n/a; 5: no
| Michael | Update Test Plan (Feedback) | 2: Archiving Pseudocode; 5: no
Day 7 | Albert | Review BRD, Tech Spec | 2: Implemetation: Authorization; 5: no
| Audrey | n/a | 2: n/a; 5: no
| Brad | n/a | 2: Logging test research & prototype; 5: no
| Joseph | n/a | 2: UM Implementaton: Create; 5: no
| Michael | Archiving Pseudocode | 2: n/a; 5: no
Day 8 | Albert | Implemetation: Authorization | 2: Implemetation: Authorization; 5: no
| Audrey | n/a | 2: UM sequence diagram, LL design; 5: no
| Brad | Logging test research & prototype | 2: Logging LL design; 5: no
| Joseph | UM Implementaton: Create | bar: 5
| Michael | n/a | 2: logging behavioral diagram; 5: no
Day 9 | Albert | Implemetation: Authorization | 2: UM Tests: Bulk Operations; 5: no
| Audrey | UM sequence diagram, LL design | 2: UM sequence diagram, LL design, looking over documents; 5: no
| Brad | Logging LL design | 2: Logging, UM LL design; 5: no
Joseph | bar: 5
| Michael | logging behavioral diagram | 2: logging feature pseudocode; 5: no
Day 10 | Albert | UM Tests: Bulk Operations | 2: UM Tests: Bulk Operations; 5: no
| Audrey | UM sequence diagram, LL design, looking over documents | 2: sequence diagram, other document checking, authorzie; 5: no
| Brad | Logging, UM LL design | 2: logging class diagram; 5: no
| Joseph | UM Tests: Bulk Operations | 2: UM Tests: Bulk Operations; 5: no
| Michael | loggind feature pseudocode | 2: Logging Tests; 5: no
Day 11 | Albert | UM Tests: Bulk Operations | 2: Tests: Update; 5: no
| Audrey | sequence diagram, other document checking, authorzie | 2: sequence diagram, other document checking; 5: no
| Brad | n/a | 2: logging class diagram; 5: no
Joseph | bar: 5
| Michael | Logging Tests | 2: Archiving; 5: no
Day 12 | Albert | Tests: Update | 2: Tests: Authorization; 5: no
| Audrey | sequence diagram, other document checking | 2: UM sequence diagram LLdesign; 5: no
| Brad | logging class diagram | 2: logging class diagram & log class for logging implementation; 5: no
| Joseph | UM implentation | 2: Um implementaiton; 5: no
| Michael | Archivng | 2: Test Plan; 5: no
Day 13 | Albert | Tests: Authorization | 2: UM Tests: Bulk Operations; 5: no
| Audrey | UM sequence diagram LLdesign | 2: UM sequence diagram LLdesign; 5: yes
| Brad | logging class diagram & log class for logging implementation | 2: log class for logging implementation; 5: no
| Joseph | Um implementaiton | 2: um tests: Bulk Operations; 5: no
| Michael | Test Plan | 2: archiving; 5: no
Day 14 | Albert | UM Tests: Bulk Operations | 2: UM Implementation: Execute bulk operations; 5: no
| Audrey | UM sequence diagram LLdesign | 2: UM IMlementation; 5: no
| Brad | n/a | 2: log class for logging implementation; 5: no
| Joseph | UM Implementation | 2: UM Implementation; 5: no
| Michael | archiving | 2: logging tests; 5: no
Day 15 | Albert | UM Implementation: Execute bulk operations | 2: Registration (BRD); 5: no
| Audrey | UM IMlementation | 2: UM implementaiton, UM Tests; 5: no
| Brad | log class for logging implementation | 2: logging implementation; 5: no
| Joseph | UM Implementation | 2: UM tests; 5: no
| Michael | logging tests | 2: archiving implementation; 5: no
Day 16 | Albert | Registration (BRD) | 2: Registration (Test Plan); 5: no
| Audrey | UM implementaiton, UM Tests | 2: UM Tests; 5: no
| Brad | logging implementation | 2: logging implementation, archiving tests; 5: no
| Joseph | UM tests | 2: UM Tests; 5: no
| Michael | archiving implementation | 2: logging tests; 5: no

## Albert
Sprint 0 | proposal | [6 empty] | Sprint | SP | Hours Worked | Over/Under
| Start Date | 2021-09-22 |  | Day of Sprint | Forecast | Actual Effort | Hours Worked | 0 | 8 | 13 | 5
| End Date | 2021-09-27 |  | 0 | 8 | 8 | 0 | 1 | 10 | 24 | 14
| Sprint Length | 6 |  | 1 | 6.67 | 7 | 2 | 2 | 6 | 9 | 3
|  |  |  | 2 | 5.34 | 7 | 0 | 3 | 14 | 24 | 10
| Capacity | 10 |  | 3 | 4.01 | 7 | 1 | 4 | 12 | 6.5 | -5.5
| Total Sprint SP | 8 |  | 4 | 2.68 | 4 | 4 | 5 | 18.5 | 15 | -3.5
| SP/Day | 1.33 |  | 5 | 1.35 | 2.5 | 3 | 6 | 20 | 38.5 | 18.5
|  |  |  | 6 | 0 | 0 | 3 | 7
[6 empty] | Total = | 13
[6 empty] | Over effort = | 5
Sprint 1 | milestone 1
| Start Date | 2021-09-29 |  | Day of Sprint | Forecast | Actual Effort | Hours Worked
| End Date | 2021-10-05 |  | 0 | 10 | 10 | 0
| Sprint Length | 7 |  | 1 | 8.5714 | 9 | 3
|  |  |  | 2 | 7.1429 | 9 | 0
| Capacity | 16 |  | 3 | 5.7143 | 7 | 4
| Total Sprint SP | 10 |  | 4 | 4.2857 | 6 | 3
| SP/Day | 1.4286 |  | 5 | 2.8571 | 4 | 5
|  |  |  | 6 | 1.4286 | 3 | 3
|  |  |  | 7 | 0 | 0 | 6
[6 empty] | Total = | 24
[6 empty] | Over effort = | 14
Sprint 2 | test plan
| Start Date | 2021-10-13 |  | Day of Sprint | Forecast | Actual Effort | Hours Worked
| End Date | 2021-10-18 |  | 0 | 6 | 6 | 0
| Sprint Length | 6 |  | 1 | 5 | 6 | 0
|  |  |  | 2 | 4 | 6 | 0
| Capacity | 8 |  | 3 | 3 | 5 | 1
| Total Sprint SP | 6 |  | 4 | 2 | 4 | 3
| SP/Day | 1 |  | 5 | 1 | 2 | 3
|  |  |  | 6 | 0 | 0 | 3
[6 empty] | Total = | 10
[6 empty] | Over effort = | 4
Sprint 3 | milestone 2
| Start Date | 2021-10-21 |  | Day of Sprint | Forecast | Actual Effort | Hours Worked
| End Date | 2021-10-26 |  | 0 | 14 | 14 | 0
| Sprint Length | 6 |  | 1 | 11.6667 | 14 | 0
|  |  |  | 2 | 9.3333 | 13 | 2
| Capacity | 18 |  | 3 | 7 | 12 | 3
| Total Sprint SP | 14 |  | 4 | 4.6667 | 8 | 8
| SP/Day | 2.3333 |  | 5 | 2.3333 | 4 | 6
|  |  |  | 6 | 0 | 0 | 5
[6 empty] | Total = | 24
[6 empty] | Over effort = | 10
Sprint 4 | UM, Logging | on older docs | and LL
| Start Date | 2021-11-05 |  | Day of Sprint | Forecast | Actual Effort | Hours Worked
| End Date | 2021-11-12 |  | 0 | 12 | 12 | 0
| Sprint Length | 8 |  | 1 | 10.5 | 11.5 | 1
|  |  |  | 2 | 9 | 11.5 | 0
| Capacity | 16 |  | 3 | 7.5 | 11.5 | 0
| Total Sprint SP | 12 |  | 4 | 6 | 10.5 | 2
| SP/Day | 1.5 |  | 5 | 4.5 | 10.5 | 0
|  |  |  | 6 | 3 | 9 | 1.5
|  |  |  | 7 | 1.5 | 8.5 | 1
|  |  |  | 8 | 0 | 8 | 1
[6 empty] | Total = | 6.5
[6 empty] | Over effort = | -5.5
Sprint 5 | sprint 4 + | core comp
| Start Date | 2021-11-14 |  | Day of Sprint | Forecast | Actual Effort | Hours Worked
| End Date | 2021-11-19 |  | 0 | 18.5 | 18.5 | 0
| Sprint Length | 10 |  | 1 | 16.65 | 17 | 2
|  |  |  | 2 | 14.8 | 15.75 | 2
| Capacity | 20 |  | 3 | 12.95 | 14.5 | 2
| Total Sprint SP | 18.5 |  | 4 | 11.1 | 14.5 | 0
| SP/Day | 1.85 |  | 5 | 9.25 | 12.5 | 2
|  |  |  | 6 | 7.4 | 10.5 | 2
|  |  |  | 7 | 5.55 | 8.5 | 2
|  |  |  | 8 | 3.7 | 8 | 1
|  |  |  | 9 | 1.85 | 7.5 | 1
|  |  |  | 10 | 0 | 6 | 1
[6 empty] | Total = | 15
[6 empty] | Over effort = | -3.5
Sprint 6 | sprint 5 + | codes
| Start Date | 2021-11-29 |  | Day of Sprint | Forecast | Actual Effort | Hours Worked
| End Date | 2021-12-14 |  | 0 | 20 | 20 | 0
| Sprint Length | 16 |  | 1 | 18.75 | 20 | 1
|  |  |  | 2 | 17.5 | 19.5 | 1
| Capacity | 22 |  | 3 | 16.25 | 18.5 | 1.5
| Total Sprint SP | 20 |  | 4 | 15 | 17.5 | 0
| SP/Day | 1.25 |  | 5 | 13.75 | 17.5 | 0
|  |  |  | 6 | 12.5 | 17.5 | 0
|  |  |  | 7 | 11.25 | 17.5 | 0
|  |  |  | 8 | 10 | 17 | 1
|  |  |  | 9 | 8.75 | 15.5 | 5
|  |  |  | 10 | 7.5 | 14.5 | 2
|  |  |  | 11 | 6.25 | 14 | 1
|  |  |  | 12 | 5 | 11 | 5
|  |  |  | 13 | 3.75 | 9 | 5
|  |  |  | 14 | 2.5 | 6 | 5
|  |  |  | 15 | 1.25 | 3 | 5
|  |  |  | 16 | 0 | 0 | 6
[6 empty] | Total = | 38.5
[6 empty] | Over effort = | 18.5

## Audrey
Sprint 0 | proposal | [6 empty] | Sprint | SP | Hours Worked | Over/Under
| Start Date | 2021-09-22 |  | Day of Sprint | Forecast | Actual Effort | Hours Worked | 0 | 4 | 16 | 12
| End Date | 2021-09-27 |  | 0 | 4 | 4 | 0 | 1 | 12 | 27 | 15
| Sprint Length | 6 |  | 1 | 3.33 | 3 | 1 | 2 | 6 | 11 | 5
|  |  |  | 2 | 2.66 | 3 | 1 | 3 | 14 | 20 | 6
| Capacity | 10 |  | 3 | 1.99 | 1 | 4 | 4 | 14 | 11.5 | -2.5
| Total Sprint SP | 4 |  | 4 | 1.32 | 1 | 1 | 5 | 19 | 17.5 | -1.5
| SP/Day | 0.67 |  | 5 | 0.65 | 0.5 | 4 | 6 | 20 | 40.75 | 20.75
|  |  |  | 6 | 0 | 0 | 5 | 7
[6 empty] | Total = | 16
[6 empty] | Over Effort = | 12
Sprint 1 | milestone 1
| Start Date | 2021-09-29 |  | Day of Sprint | Forecast | Actual Effort | Hours Worked
| End Date | 2021-10-05 |  | 0 | 12 | 12 | 0
| Sprint Length | 7 |  | 1 | 10.2857 | 11 | 2
|  |  |  | 2 | 8.5714 | 11 | 0
| Capacity | 15 |  | 3 | 6.8571 | 9 | 4
| Total Sprint SP | 12 |  | 4 | 5.1429 | 8 | 3
| SP/Day | 1.7143 |  | 5 | 3.4286 | 5 | 6
|  |  |  | 6 | 1.7143 | 2 | 6
|  |  |  | 7 | 0 | 0 | 6
[6 empty] | Total = | 27
[6 empty] | Over Effort = | 15
Sprint 2 | test plan
| Start Date | 2021-10-13 |  | Day of Sprint | Forecast | Actual Effort | Hours Worked
| End Date | 2021-10-18 |  | 0 | 6 | 6 | 0
| Sprint Length | 6 |  | 1 | 5 | 6 | 0
|  |  |  | 2 | 4 | 6 | 0
| Capacity | 8 |  | 3 | 3 | 3 | 4
| Total Sprint SP | 6 |  | 4 | 2 | 2 | 3
| SP/Day | 1 |  | 5 | 1 | 1 | 2
|  |  |  | 6 | 0 | 0 | 2
[6 empty] | Total = | 11
[6 empty] | Over Effort = | 5
Sprint 3 | project plan | network diagram
| Start Date | 2021-10-21 |  | Day of Sprint | Forecast | Actual Effort | Hours Worked
| End Date | 2021-10-26 |  | 0 | 14 | 14 | 0
| Sprint Length | 6 |  | 1 | 11.6667 | 14 | 0
|  |  |  | 2 | 9.3333 | 13 | 2
| Capacity | 18 |  | 3 | 7 | 11 | 2.5
| Total Sprint SP | 14 |  | 4 | 4.6667 | 7 | 4
| SP/Day | 2.3333 |  | 5 | 2.3333 | 4 | 3.5
|  |  |  | 6 | 0 | 0 | 8
[6 empty] | Total = | 20
[6 empty] | Over Effort = | 6
Sprint 4 | UM, Logging | on older docs | and LL
| Start Date | 2021-11-05 |  | Day of Sprint | Forecast | Actual Effort | Hours Worked
| End Date | 2021-11-12 |  | 0 | 14 | 14 | 0
| Sprint Length | 8 |  | 1 | 12.25 | 13.5 | 1
|  |  |  | 2 | 10.5 | 13.5 | 0
| Capacity | 16 |  | 3 | 8.75 | 13.5 | 0
| Total Sprint SP | 14 |  | 4 | 7 | 13 | 1.5
| SP/Day | 1.75 |  | 5 | 5.25 | 13 | 0
|  |  |  | 6 | 3.5 | 12 | 2
|  |  |  | 7 | 1.75 | 10.5 | 3
|  |  |  | 8 | 0 | 7 | 4
[6 empty] | Total = | 11.5
[6 empty] | Over effort = | -2.5
Sprint 5 | sprint 4 + | core comp
| Start Date | 2021-11-14 |  | Day of Sprint | Forecast | Actual Effort | Hours Worked
| End Date | 2021-11-19 |  | 0 | 19 | 19 | 0
| Sprint Length | 10 |  | 1 | 17.1 | 18.5 | 1.5
|  |  |  | 2 | 15.2 | 17.5 | 2
| Capacity | 20 |  | 3 | 13.3 | 15 | 2
| Total Sprint SP | 19 |  | 4 | 11.4 | 15 | 0
| SP/Day | 1.9 |  | 5 | 9.5 | 15 | 0
|  |  |  | 6 | 7.6 | 14 | 2
|  |  |  | 7 | 5.7 | 13 | 2
|  |  |  | 8 | 3.8 | 13 | 0
|  |  |  | 9 | 1.9 | 12 | 2.5
|  |  |  | 10 | 0 | 6 | 5.5
[6 empty] | Total = | 17.5
[6 empty] | Over effort = | -1.5
Sprint 6 | sprint 5 + | codes
| Start Date | 2021-11-29 |  | Day of Sprint | Forecast | Actual Effort | Hours Worked
| End Date | 2021-12-14 |  | 0 | 20 | 20 | 0
| Sprint Length | 16 |  | 1 | 18.75 | 19 | 2
|  |  |  | 2 | 17.5 | 19 | 0
| Capacity | 22 |  | 3 | 16.25 | 18.75 | 2
| Total Sprint SP | 20 |  | 4 | 15 | 18.5 | 2
| SP/Day | 1.25 |  | 5 | 13.75 | 18.5 | 0
|  |  |  | 6 | 12.5 | 18.5 | 0
|  |  |  | 7 | 11.25 | 18.5 | 0
|  |  |  | 8 | 10 | 18 | 5
|  |  |  | 9 | 8.75 | 16 | 6
|  |  |  | 10 | 7.5 | 12 | 3
|  |  |  | 11 | 6.25 | 11.5 | 2
|  |  |  | 12 | 5 | 10 | 1
|  |  |  | 13 | 3.75 | 9 | 5
|  |  |  | 14 | 2.5 | 7 | 3.25
|  |  |  | 15 | 1.25 | 5.5 | 4
|  |  |  | 16 | 0 | 0 | 5.5
[6 empty] | Total = | 40.75
[6 empty] | Over effort = | 20.75

## Brad
Sprint 0 | proposal | [6 empty] | Sprint | SP | Hours Worked | Over/Under
| Start Date | 2021-09-22 |  | Day of Sprint | Forecast | Actual Effort | Hours Worked | 0 | 9 | 20 | 11
| End Date | 2021-09-27 |  | 0 | 9 | 9 | 0 | 1 | 18.5 | 33 | 14.5
| Sprint Length | 6 |  | 1 | 7.5 | 8 | 2 | 2 | 6 | 5 | -1
|  |  |  | 2 | 6 | 8 | 0 | 3 | 14 | 16 | 2
| Capacity | 10 |  | 3 | 4.5 | 5 | 6 | 4 | 14 | 12.5 | -1.5
| Total Sprint SP | 9 |  | 4 | 3 | 5 | 3 | 5 | 19 | 10 | -9
| SP/Day | 1.5 |  | 5 | 1.5 | 3 | 4 | 6 | 20 | 38 | 18
|  |  |  | 6 | 0 | 0 | 5 | 7
[6 empty] | Total = | 20
[6 empty] | Over Effort = | 11
Sprint 1 | milestone 1
| Start Date | 2021-09-29 |  | Day of Sprint | Forecast | Actual Effort | Hours Worked
| End Date | 2021-10-05 |  | 0 | 18.5 | 18.5 | 0
| Sprint Length | 7 |  | 1 | 15.8571 | 17.5 | 3
|  |  |  | 2 | 13.2143 | 17.5 | 0
| Capacity | 20 |  | 3 | 10.5714 | 16.5 | 4
| Total Sprint SP | 18.5 |  | 4 | 7.9286 | 14.5 | 6
| SP/Day | 2.6429 |  | 5 | 5.2857 | 9.5 | 6
|  |  |  | 6 | 2.6429 | 5.5 | 7
|  |  |  | 7 | 0 | 0 | 7
[6 empty] | Total = | 33
[6 empty] | Over Effort = | 14.5
Sprint 2 | test plan
| Start Date | 2021-10-13 |  | Day of Sprint | Forecast | Actual Effort | Hours Worked
| End Date | 2021-10-18 |  | 0 | 6 | 6 | 0
| Sprint Length | 6 |  | 1 | 5 | 6 | 0
|  |  |  | 2 | 4 | 6 | 0
| Capacity | 8 |  | 3 | 3 | 5 | 1
| Total Sprint SP | 6 |  | 4 | 2 | 5 | 0
| SP/Day | 1 |  | 5 | 1 | 3 | 2
|  |  |  | 6 | 0 | 1 | 2
[6 empty] | Total = | 5
[6 empty] | Over Effort = | -1
Sprint 3 | project plan | network diagram
| Start Date | 2021-10-21 |  | Day of Sprint | Forecast | Actual Effort | Hours Worked
| End Date | 2021-10-26 |  | 0 | 14 | 14 | 0
| Sprint Length | 6 |  | 1 | 11.6667 | 12 | 1.5
|  |  |  | 2 | 9.3333 | 9 | 3.5
| Capacity | 18 |  | 3 | 7 | 8.25 | 0.5
| Total Sprint SP | 14 |  | 4 | 4.6667 | 5.25 | 4.75
| SP/Day | 2.3333 |  | 5 | 2.3333 | 1 | 3.75
|  |  |  | 6 | 0 | 0 | 2
[6 empty] | Total = | 16
[6 empty] | Over Effort = | 2
Sprint 4 | UM, Logging | on older docs | and LL
| Start Date | 2021-11-05 |  | Day of Sprint | Forecast | Actual Effort | Hours Worked
| End Date | 2021-11-12 |  | 0 | 14 | 14 | 0
| Sprint Length | 8 |  | 1 | 12.25 | 13 | 1
|  |  |  | 2 | 10.5 | 13 | 0
| Capacity | 16 |  | 3 | 8.75 | 13 | 1.25
| Total Sprint SP | 14 |  | 4 | 7 | 12 | 3
| SP/Day | 1.75 |  | 5 | 5.25 | 12 | 0
|  |  |  | 6 | 3.5 | 11 | 3
|  |  |  | 7 | 1.75 | 11 | 0
|  |  |  | 8 | 0 | 9 | 4.25
[6 empty] | Total = | 12.5
[6 empty] | Over effort = | -1.5
Sprint 5 | sprint 4 + | core comp
| Start Date | 2021-11-15 |  | Day of Sprint | Forecast | Actual Effort | Hours Worked
| End Date | 2021-11-24 |  | 0 | 19 | 19 | 0
| Sprint Length | 10 |  | 1 | 17.1 | 19 | 0
|  |  |  | 2 | 15.2 | 17 | 1
| Capacity | 20 |  | 3 | 13.3 | 14 | 1.5
| Total Sprint SP | 19 |  | 4 | 11.4 | 12 | 2
| SP/Day | 1.9 |  | 5 | 9.5 | 10 | 1
|  |  |  | 6 | 7.6 | 8.5 | 1.5
|  |  |  | 7 | 5.7 | 6.25 | 1.75
|  |  |  | 8 | 3.8 | 4 | 1.25
|  |  |  | 9 | 1.9 | 4 | 0
|  |  |  | 10 | 0 | 4 | 0
[6 empty] | Total = | 10
[6 empty] | Over effort = | -9
Sprint 6 | sprint 5 + | codes
| Start Date | 2021-11-29 |  | Day of Sprint | Forecast | Actual Effort | Hours Worked
| End Date | 2021-12-14 |  | 0 | 20 | 20 | 0
| Sprint Length | 16 |  | 1 | 18.75 | 20 | 0
|  |  |  | 2 | 17.5 | 18 | 4
| Capacity | 22 |  | 3 | 16.25 | 17.5 | 4
| Total Sprint SP | 20 |  | 4 | 15 | 17 | 2
| SP/Day | 1.25 |  | 5 | 13.75 | 16.5 | 2
|  |  |  | 6 | 12.5 | 16.5 | 0
|  |  |  | 7 | 11.25 | 15.5 | 3
|  |  |  | 8 | 10 | 15 | 6
|  |  |  | 9 | 8.75 | 14 | 4
|  |  |  | 10 | 7.5 | 14 | 0
|  |  |  | 11 | 6.25 | 14 | 0
|  |  |  | 12 | 5 | 12 | 2.5
|  |  |  | 13 | 3.75 | 12 | 0
|  |  |  | 14 | 2.5 | 11 | 1
|  |  |  | 15 | 1.25 | 5 | 5
|  |  |  | 16 | 0 | 0 | 4.5
[6 empty] | Total = | 38
[6 empty] | Over effort = | 18

## Joseph
Sprint 0 | proposal | [6 empty] | Sprint | SP | Hours Worked | Over/Under
| Start Date | 2021-09-22 |  | Day of Sprint | Forecast | Actual Effort | Hours Worked | 0 | 4 | 18 | 14
| End Date | 2021-09-27 |  | 0 | 4 | 4 | 0 | 1 | 5.5 | 24 | 18.5
| Sprint Length | 6 |  | 1 | 3.33 | 4 | 1 | 2 | 6 | 11 | 5
|  |  |  | 2 | 2.66 | 4 | 0 | 3 | 14 | 28 | 14
| Capacity | 10 |  | 3 | 1.99 | 2 | 6 | 4 | 15 | 13 | -2
| Total Sprint SP | 4 |  | 4 | 1.32 | 2 | 1 | 5 | 19 | 10.75 | -8.25
| SP/Day | 0.67 |  | 5 | 0.65 | 0 | 5 | 6 | 19 | 31.5 | 12.5
|  |  |  | 6 | 0 | 0 | 5 | 7
[6 empty] | Total = | 18
[6 empty] | Over Effort = | 14
Sprint 1 | milestone 1
| Start Date | 2021-09-29 |  | Day of Sprint | Forecast | Actual Effort | Hours Worked
| End Date | 2021-10-05 |  | 0 | 5.5 | 5.5 | 0
| Sprint Length | 7 |  | 1 | 4.7143 | 5 | 2
|  |  |  | 2 | 3.9286 | 5 | 0
| Capacity | 10 |  | 3 | 3.1429 | 4 | 2
| Total Sprint SP | 5.5 |  | 4 | 2.3571 | 3 | 3
| SP/Day | 0.78571 |  | 5 | 1.5714 | 2 | 5
|  |  |  | 6 | 0.78571 | 1 | 6
|  |  |  | 7 | 0 | 0 | 6
[6 empty] | Total = | 24
[6 empty] | Over Effort = | 18.5
Sprint 2 | test plan
| Start Date | 2021-10-13 |  | Day of Sprint | Forecast | Actual Effort | Hours Worked
| End Date | 2021-10-18 |  | 0 | 6 | 6 | 0
| Sprint Length | 6 |  | 1 | 5 | 6 | 0
|  |  |  | 2 | 4 | 6 | 0
| Capacity | 8 |  | 3 | 3 | 3 | 4
| Total Sprint SP | 6 |  | 4 | 2 | 2 | 3
| SP/Day | 1 |  | 5 | 1 | 1 | 2
|  |  |  | 6 | 0 | 0 | 2
[6 empty] | Total = | 11
[6 empty] | Over Effort = | 5
Sprint 3 | project plan | network diagram
| Start Date | 2021-10-21 |  | Day of Sprint | Forecast | Actual Effort | Hours Worked
| End Date | 2021-10-26 |  | 0 | 14 | 14 | 0
| Sprint Length | 6 |  | 1 | 11.6667 | 14 | 0
|  |  |  | 2 | 9.3333 | 13 | 6.5
| Capacity | 18 |  | 3 | 7 | 10 | 5
| Total Sprint SP | 14 |  | 4 | 4.6667 | 7 | 4
| SP/Day | 2.3333 |  | 5 | 2.3333 | 4 | 5
|  |  |  | 6 | 0 | 0 | 7.5
[6 empty] | Total = | 28
[6 empty] | Over Effort = | 14
Sprint 4 | UM, Logging | on older docs | and LL
| Start Date | 2021-11-05 |  | Day of Sprint | Forecast | Actual Effort | Hours Worked
| End Date | 2021-11-12 |  | 0 | 15 | 15 | 0
| Sprint Length | 8 |  | 1 | 13.125 | 15 | 1
|  |  |  | 2 | 11.25 | 15 | 1
| Capacity | 16 |  | 3 | 9.375 | 15 | 1
| Total Sprint SP | 15 |  | 4 | 7.5 | 15 | 2
| SP/Day | 1.875 |  | 5 | 5.625 | 14 | 2
|  |  |  | 6 | 3.75 | 13 | 2
|  |  |  | 7 | 1.875 | 12 | 2
|  |  |  | 8 | 0 | 11 | 2
[6 empty] | Total = | 13
[6 empty] | Over effort = | -2
Sprint 5 | sprint 4 + | core comp
| Start Date | 2021-11-14 |  | Day of Sprint | Forecast | Actual Effort | Hours Worked
| End Date | 2021-11-19 |  | 0 | 19 | 19 | 0
| Sprint Length | 10 |  | 1 | 17.1 | 17 | 1
|  |  |  | 2 | 15.2 | 16.5 | 0.5
| Capacity | 20 |  | 3 | 13.3 | 15.5 | 1
| Total Sprint SP | 19 |  | 4 | 11.4 | 15.5 | 0
| SP/Day | 1.9 |  | 5 | 9.5 | 14.75 | 1.25
|  |  |  | 6 | 7.6 | 14.25 | 0.5
|  |  |  | 7 | 5.7 | 13.75 | 0.5
|  |  |  | 8 | 3.8 | 13.25 | 0.75
|  |  |  | 9 | 1.9 | 12.25 | 0.75
|  |  |  | 10 | 0 | 8 | 4.5
[6 empty] | Total = | 10.75
[6 empty] | Over effort = | -8.25
Sprint 6 | sprint 5 + | codes
| Start Date | 2021-11-29 |  | Day of Sprint | Forecast | Actual Effort | Hours Worked
| End Date | 2021-12-14 |  | 0 | 19 | 19 | 0
| Sprint Length | 16 |  | 1 | 17.8125 | 18.75 | 1
|  |  |  | 2 | 16.625 | 18.5 | 2
| Capacity | 22 |  | 3 | 15.4375 | 18.25 | 1
| Total Sprint SP | 19 |  | 4 | 14.25 | 18 | 2
| SP/Day | 1.1875 |  | 5 | 13.0625 | 18 | 0.5
|  |  |  | 6 | 11.875 | 18 | 0
|  |  |  | 7 | 10.6875 | 17.75 | 2
|  |  |  | 8 | 9.5 | 17.75 | 4
|  |  |  | 9 | 8.3125 | 17.75 | 0
|  |  |  | 10 | 7.125 | 15.25 | 4
|  |  |  | 11 | 5.9375 | 13 | 2.5
|  |  |  | 12 | 4.75 | 9 | 3
|  |  |  | 13 | 3.5625 | 6.25 | 2
|  |  |  | 14 | 2.375 | 4.75 | 2.5
|  |  |  | 15 | 1.1875 | 2.25 | 3
|  |  |  | 16 | 0 | 0 | 2
[6 empty] | Total = | 31.5
[6 empty] | Over effort = | 12.5

## Michael
Sprint 0 | proposal | [6 empty] | Sprint | SP | Hours Worked | Over/Under
| Start Date | 2021-09-22 |  | Day of Sprint | Forecast | Actual Effort | Hours Worked | 0 | 4 | 18 | 14
| End Date | 2021-09-27 |  | 0 | 8 | 8 | 0 | 1 | 11.5 | 28 | 16.5
| Sprint Length | 6 |  | 1 | 6.67 | 7 | 1 | 2 | 6 | 11 | 5
|  |  |  | 2 | 5.33 | 7 | 0 | 3 | 16 | 23 | 7
| Capacity | 10 |  | 3 | 4 | 4 | 6 | 4 | 16 | 8 | -8
| Total Sprint SP | 8 |  | 4 | 2.66 | 4 | 1 | 5 | 19 | 12 | -7
| SP/Day | 0.67 |  | 5 | 1.33 | 2 | 4 | 6 | 22 | 35 | 13
|  |  |  | 6 | 0 | 0 | 5 | 7
[6 empty] | Total = | 17
[6 empty] | Over Effort = | 14
Sprint 1 | milestone 1
| Start Date | 2021-09-29 |  | Day of Sprint | Forecast | Actual Effort | Hours Worked
| End Date | 2021-10-05 |  | 0 | 10.5 | 10.5 | 0
| Sprint Length | 7 |  | 1 | 9 | 9.5 | 3
|  |  |  | 2 | 7.5 | 9.5 | 0
| Capacity | 12 |  | 3 | 6 | 7.5 | 7
| Total Sprint SP | 10.5 |  | 4 | 4.5 | 6.5 | 5
| SP/Day | 1.5 |  | 5 | 3 | 4.5 | 5
|  |  |  | 6 | 1.5 | 2.5 | 5
|  |  |  | 7 | 0 | 0 | 5
[6 empty] | Total = | 30
[6 empty] | Over Effort = | 19.5
Sprint 2 | test plan
| Start Date | 2021-10-13 |  | Day of Sprint | Forecast | Actual Effort | Hours Worked
| End Date | 2021-10-18 |  | 0 | 6 | 6 | 0
| Sprint Length | 6 |  | 1 | 5 | 6 | 0
|  |  |  | 2 | 4 | 6 | 0
| Capacity | 8 |  | 3 | 3 | 5 | 1
| Total Sprint SP | 6 |  | 4 | 2 | 4 | 1
| SP/Day | 1 |  | 5 | 1 | 1 | 3
|  |  |  | 6 | 0 | 0 | 1
[6 empty] | Total = | 6
[6 empty] | Over Effort = | 0
Sprint 3 | project plan | network diagram
| Start Date | 2021-10-21 |  | Day of Sprint | Forecast | Actual Effort | Hours Worked
| End Date | 2021-10-26 |  | 0 | 16 | 16 | 0
| Sprint Length | 6 |  | 1 | 13.3333 | 16 | 0
|  |  |  | 2 | 10.6667 | 15 | 2
| Capacity | 18 |  | 3 | 8 | 14 | 1
| Total Sprint SP | 16 |  | 4 | 5.3333 | 11 | 4
| SP/Day | 2.6667 |  | 5 | 2.6667 | 7 | 6
|  |  |  | 6 | 0 | 0 | 10
[6 empty] | Total = | 23
[6 empty] | Over Effort = | 7
Sprint 4 | UM, Logging | on older docs | and LL
| Start Date | 2021-11-05 |  | Day of Sprint | Forecast | Actual Effort | Hours Worked
| End Date | 2021-11-12 |  | 0 | 16 | 16 | 0
| Sprint Length | 8 |  | 1 | 14 | 16 | 0
|  |  |  | 2 | 12 | 16 | 0
| Capacity | 16 |  | 3 | 10 | 16 | 0
| Total Sprint SP | 16 |  | 4 | 8 | 15 | 3
| SP/Day | 2 |  | 5 | 6 | 14 | 2
|  |  |  | 6 | 4 | 12 | 3
|  |  |  | 7 | 2 |  | 0
|  |  |  | 8 | 0 |  | 0
[6 empty] | Total = | 8
[6 empty] | Over effort = | -8
Sprint 5 | sprint 4 + | core comp
| Start Date | 2021-11-14 |  | Day of Sprint | Forecast | Actual Effort | Hours Worked
| End Date | 2021-11-19 |  | 0 | 19 | 19 | 0
| Sprint Length | 10 |  | 1 | 17.1 | 17 | 3
|  |  |  | 2 | 15.2 | 16.5 | 1
| Capacity | 20 |  | 3 | 13.3 | 16 | 1
| Total Sprint SP | 19 |  | 4 | 11.4 | 15.5 | 1
| SP/Day | 1.9 |  | 5 | 9.5 | 15 | 1
|  |  |  | 6 | 7.6 | 14 | 1
|  |  |  | 7 | 5.7 | 12 | 1
|  |  |  | 8 | 3.8 | 11 | 1
|  |  |  | 9 | 1.9 | 10 | 1
|  |  |  | 10 | 0 | 9 | 1
[6 empty] | Total = | 12
[6 empty] | Over effort = | -7
Sprint 6 | sprint 5 + | codes
| Start Date | 2021-11-29 |  | Day of Sprint | Forecast | Actual Effort | Hours Worked
| End Date | 2021-12-14 |  | 0 | 22 | 22 | 0
| Sprint Length | 16 |  | 1 | 20.625 | 21 | 3
|  |  |  | 2 | 19.25 | 20 | 2
| Capacity | 24 |  | 3 | 17.875 | 19 | 2
| Total Sprint SP | 22 |  | 4 | 16.5 | 17 | 2
| SP/Day | 1.375 |  | 5 | 15.125 | 16.5 | 1
|  |  |  | 6 | 13.75 | 16.5 | 0
|  |  |  | 7 | 12.375 | 14.5 | 2
|  |  |  | 8 | 11 | 14 | 1
|  |  |  | 9 | 9.625 | 12 | 3
|  |  |  | 10 | 8.25 | 9 | 3
|  |  |  | 11 | 6.875 | 8 | 1
|  |  |  | 12 | 5.5 | 8 | 0
|  |  |  | 13 | 4.125 | 7 | 2
|  |  |  | 14 | 2.75 | 6 | 2
|  |  |  | 15 | 1.375 | 4 | 5
|  |  |  | 16 | 0 | 0 | 6
[6 empty] | Total = | 35
[6 empty] | Over effort = | 13

## Error Chart
Sprint # | % Error | Expected Hours | Actual Hours | Capacity
0 | 154.5455 | 33 | 84 | 50
1 | 45.1327 | 56.5 | 82 | 73
2 | 23.3333 | 30 | 37 | 40
3 | 54.1667 | 72 | 111 | 90
4 | -27.4648 | 71 | 51.5 | 80
5 | -30.9524 | 94.5 | 65.25 | 100
6 | 81.9307 | 101 | 183.75 | 112
7

## Retrospective
Sprint # | Date | Who | What did we do well? | What did we do wrong? | How can we improve next time?
0 | 2021-09-27 | Albert | As a team, we have good communcaiton | Didnt ask as many questions to professor as should have | Make sure we have priority on backlog
|  | Audrey | As a team, we have good communcaiton and meet when necessary. | Be more productive when waiting for feedback | Work on other items when waiting for feedback
|  | Brad | As a team, we have good communcaiton | Be more productive when waiting for feedback | send more emails to professor when need help, not jsut wait for office hours
|  | Joseph | As a team, we have good communcaiton. | Didnt complete tasks during sprint | work on other items when waiting for feedback
|  | Michael | As a team, we have good communcaiton | Didn't ask for help as much when needed | Make sure we have priority on backlog
1 | 2021-10-06 | Albert | met more as needed, communicated well | We didn't update the status of tasks as often as we should have. | assigning tasks before begining and continously marking when things are done
|  | Audrey | met more as needed, communicated well, got all tasks done during sprint | we worked on it a lot more then orginially planned | make better estimates of story point values
|  | Brad | met more as needed, communicated well | scrum wasnt to level of detail needed it to be at | make individual burndown charts, improve backlog
|  | Joseph | got all WI done, communicated well | we worked on it a lot more then orginially planned | plan the sprint accordingly, write down meeting inormation
|  | Michael | met more as needed, communicated well | didnt update keep track of how many hours worked each day | make nicer and easier way to see how long worked on each task each day
2 | 2021-10-19 | Albert | did better job on prioritizing items each sprint | not accurately keeping track of hours | at the end of each day, update hours | 1 | what did we do well?
|  | Audrey | improved our use of scrum | didnt communicate as much as could have | Still have meetings on scheduled days, even if its just to say what were going to work on, and ask questions
|  | Brad | more clear view of who was doing what task | didnt communicate as much, started late | plan the next sprint ahead of time in order to begin working on the WI during the first day of the sprint
|  | Joseph | split of tasks more evenly | didnt specify who was in charge of what work item | Clearly note who is in charge of which work item
|  | Michael | actually used our backlog | need to update hours daily, not at the end | Update hours at the end of every day
3 | 2021-10-27 | Albert | updated hours on more daily basis, communciated well | Some tasks were not very clearly defined during sprint planning | make sure everyone understands what they are working on during sprint planning | 2 | what did we do wrong?
|  | Audrey | i think we communicated well, met as needed, and were all made clear on what we needed to do | people working on each others assigned tasks | swap tasks if both parties working more on each others task, make that adjustment during sprint planning
|  | Brad | communicated well and asked for help when needed it from each other | having larger crunch time, working more on tasks in beginning of sprint | work on tasks evenly thorughout sprint to avoid all piling up at end
|  | Joseph | made progress on finding information for our resoruces, asking for help when needed | didnt update backlog on where at in progress for a task | update hours on a daily basis
|  | Michael | helped each other out as needed, did more research | not asking as many questions even though still confuesed on what needs to be done | send more emails when have questions regarding whats due, update backlog when finish a task
4 | 2021-11-13 | Albert | working on task independentely were productive | We didn't meet much often as previous sprints and we had lack of communication | more communication would encourage us to finish our tasks faster | 3 | how can we improve next time?
|  | Audrey | we planned for our sprint better | We didnt meet as much as we normally do, missing two days we typically meet, we didnt finish all the tasks for this sprint | be more productive when we dont meet, keep ourselves accountable, fill out hours after working on task
|  | Brad | Research seemed more productive than in past sprints | Didn't communicate as much, self-starting was difficult | Communicate more to increase hours worked
|  | Joseph | Reserch gathering for UM was good | Need to communicate with group more | Ask more about difficulty in tasks for better understanding
|  | Michael | sprint planning went very well | We did not work on things together, when these tasks required collaboration | Plan specifically what will be worked on during a given meeting or day
5 |  | Albert | prioritized tasks well and helped each other out | We left most of talks to work on them at the end of the sprint, which contributed to uncomplete some of our tasks. Moreover, we didn't updated our hours on our oun sprints daily | Working at least an hour everyday on our own tasks and communicate every day to be aware of each others' progress
|  | Audrey | we did well planning this sprint and leaving knowing we all needed to with breaking up the core components | Since it was Thanksgivng break, we did not communicate as much as we normally would have. Also not asking questions when unsure of a task and fillowing hours out | Communicate to the person who is blocking us and work togehter to make sure the task get completed. Plan out a better schedule as to finish everything during the sprint
|  | Brad | improved our use of scrum | Some tasks not as clearly defined/described in the sprint backlog | Ask for clarification on tasks sooner, break down work more when necessary
|  | Joseph | working on task independentely were productive | Didn't ask for help as much when needed | Make sure we have priority on backlog
|  | Michael | Spring Planning went well | A lot of work was not completed and carried over | Plan more specifically when work will be done
6 |  | Albert | Helped each other out to finish our tasks on time by the end of the sprint | Some of us were blocked for some days which contributed to get behind our sprint tasks | If we notice that we are blocked on a task, we should let everyone know to finish our tasks faster
|  | Audrey | writing code for UM implementations was completed on time as we planned | We didn't update the status of tasks as often as we should have. | at the end of each day, update hours
|  | Brad | spring Planning went well | didnt update keep track of how many hours worked each day | Try to avoid carryover from previous sprint
|  | Joseph | did better job prioritizing items each time | didnt communicate as much as could have | work on other items when waiting for feedback
|  | Michael | We were able to complete our work despite caryover from the previous sprint | Too much work was saved for the last few days | Moving forward we need to be better at completing all tasks in a sprint and not letting things get carried over to the next sprint
7 |  | Albert
Audrey
Brad
Joseph
Michael
8 |  | Albert
Audrey
Brad
Joseph
Michael

## Sprint 3
Sprint 3 | milestone 2
| Start Date | 2021-10-21 |  | Day of Sprint | Actual Effort |  |  | Day of Sprint | Forecast | Actual
| End Date | 2021-10-26 |  | 0 | 72 |  |  | 0 | 72 | 72
| Sprint Length | 6 |  | 1 | 70 |  |  | 1 | 60 | 70
| Team Size | 5 |  | 2 | 60 |  |  | 2 | 48 | 60
| Team Capacity | 90 |  | 3 | 53.5 |  |  | 3 | 36 | 53.5
| Total Sprint SP | 72 |  | 4 | 37.5 |  |  | 4 | 24 | 37.5
| SP/Day | 12 |  | 5 | 20 |  |  | 5 | 12 | 20
|  |  |  | 6 | 0 |  |  | 6 | 0 | 0
|  |  |  | th | f | s | s | m | t
Who | Tasks | SP | Day of Sprint (hours worked)
|  |  | 0 | 1 | 2 | 3 | 4 | 5 | 6
Albert
| Test case datastudent discounts, careers | 2 | 0 | 0 | 0 | 0 | 4 | 1 | 0
| IPs/URLs of external servers | 4 | 0 | 0 | 2 | 3 | 2 | 2 | 0
| Network Diagram: 3rd party services & servers | 4 | 0 | 0 | 0 | 0 | 2 | 2 | 0
| Schedule Sprints | 2 | 0 | 0 | 0 | 0 | 0 | 1 | 0
| Generate Roadmap from schedule | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 4
SP Decrement |  |  | 0 | 0 | 1 | 1 | 4 | 4 | 4
Audrey
| Test case data: matching, messaging | 2 | 0 | 0 | 2 | 1 | 2 | 0 | 0
| Network Diagram: Requests | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 3
| Determine critical path tasks | 4 | 0 | 0 | 0 | 1 | 2 | 2 | 3
| Test plan: testing schedule | 4 | 0 | 0 | 0 | 0.5 | 0 | 1.5 | 2
SP Decrement |  |  | 0 | 0 | 1 | 2 | 4 | 3 | 4
Brad
| Choose server provider | 4 | 0 | 1.5 | 1 | 0 | 0 | 0 | 0
| Test case data: schedules, classes | 2 | 0 | 0 | 2 | 0.5 | 2.75 | 0 | 0
| Determine feature development order | 4 | 0 | 0 | 0 | 0 | 2 | 2 | 0.5
| Validate schedule with team | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0.5
| Risk Identification | 3 | 0 | 0 | 0.5 | 0 | 0 | 0.75 | 0
| Other | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2
SP Decrement |  |  | 0 | 2 | 3 | 0.5 | 3 | 4.5 | 1
Joseph
| Information gathering: aid, careers, schedule of classes | 4 | 0 | 0 | 4 | 1.5 | 1 | 0 | 0
| Test case data: aid | 2 | 0 | 0 | 2 | 2 | 1.5 | 1.5 | 2
| Network Diagram: Node system specs | 2 | 0 | 0 | 0.5 | 1.5 | 1 | 1.5 | 2
| Schedule Project Milestones | 2 | 0 | 0 | 0 | 0 | 0.5 | 0.5 | 1.5
| Progression and Regression Testing details | 4 | 0 | 0 | 0 | 0 | 0 | 1.5 | 2
SP Decrement |  |  | 0 | 0 | 4 | 2 | 2 | 2 | 4
Michael
| Test case data: course rating, registration, login, logout | 2 | 0 | 0 | 2 | 1 | 0 | 2 | 0
| Network Diagram: Responses | 4 | 0 | 0 | 0 | 0 | 2 | 2 | 0
| Plan deployment process | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 4
| Detail testing environment | 4 | 0 | 0 | 0 | 0 | 0 | 2 | 3
| Risk Mitigation | 2 | 0 | 0 | 0 | 0 | 2 | 0 | 3
SP Decrement |  |  | 0 | 0 | 1 | 1 | 3 | 4 | 7
Daily Scrum Meeting
Day of Sprint | Who | What did you work on Yesterday? |  |  | What are you working on today? |  |  | Are You Blocked?
Day 1 | Albert | n/a |  |  | n/a |  |  | no
| Audrey | n/a |  |  | n/a |  |  | no
| Brad | n/a |  |  | choose service provider |  |  | no
| Joseph | n/a |  |  | n/a |  |  | no
| Michael | n/a |  |  | n/a |  |  | no
Day 2 | Albert | n/a |  |  | ip/urls |  |  | no
| Audrey | n/a |  |  | test cases |  |  | no
| Brad | choose service provider |  |  | choose service provider, test cases, risk identification |  |  | no
| Joseph | n/a | [5 empty] | no
| Michael | n/a |  |  | test cases |  |  | no
Day 3 | Albert | ip/urls |  |  | test cases, network diagram |  |  | no
| Audrey | test cases |  |  | test cases, gnatt chart |  |  | no
| Brad | choose service provider, test cases, risk identification |  |  | test cases |  |  | no
| Joseph | [6 empty] | no
| Michael | test cases |  |  | test cases |  |  | no
Day 4 | Albert | test cases, network diagram |  |  | test cases, network diagram |  |  | no
| Audrey | test cases, gnatt chart |  |  | test cases, critical path |  |  | no
| Brad | test cases |  |  | test cases, feature development order |  |  | no
| Joseph |  |  |  | test cases, phone call, emails, research specs |  |  | no
| Michael | test cases |  |  | test cases, looking at risk identification |  |  | no
Day 5 | Albert | test cases, network diagram |  |  | schedule sprint, network diagram |  |  | yes
| Audrey | test cases, critical path |  |  | testing scedule, critical path, requests |  |  | no
| Brad | test cases, feature development order |  |  | more feature development order, risk, validate schedule |  |  | no
| Joseph | test cases, phone call, emails, research specs |  |  | test cases, specs, emails |  |  | yes
| Michael | test cases, looking at risk identification |  |  | test cases, risk mitagation |  |  | no
Day 6 | Albert | schedule sprint, network diagram |  |  | roadmap |  |  | no
| Audrey | testing scedule, critical path, requests |  |  | requests, critical path, testing schedule |  |  | no
| Brad | more feature development order, risk, validate schedule |  |  | feature development order, validate schedule, other |  |  | no
| Joseph | test cases, specs, emails | [5 empty] | no
| Michael | test cases, risk mitagation |  |  | plan deployment process, testing enviornment, risk mitagation |  |  | no

## Story Point Breakdown (hidden)
Sprint 0 | total = 30
SP
| Proposal |  |  | 30
|  | Features | 24
|  | Needs/Problems | 2
|  | Goals/Solution | 2
|  | Obstacles & Solutions | 2
30
Sprint 1 | total = 35
SP
| BRD |  |  | 37
|  | Summary, Glossary, Appendix | 3
|  | Requirements | 18
|  | Processes | 14
|  | In and out of scope | 2
| Tech Spec |  |  | 4
|  | OS | 1
|  | Product | 2
|  | Project | 1
| Site Map |  |  | 8
|  | Design | 5
|  | Errors | 3
| HL Design |  |  | 7
|  | Software | 3.5
|  | Hardware | 3.5
56
Sprint 2 | total =
SP

## Sprint 2
Sprint 2 | test plan
| Start Date | 2021-10-13 |  | Day of Sprint | Actual Effort |  |  | Day of Sprint | Forecast | Actual Effort
| End Date | 2021-10-18 |  | 0 | 30 |  |  | 0 | 30 | 30
| Sprint Length | 6 |  | 1 | 30 |  |  | 1 | 25 | 30
| Team Size | 5 |  | 2 | 30 |  |  | 2 | 20 | 30
| Team Capacity | 30 |  | 3 | 22 |  |  | 3 | 15 | 22
| Total Sprint SP | 30 |  | 4 | 16 |  |  | 4 | 10 | 16
| SP/Day | 5 |  | 5 | 6 |  |  | 5 | 5 | 6
|  |  |  | 6 | 0 |  |  | 6 | 0 | 0
|  |  |  | w | th | f | s | s | m
Who | Tasks | SP | Day of Sprint (hours worked)
|  |  | 0 | 1 | 2 | 3 | 4 | 5 | 6
Albert
| Test cases: Discounts | 3 | 0 | 0 | 0 | 0 | 2 | 1 | 0
| Test cases: Careers | 3 | 0 | 0 | 0 | 0 | 1 | 2 | 3
SP Decrement |  |  | 0 | 0 | 0 | 0 | 2 | 2 | 2
Audrey
| Test cases: Matching | 3 | 0 | 0 | 0 | 4 | 1 | 1 | 1
| Test cases: Messaging | 3 | 0 | 0 | 0 | 0 | 2 | 1 | 1
SP Decrement |  |  | 0 | 0 | 0 | 3 | 2 | 1 | 0
Brad
| Test cases: Schedule Building | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 1
| Test cases: Schedule of Classes | 3 | 0 | 0 | 0 | 0 | 0 | 1 | 1
SP Decrement |  |  | 0 | 0 | 0 | 1 | 0 | 3 | 2
Joseph
| Phone calls: career center | 1 | 0 | 0 | 0 | 2 | 0 | 0 | 1
| Phone calls: financial aid | 1 | 0 | 0 | 0 | 2 | 0 | 0 | 1
| Phone calls: David Brown (SoC) | 1 | 0 | 0 | 0 | 3 | 0.5 | 0 | 1
| Test cases: Aid | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 1
SP Decrement |  |  | 0 | 0 | 0 | 3 | 1 | 1 | 1
Michael
| Test cases: Course Difficulty | 3 | 0 | 0 | 0 | 0 | 0 | 2 | 1
| Test cases: Registration | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0
| Test cases: Login | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0
| Test cases: Logout | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
SP Decrement |  |  | 0 | 0 | 0 | 1 | 1 | 3 | 1
Daily Scrum Meeting
Day of Sprint | Who | What did you work on Yesterday? |  |  | What are you working on today? |  |  | Are You Blocked?
Day 1 | Albert | n/a |  |  | n/a |  |  | no
| Audrey | n/a |  |  | n/a |  |  | no
| Brad | n/a |  |  | n/a |  |  | no
| Joseph | n/a |  |  | n/a |  |  | no
| Michael | n/a |  |  | n/a |  |  | no
Day 2 | Albert | n/a |  |  | n/a |  |  | no
| Audrey | n/a |  |  | n/a |  |  | no
| Brad | n/a |  |  | n/a |  |  | no
| Joseph | n/a |  |  | n/a |  |  | no
| Michael | n/a |  |  | n/a |  |  | no
Day 3 | Albert | n/a |  |  | n/a |  |  | no
| Audrey | n/a |  |  | match test cases |  |  | no
| Brad | n/a |  |  | schedule builder test cases |  |  | no
| Joseph | n/a |  |  | phone calls, aid test cases |  |  | yes
| Michael | n/a |  |  | registration test cases |  |  | no
Day 4 | Albert | n/a |  |  | career opps, student discounts test cases |  |  | no
| Audrey | match test cases |  |  | messaging, matching test cases |  |  | no
| Brad | schedule builder test cases |  |  | n/a |  |  | no
| Joseph | phone calls, aid test cases |  |  | phone calls |  |  | yes
| Michael | registration test cases |  |  | login test cases |  |  | no
Day 5 | Albert | career opps, student discounts test cases |  |  | discounts, careers test cases |  |  | yes
| Audrey | messaging, matching test cases |  |  | messaging, matching test cases |  |  | no
| Brad | n/a |  |  | schedule building, schedule of classes test cases |  |  | no
| Joseph | phone calls |  |  | aid test cases |  |  | yes
| Michael | login test cases |  |  | course reviews, logout test cases |  |  | no
Day 6 | Albert | discounts, careers test cases |  |  | careers test cases |  |  | no
| Audrey | messaging, matching test cases |  |  | messaging, matching test cases |  |  | no
| Brad | schedule building, schedule of classes test cases |  |  | schedule building, schedule of classes test cases |  |  | no
| Joseph | aid test cases |  |  | aid test cases, phone calls |  |  | no
| Michael | course reviews, logout test cases |  |  | course reviews test cases |  |  | no

## Sprint 1
Sprint 1 | milestone 1
| Start Date | 2021-09-29 |  | Day of Sprint | Actual Effort |  | Day of Sprint | Forecast | Actual Effort
| End Date | 2021-10-05 |  | 0 | 56.5 |  | 0 | 56.5 | 56.5
| Sprint Length | 7 |  | 1 | 53 |  | 1 | 48.4286 | 52
| Team Size | 5 |  | 2 | 53 |  | 2 | 40.3571 | 52
| Team Capacity | 60 |  | 3 | 45 |  | 3 | 32.2857 | 44
| Total Sprint SP | 56.5 |  | 4 | 40 |  | 4 | 24.2143 | 38
| SP/Day | 8.0714 |  | 5 | 26 |  | 5 | 16.1429 | 25
|  |  |  | 6 | 15 |  | 6 | 8.0714 | 14
|  |  |  | 7 | 0 |  | 7 | 0 | 0
Who | Tasks | SP | Day of Sprint (hours worked)
|  |  | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7
Albert
| Process - Student Discounts | 2 | 0 | 1 | 0 | 1 | 0 | 0 | 1 | 0
| Process - Career Opp | 2 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1
| Requirements - Student Discounts | 2 | 0 | 1 | 0 | 0 | 2 | 2 | 1 | 1
| Requirements - Career Opps | 2 | 0 | 0 | 0 | 1 | 1 | 2 | 0 | 1.5
| View - Student Discounts | 0.5 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0.5
| View - Career Opps | 0.5 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0
| OS Requirement | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2
SP Decrement |  |  | 0 | 1 | 0 | 2 | 1 | 2 | 1 | 3
Audrey
| Glossary | 0.5 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0
| Document Version | 0.5 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0
| In Scope | 1 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 0
| Process - Matching | 2 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1
| Requirements - Matching | 2 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1
| View - Matching | 0.5 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1
| Error Hangling | 4 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 2
| Project Requirements | 1.5 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1
SP Decrement |  |  | 0 | 1 | 0 | 2 | 1 | 3 | 3 | 2
Brad
| Process - Comparison | 2 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0
| Process - Builder | 2 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0
| Requirements - Comparison | 2 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 1
| Requirements - Builder | 2 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 2
| Requirements - Messaging | 2 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0
| View - Comparison | 0.5 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1
| View - Messaging | 0.5 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0
| View - Builder | 0.5 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1
| Hardware | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1
| Software | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1
| Choosing Hardware and Software | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0
SP Decrement |  |  | 0 | 1 | 0 | 1 | 2 | 5 | 4 | 5.5
Joseph
| Executive Summary | 0.5 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0
| Project Description | 0.5 | 0 | 0.5 | 0 | 0.5 | 0 | 0 | 0 | 0
| Process - Aid | 2 | 0 | 1 | 0 | 1.5 | 1 | 2 | 2 | 2
| Requirement - Aid | 2 | 0 | 1 | 0 | 0 | 2 | 1 | 2 | 2
| View - Aid | 0.5 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 2
SP Decrement |  |  | 0 | 0.5 | 0 | 1 | 1 | 1 | 1 | 1
Michael
| Out of Scope | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1
| Process - Course Difficulty | 2 | 0 | 2 | 0 | 1 | 1 | 0 | 1 | 1
| Requirements - Course Difficulty | 2 | 0 | 1 | 0 | 2 | 1 | 0 | 1 | 2
| Requirements - Schedule of Classes | 2 | 0 | 0 | 0 | 2 | 1 | 2 | 0 | 0
| Requirements - Core | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0
| View - Schule of Classes | 0.5 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0
| View - Course Difficulty | 0.5 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 1
| Product Requirements | 1.5 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0
SP Decrement |  |  | 0 | 1 | 0 | 2 | 1 | 2 | 2 | 2.5

## Sprint 0
Sprint 0 | proposal | [5 empty] | Day of Sprint | Forecast | Actual Effort
| Start Date | 2021-09-22 |  | Day of Sprint | Actual Effort |  | 0 | 33 | 33
| End Date | 2021-09-27 |  | 0 | 33 |  | 1 | 27.5 | 29
| Sprint Length | 6 |  | 1 | 29 |  | 2 | 22 | 29
| Team Size | 5 |  | 2 | 29 |  | 3 | 16.5 | 19
| Team Capacity | 50 |  | 3 | 19 |  | 4 | 11 | 16
| Total Sprint SP | 33 |  | 4 | 16 |  | 5 | 5.5 | 10
| SP/Day | 5.5 |  | 5 | 10 |  | 6 | 0 | 5
|  |  |  | 6 | 5
Who | Tasks | SP | Day of Sprint (hours worked)
|  |  | 0 | 1 | 2 | 3 | 4 | 5 | 6
Albert
| Obstacles & Solutions | 2 | 0 | 2 | 0 | 1 | 1 | 0 | 1
| Feature: Class Opp | 3 | 0 | 0 | 0 | 0 | 0 | 2 | 2
| Featue: Student Discounts | 3 | 0 | 0 | 0 | 0 | 3 | 1 | 0
SP Decrement |  |  | 0 | 1 | 0 | 0 | 3 | 1.5 | 2.5
Audrey
| Introduction | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 1
| Feature: Matching | 3 | 0 | 0 | 1 | 4 | 1 | 4 | 4
SP Decrement |  |  | 0 | 1 | 0 | 2 | 0 | 0.5 | 0.5
Brad
| Feature: Builder | 3 | 0 | 2 | 0 | 2 | 1 | 2 | 2
| Feature: Comparison | 3 | 0 | 0 | 0 | 2 | 2 | 2 | 2
| Feaure: Matching | 3 | 0 | 0 | 0 | 2 | 0 | 0 | 1
SP Decrement |  |  |  | 1 | 0 | 3 | 0 | 2 | 3
Joseph
| Goals/Solution | 1 | 0 | 1 | 0 | 2 | 0 | 1 | 0
| Feature: Aid | 3 | 0 | 0 | 0 | 4 | 1 | 4 | 5
SP Decrement |  |  | 0 | 0 | 0 | 2 | 2 | 0 | 0
Michael
| Needs/Problems | 2 | 0 | 0 | 0 | 1 | 0 | 0 | 1
| Feature: Course Diff | 3 | 0 | 1 | 0 | 4 | 0 | 2 | 2
| Feature: Schedule of Class | 3 | 0 | 0 | 0 | 1 | 1 | 2 | 2
SP Decrement |  |  | 0 | 1 | 0 | 3 | 0 | 2 | 2

## Kanban Board (hidden)
Sprint 2 | Assigned | To Do | In Progress | Blocked | Done
| Joseph |  |  |  | Phone calls: career center
| Joseph |  |  |  | Phone calls: financial aid
| Joseph |  |  |  | Phone calls: David Brown (schedule of classes)
| Brad |  |  |  | Test cases: Schedule Building
| Albert |  |  |  | Test cases: Discounts
| Audrey |  |  |  | Test cases: Matching
| Joseph |  |  |  | Test cases: Aid
| Michael |  |  |  | Test cases: Course Difficulty
| Albert |  |  |  | Test cases: Careers
| Michael |  |  |  | Test cases: Schedule of Classes
| Audrey |  |  |  | Test cases: Messaging
| Michael |  |  |  | Test cases: Registration
| Michael |  |  |  | Test cases: Login
| Michael |  |  |  | Test cases: Logout
Sprint 3 | Assigned | To Do | In Progress | Blocked | Done
| Albert |  |  |  | Test case data: student discounts, careers
| Audrey |  |  |  | Test case data: matching, messaging
| Brad |  |  |  | Test case data: schedules, classes
| Joseph |  |  |  | Test case data: aid
| Michael |  |  |  | Test case data: course rating, registration, login, logout
| Audrey |  |  |  | Test plan: testing schedule
| Michael |  |  |  | Detail testing environment
| Joseph |  |  |  | Progression and Regression Testing details
| Joseph |  |  |  | Information gathering: aid, careers, schedule of classes
| Brad |  |  |  | Network Diagram: Choose server provider
| Joseph |  |  |  | Network Diagram: Node system specs
| Albert |  |  |  | Network Diagram: IPs/URLs of external servers
| Audrey |  |  |  | Network Diagram: Requests
| Michael |  |  |  | Network Diagram: Responses
| Albert |  |  |  | Network Diagram: 3rd party services & servers
| Brad |  |  |  | Determine feature development order
| Audrey |  |  |  | Determine critical path tasks
| Michael |  |  |  | Plan deployment process
| Brad |  |  |  | Risk Identification
| Michael |  |  |  | Risk Mitigation
| Joseph |  |  |  | Schedule Project Milestones
| Albert |  |  |  | Schedule Sprints
| Brad |  |  |  | Validate schedule with team
| Albert |  |  |  | Generate Roadmap from schedule