## Project Backlog
Work Item | Priority | Story Point | Internal Due Date | External Due Date
Tech Spec | 1 | 4 | 2022-03-05 | 2022-03-07
Registration | 2 | 25.5 | 2022-03-05 | 2022-03-07
Login | 3 | 6.5 | 2022-03-05 | 2022-03-07
Logout | 4 | 18 | 2022-03-05 | 2022-03-07
User Management | 5 | 7 | 2022-03-05 | 2022-03-07
User Access Control | 6 | 20 | 2022-03-05 | 2022-03-07
Usage Analysis Design | 7 | 21 | 2022-03-05 | 2022-03-07
Schedule Builder | 8 | 24 | 2022-03-05 | 2022-03-07
Messages | 9 | 22 | 2022-03-05 | 2022-03-07
Schedule of Classes | 10 | 22 | 2022-03-05 | 2022-03-07
Automated Moderating | 11 | 20.25 | 2022-03-05 | 2022-03-07
GPA Calculator | 12 | 23 | 2022-03-05 | 2022-03-07
Student Discounts | 13 | 22 | 2022-03-05 | 2022-03-07
Feedback | 14 | 2 | 2022-03-05 | 2022-03-07
Recipe Sharing | 15 | 1.25 | 2022-03-05 | 2022-03-07
Project Proposal | Done | 30 | 2021-09-06 | 2021-09-06
BRD | Done | 37 | 2021-10-06 | 2021-10-06
Site Map | Done | 8.5 | 2021-10-06 | 2021-10-06
HL Design | Done | 7 | 2021-10-06 | 2021-10-06
Tech Spec | Done | 4 | 2021-10-06 | 2021-10-06
Test Cases | Done | 30 | 2021-10-18 | 2021-10-27
Network Diagram | Done | 26 | 2021-10-26 | 2021-10-27
Project Plan | Done | 22 | 2021-10-26 | 2021-10-27 |  | tu/th | tu | th | fri
Roadmap | Done | 2 | 2021-10-26 | 2021-10-27 | albert |  | class at 7
Test Plan | Done | 22 | 2021-10-26 | 2021-10-27 | audrey |  | free after 4 | free after 3
LL Design | Done | 24.5 | 2021-11-12 | 2021-12-08 | brad | class 12:30-1:45
LL Design | Done | 46.5 | 2021-11-24 | 2021-12-08 | devarsh
Core Requirements | Done | 42 | 2021-11-24 | 2021-12-08 | jacob | 3 works
LL Design | Done | 31 | 2021-12-07 | 2021-12-08 | joseph
Core Requirements | Done | 32 | 2021-12-07 | 2021-12-08 | michael |  | class at 7
UM | Done | 19 | 2021-12-07 | 2021-12-08 | sze
Logging | Done | 19 | 2021-12-07 | 2021-12-08 | goal |  | 2022-04-05 | 2022-04-05 | 2?
Feedback | Done | 8 | 2022-01-22 | 2022-01-24
Tech Spec | Done | 12 | 2022-01-22 | 2022-01-24
Registration | Done | 32 | 2022-01-22 | 2022-01-24
Login | Done | 32 | 2022-01-22 | 2022-01-24
Logout | Done | 32 | 2022-01-22 | 2022-01-24
Error Handling | Done | 32 | 2022-01-22 | 2022-01-24
BRD | Done | 14 | 2022-02-05 | 2022-02-05
Project Plan | Done | 3 | 2022-01-29 | 2022-01-29
Feedback | Done | 6 | 2022-02-05 | 2022-02-08
Tech Spec | Done | 14 | 2022-02-05 | 2022-02-08
Registration | Done | 17 | 2022-02-05 | 2022-02-08
Login | Done | 11 | 2022-02-05 | 2022-02-08
Logout | Done | 28 | 2022-02-05 | 2022-02-08
Error Handling | Done | 17 | 2022-02-05 | 2022-02-08
Sitemap | Done | 0.25 | 2022-02-19 | 2022-02-20
Feedback | Done | 5 | 2022-02-19 | 2022-02-20
Tech Spec | Done | 9.5 | 2022-02-19 | 2022-02-20
Registration | Done | 48 | 2022-02-19 | 2022-02-20
Login | Done | 22 | 2022-02-19 | 2022-02-20
Logout | Done | 38 | 2022-02-19 | 2022-02-20
Book Selling | Done | 3 | 2022-02-19 | 2022-02-20
GPA Calculator | Done | 3 | 2022-02-19 | 2022-02-20
Recipe Sharing | Done | 1.25 | 2022-02-19 | 2022-02-20
Event Planning | Done | 1.25 | 2022-02-19 | 2022-02-20
Automated Moderating | Done | 0.5 | 2022-02-19 | 2022-02-20
User Management | Done | 12 | 2022-02-19 | 2022-02-20
User Access Control | Done | 20 | 2022-02-19 | 2022-02-20
Usage Analysis Design | Done | 27 | 2022-02-19 | 2022-02-20

## Sprint Backlog
| Priority | Assigned | Story Point | Sprint | Status | Internal Due Date | External Due Date | Work Item Lead | Associated Work Item | 1 Story Point = 1 hour
Tech Approval: HTML | 1 | Michael | 2 | 10 | In Progress | 2022-03-05 | 2022-03-05 | Michael | Tech Specs |  | Member | SP
Recipe Sharing Site Map | 2 | Devarsh | 1 | 10 | In Progress | 2022-03-05 | 2022-03-05 | Devarsh | Recipe Sharing |  | Albert | 34
Review Recipe Sharing Test Plan | 3 | Devarsh | 0.25 | 10 | In Progress | 2022-03-05 | 2022-03-05 | Devarsh | Recipe Sharing |  | Audrey | 31
Automated Moderating Test Plan | 4 | Joseph | 0.25 | 10 | In Progress | 2022-03-05 | 2022-03-05 | Joseph | Automated Moderating |  | Brad | 40
Address test parity (tests should pass when desired result happens) (Archiving) | 5 | Michael | 2 | 10 | In Progress | 2022-03-05 | 2022-03-05 | Michael | Feedback |  | Devarsh | 21.25
Tech Approval: CSS | 6 | Michael | 2 | 10 | In Progress | 2022-03-05 | 2022-03-05 | Michael | Tech Specs |  | Jacob | 30
Email verification behavior diagram | 7 | Joseph | 2 | 10 | Todo | 2022-03-05 | 2022-03-05 | Albert | Registration |  | Joseph | 27.25
Registration Class Diagram | 8 | Albert | 2 | 10 | Todo | 2022-03-05 | 2022-03-05 | Albert | Registration |  | Michael | 34
Authentication Tokens/authentication cookies class/database diagram | 9 | Michael | 2 | 10 | Todo | 2022-03-05 | 2022-03-05 | Audrey | Authentication |  | Sze | 21
Review logout for error handling | 10 | Joseph | 2 | 10 | Todo | 2022-03-05 | 2022-03-05 | Brad | Logout |  | Expected total | 238.5
User Management frontend implementation (single CRUD operations) | 11 | Jacob | 2 | 10 | Todo | 2022-03-05 | 2022-03-05 | Audrey | UM |  | Actual total | 238.5
User Management frontend implementation (file upload for bulk operations) | 12 | Jacob | 3 | 10 | Todo | 2022-03-05 | 2022-03-05 | Audrey | UM |  | Unassigned | 0
User Management frontend implementation (bulk CRUD operations) | 13 | Jacob | 2 | 10 | Todo | 2022-03-05 | 2022-03-05 | Audrey | UM |  | Expected SP/person | 29.8125
Registration Tests | 14 | Albert | 4 | 10 | Todo | 2022-03-05 | 2022-03-05 | Albert | Registration
Email verification tests | 15 | Audrey | 2 | 10 | Todo | 2022-03-05 | 2022-03-05 | Albert | Registration
Login Tests | 16 | Audrey | 1 | 10 | In Progress | 2022-03-05 | 2022-03-05 | Audrey | Login
Logout Tests | 17 | Brad | 4 | 10 | Todo | 2022-03-05 | 2022-03-05 | Brad | Logout
Registration backend implementation | 18 | Joseph | 1.5 | 10 | In Progress | 2022-03-05 | 2022-03-05 | Albert | Registration
Registration frontend implementation | 19 | Albert | 6 | 10 | Todo | 2022-03-05 | 2022-03-05 | Albert | Registration
Email verification backend implementation | 20 | Michael | 4 | 10 | Todo | 2022-03-05 | 2022-03-05 | Albert | Registration
Email verification frontend implementation | 21 | Audrey | 2.5 | 10 | Todo | 2022-03-05 | 2022-03-05 | Albert | Registration
Login backend implementation | 22 | Audrey | 0.5 | 10 | In Progress | 2022-03-05 | 2022-03-05 | Audrey | Login
Login frontend implementation | 23 | Audrey | 1 | 10 | In Progress | 2022-03-05 | 2022-03-05 | Audrey | Login
Logout backend implementation | 24 | Brad | 4 | 10 | Todo | 2022-03-05 | 2022-03-05 | Brad | Logout
Logout frontend implementation | 25 | Brad | 4 | 10 | Todo | 2022-03-05 | 2022-03-05 | Brad | Logout
Login error handling implementation | 26 | Audrey | 2 | 10 | Todo | 2022-03-05 | 2022-03-05 | Audrey | Login
Logout error handling implementation | 27 | Brad | 4 | 10 | Todo | 2022-03-05 | 2022-03-05 | Brad | Logout
Registration error handling implementation | 28 | Joseph | 1.5 | 10 | Todo | 2022-03-05 | 2022-03-05 | Albert | Registration
Usage Analysis Dashboard Query Tests | 29 | Sze | 3 | 10 | Todo | 2022-03-05 | 2022-03-05 | Sze | Usage Analysis Dashboard
Usage Analysis Dashboard Graph/chart tests? | 30 | Sze | 4 | 10 | Todo | 2022-03-05 | 2022-03-05 | Sze | Usage Analysis Dashboard
Usage Analysis Dashboard Backend implementation Query AS02.1 | 31 | Sze | 1 | 10 | Todo | 2022-03-05 | 2022-03-05 | Sze | Usage Analysis Dashboard
Usage Analysis Dashboard Backend implementation Query AS02.2 | 32 | Sze | 1 | 10 | Todo | 2022-03-05 | 2022-03-05 | Sze | Usage Analysis Dashboard
Usage Analysis Dashboard Backend implementation Query AS02.3 | 33 | Sze | 1 | 10 | Todo | 2022-03-05 | 2022-03-05 | Sze | Usage Analysis Dashboard
Usage Analysis Dashboard Backend implementation Query AS02.4 | 34 | Sze | 1 | 10 | Todo | 2022-03-05 | 2022-03-05 | Sze | Usage Analysis Dashboard
Usage Analysis Dashboard Backend implementation Query AS02.5 | 35 | Sze | 1 | 10 | Todo | 2022-03-05 | 2022-03-05 | Sze | Usage Analysis Dashboard
Usage Analysis Dashboard Backend implementation Query AS02.6 | 36 | Sze | 1 | 10 | Todo | 2022-03-05 | 2022-03-05 | Sze | Usage Analysis Dashboard
Usage Analysis Dashboard Frontend implementation Bar graphs | 37 | Sze | 4 | 10 | Todo | 2022-03-05 | 2022-03-05 | Sze | Usage Analysis Dashboard
Usage Analysis Dashboard Frontend implementation Trend charts | 38 | Sze | 4 | 10 | Todo | 2022-03-05 | 2022-03-05 | Sze | Usage Analysis Dashboard
User Access Control Behavior Diagrams | 39 | Devarsh | 4 | 10 | In Progress | 2022-03-05 | 2022-03-05 | Devarsh | User Access Control
User Access Control Class/database diagram | 40 | Devarsh | 2 | 10 | In Progress | 2022-03-05 | 2022-03-05 | Devarsh | User Access Control
User Access Control Tests | 41 | Devarsh | 4 | 10 | Todo | 2022-03-05 | 2022-03-05 | Devarsh | User Access Control
User Access Control Backend implementation | 42 | Devarsh | 6 | 10 | Todo | 2022-03-05 | 2022-03-05 | Devarsh | User Access Control
User Access Control Frontend implementation for access denial message | 43 | Devarsh | 2 | 10 | Todo | 2022-03-05 | 2022-03-05 | Devarsh | User Access Control
User Access Control Frontend implementation for access denial redirection | 44 | Devarsh | 2 | 10 | Todo | 2022-03-05 | 2022-03-05 | Devarsh | User Access Control
Schedule Builder Behavior Diagrams | 45 | Brad | 5 | 10 | Todo | 2022-03-05 | 2022-03-05 | Brad | Schedule Builder
Schedule Builder Class diagrams | 46 | Brad | 2 | 10 | Todo | 2022-03-05 | 2022-03-05 | Brad | Schedule Builder
Schedule Builder Database diagrams | 47 | Brad | 1 | 10 | Todo | 2022-03-05 | 2022-03-05 | Brad | Schedule Builder
Schedule Builder Tests | 48 | Brad | 4 | 10 | Todo | 2022-03-05 | 2022-03-05 | Brad | Schedule Builder
Schedule Builder Backend implementation | 49 | Brad | 8 | 10 | Todo | 2022-03-05 | 2022-03-05 | Brad | Schedule Builder
Schedule Builder Frontend Implementation | 50 | Brad | 4 | 10 | Todo | 2022-03-05 | 2022-03-05 | Brad | Schedule Builder
Student Discounts Behavior Diagrams | 51 | Albert | 5 | 10 | Todo | 2022-03-05 | 2022-03-05 | Albert | Student Discounts
Student Discounts Class diagrams | 52 | Albert | 2 | 10 | Todo | 2022-03-05 | 2022-03-05 | Albert | Student Discounts
Student Discounts Database diagrams | 53 | Albert | 1 | 10 | Todo | 2022-03-05 | 2022-03-05 | Albert | Student Discounts
Student Discounts Tests | 54 | Albert | 4 | 10 | Todo | 2022-03-05 | 2022-03-05 | Albert | Student Discounts
Student Discounts Backend implementation | 55 | Albert | 6 | 10 | Todo | 2022-03-05 | 2022-03-05 | Albert | Student Discounts
Student Discounts Frontend Implementation | 56 | Albert | 4 | 10 | Todo | 2022-03-05 | 2022-03-05 | Albert | Student Discounts
Message Behavior Diagrams | 57 | Audrey | 5 | 10 | Todo | 2022-03-05 | 2022-03-05 | Audrey | Messages
Message Class diagrams | 58 | Audrey | 2 | 10 | Todo | 2022-03-05 | 2022-03-05 | Audrey | Messages
Message Database diagrams | 59 | Audrey | 1 | 10 | Todo | 2022-03-05 | 2022-03-05 | Audrey | Messages
Message Tests | 60 | Audrey | 4 | 10 | Todo | 2022-03-05 | 2022-03-05 | Audrey | Messages
Message Backend implementation | 61 | Audrey | 6 | 10 | Todo | 2022-03-05 | 2022-03-05 | Audrey | Messages
Message Frontend Implementation | 62 | Audrey | 4 | 10 | Todo | 2022-03-05 | 2022-03-05 | Audrey | Messages
GPA Calc/Leaderboard Behavior Diagrams | 63 | Jacob | 5 | 10 | Todo | 2022-03-05 | 2022-03-05 | Jacob | GPA Calculator
GPA Calc/Leaderboard Class diagrams | 64 | Jacob | 2 | 10 | Todo | 2022-03-05 | 2022-03-05 | Jacob | GPA Calculator
GPA Calc/Leaderboard Database diagrams | 65 | Jacob | 1 | 10 | Todo | 2022-03-05 | 2022-03-05 | Jacob | GPA Calculator
GPA Calc/Leaderboard Tests | 66 | Jacob | 4 | 10 | Todo | 2022-03-05 | 2022-03-05 | Jacob | GPA Calculator
GPA Calc/Leaderboard Backend implementation | 67 | Jacob | 4 | 10 | Todo | 2022-03-05 | 2022-03-05 | Jacob | GPA Calculator
GPA Calc/Leaderboard Frontend Implementation | 68 | Jacob | 7 | 10 | Todo | 2022-03-05 | 2022-03-05 | Jacob | GPA Calculator
Automated Moderting Behavior Diagrams | 69 | Joseph | 5 | 10 | Todo | 2022-03-05 | 2022-03-05 | Joseph | Automated Moderating
Automated Moderting Class diagrams | 70 | Joseph | 2 | 10 | Todo | 2022-03-05 | 2022-03-05 | Joseph | Automated Moderating
Automated Moderting Database diagrams | 71 | Joseph | 1 | 10 | Todo | 2022-03-05 | 2022-03-05 | Joseph | Automated Moderating
Automated Moderting Tests | 72 | Joseph | 4 | 10 | Todo | 2022-03-05 | 2022-03-05 | Joseph | Automated Moderating
Automated Moderting Backend implementation | 73 | Joseph | 4 | 10 | Todo | 2022-03-05 | 2022-03-05 | Joseph | Automated Moderating
Automated Moderting Frontend Implementation | 74 | Joseph | 4 | 10 | Todo | 2022-03-05 | 2022-03-05 | Joseph | Automated Moderating
Schedule of Classes Behavior Diagrams | 75 | Michael | 5 | 10 | Todo | 2022-03-05 | 2022-03-05 | Michael | Schedule of Classes
Schedule of Classes Class diagrams | 76 | Michael | 2 | 10 | Todo | 2022-03-05 | 2022-03-05 | Michael | Schedule of Classes
Schedule of Classes Database diagrams | 77 | Michael | 1 | 10 | Todo | 2022-03-05 | 2022-03-05 | Michael | Schedule of Classes
Schedule of Classes Tests | 78 | Michael | 4 | 10 | Todo | 2022-03-05 | 2022-03-05 | Michael | Schedule of Classes
Schedule of Classes Backend implementation | 79 | Michael | 6 | 10 | Todo | 2022-03-05 | 2022-03-05 | Michael | Schedule of Classes
Schedule of Classes Frontend Implementation | 80 | Michael | 4 | 10 | Todo | 2022-03-05 | 2022-03-05 | Michael | Schedule of Classes
11
11
12
12
13
13
Introduction | Done | Audrey | 1 | 0 | Done | 2021-09-06 | 2021-09-06 | Audrey | Project Proposal
Needs and Problems | Done | Michael | 2 | 0 | Done | 2021-09-06 | 2021-09-06 | Audrey | Project Proposal
Goals and Objective | Done | Joseph | 1 | 0 | Done | 2021-09-06 | 2021-09-06 | Audrey | Project Proposal
Feature: Schedule Builder | Done | Brad | 3 | 0 | Done | 2021-09-06 | 2021-09-06 | Audrey | Project Proposal
Feature: Schedule Comparison | Done | Brad | 3 | 0 | Done | 2021-09-06 | 2021-09-06 | Audrey | Project Proposal
Feature: Course Difficulty | Done | Michael | 3 | 0 | Done | 2021-09-06 | 2021-09-06 | Audrey | Project Proposal
Feature: Matching | Done | Audrey | 3 | 0 | Done | 2021-09-06 | 2021-09-06 | Audrey | Project Proposal
Feture: Student Discounts | Done | Albert | 3 | 0 | Done | 2021-09-06 | 2021-09-06 | Audrey | Project Proposal
Feature: Aid | Done | Joseph | 3 | 0 | Done | 2021-09-06 | 2021-09-06 | Audrey | Project Proposal
Feature: Career Opps | Done | Albert | 3 | 0 | Done | 2021-09-06 | 2021-09-06 | Audrey | Project Proposal
Feature: Schedule of Classes | Done | Michael | 3 | 0 | Done | 2021-09-06 | 2021-09-06 | Audrey | Project Proposal
Feature: Messaging | Done | Brad | 3 | 0 | Done | 2021-09-06 | 2021-09-06 | Audrey | Project Proposal
Obstacles and Solutions | Done | Albert | 2 | 0 | Done | 2021-09-06 | 2021-09-06 | Audrey | Project Proposal
Executive Summary | Done | Joseph | 0.5 | 1 | Done | 2021-10-06 | 2021-10-06 | Albert | BRD
Project Description | Done | Joseph | 0.5 | 1 | Done | 2021-10-06 | 2021-10-06 | Albert | BRD
In Scope | Done | Audrey | 1 | 1 | Done | 2021-10-06 | 2021-10-06 | Albert | BRD
Out of Scope | Done | Michael | 1 | 1 | Done | 2021-10-06 | 2021-10-06 | Albert | BRD
Process - Builder | Done | Brad | 2 | 1 | Done | 2021-10-06 | 2021-10-06 | Albert | BRD
Process - Course Difficulty | Done | Michael | 2 | 1 | Done | 2021-10-06 | 2021-10-06 | Albert | BRD
Process - Matching | Done | Audrey | 2 | 1 | Done | 2021-10-06 | 2021-10-06 | Albert | BRD
Process - Career Opportuinty | Done | Albert | 2 | 1 | Done | 2021-10-06 | 2021-10-06 | Albert | BRD
Process - Aid | Done | Joseph | 2 | 1 | Done | 2021-10-06 | 2021-10-06 | Albert | BRD
Process - Student Discount | Done | Albert | 2 | 1 | Done | 2021-10-06 | 2021-10-06 | Albert | BRD
Process - Comparison | Done | Brad | 2 | 1 | Done | 2021-10-06 | 2021-10-06 | Albert | BRD
Requirements - Builder | Done | Brad | 2 | 1 | Done | 2021-10-06 | 2021-10-06 | Albert | BRD
Requirements - Course Difficulty | Done | Michael | 2 | 1 | Done | 2021-10-06 | 2021-10-06 | Albert | BRD
Requirements - Matching | Done | Audrey | 2 | 1 | Done | 2021-10-06 | 2021-10-06 | Albert | BRD
Requirements - Career Opportuinty | Done | Albert | 2 | 1 | Done | 2021-10-06 | 2021-10-06 | Albert | BRD
Requirements - Aid | Done | Joseph | 2 | 1 | Done | 2021-10-06 | 2021-10-06 | Albert | BRD
Requirements - Student Discount | Done | Albert | 2 | 1 | Done | 2021-10-06 | 2021-10-06 | Albert | BRD
Requirements - Comparison | Done | Brad | 2 | 1 | Done | 2021-10-06 | 2021-10-06 | Albert | BRD
Reuquirements - Messaging | Done | Brad | 2 | 1 | Done | 2021-10-06 | 2021-10-06 | Albert | BRD
Requirements - Schedule of Classes | Done | Michael | 2 | 1 | Done | 2021-10-06 | 2021-10-06 | Albert | BRD
Requirements - Core | Done | Michael | 1 | 1 | Done | 2021-10-06 | 2021-10-06 | Albert | BRD
Glossary | Done | Audrey | 0.5 | 1 | Done | 2021-10-06 | 2021-10-06 | Albert | BRD
Document History | Done | Audrey | 0.5 | 1 | Done | 2021-10-06 | 2021-10-06 | Albert | BRD
Error Handling | Done | Audrey | 4 | 1 | Done | 2021-10-06 | 2021-10-06 | Audrey | Site Map
View - Builder | Done | Brad | 0.5 | 1 | Done | 2021-10-06 | 2021-10-06 | Audrey | Site Map
View Comparison | Done | Brad | 0.5 | 1 | Done | 2021-10-06 | 2021-10-06 | Audrey | Site Map
View - Course Difficulty | Done | Michael | 0.5 | 1 | Done | 2021-10-06 | 2021-10-06 | Audrey | Site Map
View - Matching | Done | Audrey | 0.5 | 1 | Done | 2021-10-06 | 2021-10-06 | Audrey | Site Map
View - Student Discount | Done | Albert | 0.5 | 1 | Done | 2021-10-06 | 2021-10-06 | Audrey | Site Map
View - Aid | Done | Joseph | 0.5 | 1 | Done | 2021-10-06 | 2021-10-06 | Audrey | Site Map
View - Career Opportunity | Done | Albert | 0.5 | 1 | Done | 2021-10-06 | 2021-10-06 | Audrey | Site Map
View - Schedule of Classes | Done | Michael | 0.5 | 1 | Done | 2021-10-06 | 2021-10-06 | Audrey | Site Map
View - Messaging | Done | Brad | 0.5 | 1 | Done | 2021-10-06 | 2021-10-06 | Audrey | Site Map
Software | Done | Brad | 3 | 1 | Done | 2021-10-06 | 2021-10-06 | Brad | HL Design
Hardware | Done | Brad | 3 | 1 | Done | 2021-10-06 | 2021-10-06 | Brad | HL Design
Choose Software and Hardware | Done | Brad | 1 | 1 | Done | 2021-10-06 | 2021-10-06 | Brad | HL Design
OS Requirements | Done | Albert | 1 | 1 | Done | 2021-10-06 | 2021-10-06 | Michael | Tech Spec
Project Requirements | Done | Audrey | 1.5 | 1 | Done | 2021-10-06 | 2021-10-06 | Michael | Tech Spec
Product Requirements | Done | Michael | 1.5 | 1 | Done | 2021-10-06 | 2021-10-06 | Michael | Tech Spec
Phone calls: career center | Done | Joseph | 1 | 2 | Done | 2021-10-18 |  | Joseph
Phone calls: financial aid | Done | Joseph | 1 | 2 | Done | 2021-10-18 |  | Joseph
Phone calls: David Brown (schedule of classes) | Done | Joseph | 1 | 2 | Done | 2021-10-18 |  | Joseph
Test cases: Schedule Building | Done | Brad | 3 | 2 | Done | 2021-10-18 | 2021-10-27 | Joseph | Test Plan
Test cases: Discounts | Done | Albert | 3 | 2 | Done | 2021-10-18 | 2021-10-27 | Joseph | Test Plan
Test cases: Matching | Done | Audrey | 3 | 2 | Done | 2021-10-18 | 2021-10-27 | Joseph | Test Plan
Test cases: Aid | Done | Joseph | 3 | 2 | Done | 2021-10-18 | 2021-10-27 | Joseph | Test Plan
Test cases: Course Difficulty | Done | Michael | 3 | 2 | Done | 2021-10-18 | 2021-10-27 | Joseph | Test Plan
Test cases: Careers | Done | Albert | 3 | 2 | Done | 2021-10-18 | 2021-10-27 | Joseph | Test Plan
Test cases: Schedule of Classes | Done | Brad | 3 | 2 | Done | 2021-10-18 | 2021-10-27 | Joseph | Test Plan
Test cases: Messaging | Done | Audrey | 3 | 2 | Done | 2021-10-18 | 2021-10-27 | Joseph | Test Plan
Test cases: Registration | Done | Michael | 1 | 2 | Done | 2021-10-18 | 2021-10-27 | Joseph | Test Plan
Test cases: Login | Done | Michael | 1 | 2 | Done | 2021-10-18 | 2021-10-27 | Joseph | Test Plan
Test cases: Logout | Done | Michael | 1 | 2 | Done | 2021-10-18 | 2021-10-27 | Joseph | Test Plan
Information gathering: aid, careers, schedule of classes | Done | Joseph | 4 | 3 | Done | 2021-10-26 | 2021-10-27 | Albert | Network Diagram
Network Diagram: Choose server provider | Done | Brad | 4 | 3 | Done | 2021-10-26 | 2021-10-27 | Albert | Network Diagram
Test case data: student discounts, careers | Done | Albert | 2 | 3 | Done | 2021-10-26 | 2021-10-27 | Michael | Test Plan
Test case data: matching, messaging | Done | Audrey | 2 | 3 | Done | 2021-10-26 | 2021-10-27 | Michael | Test Plan
Test case data: schedules, classes | Done | Brad | 2 | 3 | Done | 2021-10-26 | 2021-10-27 | Michael | Test Plan
Test case data: aid | Done | Joseph | 2 | 3 | Done | 2021-10-26 | 2021-10-27 | Michael | Test Plan
Test case data: course rating, registration, login, logout | Done | Michael | 2 | 3 | Done | 2021-10-26 | 2021-10-27 | Michael | Test Plan
Network Diagram: Node system specs | Done | Joseph | 2 | 3 | Done | 2021-10-26 | 2021-10-27 | Albert | Network Diagram
Network Diagram: IPs/URLs of external servers | Done | Albert | 4 | 3 | Done | 2021-10-26 | 2021-10-27 | Albert | Network Diagram
Network Diagram: Requests | Done | Audrey | 4 | 3 | Done | 2021-10-26 | 2021-10-27 | Albert | Network Diagram
Network Diagram: Responses | Done | Michael | 4 | 3 | Done | 2021-10-26 | 2021-10-27 | Albert | Network Diagram
Network Diagram: 3rd party services & servers | Done | Albert | 4 | 3 | Done | 2021-10-26 | 2021-10-27 | Albert | Network Diagram
Determine feature development order | Done | Brad | 4 | 3 | Done | 2021-10-26 | 2021-10-27 | Brad | Project Plan
Determine critical path tasks | Done | Audrey | 4 | 3 | Done | 2021-10-26 | 2021-10-27 | Brad | Project Plan
Plan deployment process | Done | Michael | 4 | 3 | Done | 2021-10-26 | 2021-10-27 | Brad | Project Plan
Risk Identification | Done | Brad | 3 | 3 | Done | 2021-10-26 | 2021-10-27 | Brad | Project Plan
Risk Mitigation | Done | Michael | 2 | 3 | Done | 2021-10-26 | 2021-10-27 | Brad | Project Plan
Schedule Project Milestones | Done | Joseph | 2 | 3 | Done | 2021-10-26 | 2021-10-27 | Brad | Project Plan
Schedule Sprints | Done | Albert | 2 | 3 | Done | 2021-10-26 | 2021-10-27 | Brad | Project Plan
Validate schedule with team | Done | Brad | 1 | 3 | Done | 2021-10-26 | 2021-10-27 | Brad | Project Plan
Generate Roadmap from schedule | Done | Albert | 2 | 3 | Done | 2021-10-26 | 2021-10-27 | Brad | Project Plan
Test plan: testing schedule | Done | Audrey | 4 | 3 | Done | 2021-10-26 | 2021-10-27 | Michael | Test Plan
Detail testing environment | Done | Michael | 4 | 3 | Done | 2021-10-26 | 2021-10-27 | Michael | Test Plan
Progression and Regression Testing details | Done | Joseph | 4 | 3 | Done | 2021-10-26 | 2021-10-27 | Michael | Test Plan
UM Business Requirements | 1 | Joseph | 3 | 4 | Done | 2021-11-12 | 2021-12-08 | Audrey | BRD
Logging Business Requirements | 2 | Brad | 3 | 4 | Done | 2021-11-12 | 2021-12-08 | Audrey | BRD
UM Site Map | 3 | Joseph | 1 | 4 | Done | 2021-11-12 | 2021-12-08 | Audrey | Site Map
UM test plan | 4 | Audrey | 4 | 4 | Done | 2021-11-12 | 2021-12-08 | Audrey | Test Plan
Logging test plan | 5 | Albert | 3.5 | 4 | Done | 2021-11-12 | 2021-12-08 | Audrey | Test Plan
UM class diagram (UML) | 6 | Joseph | 1 | 4 | Done | 2021-11-12 | 2021-12-08 | Audrey | LL Design
Logging class diagram | 7 | Brad | 1 | 4 | Done | 2021-11-12 | 2021-12-08 | Audrey | LL Design
UM sequence diagram | 8 | Audrey | 3 | 4 | Done | 2021-11-12 | 2021-12-08 | Audrey | LL Design
Logging behavioral diagram | 9 | Michael | 5 | 4 | Done | 2021-11-12 | 2021-12-08 | Audrey | LL Design
UM interfaces to other components | 10 | Albert | 0 | 4 | Done | 2021-11-12 | 2021-12-08 | Audrey | LL Design
Logging interfaces to other components | 11 | Brad | 1 | 4 | Done | 2021-11-12 | 2021-12-08 | Audrey | LL Design
UM Feature Pseudocode | 12 | Albert | 0 | 4 | Done | 2021-11-12 | 2021-12-08 | Audrey | LL Design
Logging Feature Pseudocode | 13 | Michael | 0 | 4 | Done | 2021-11-12 | 2021-12-08 | Audrey | LL Design
Compile UM LL Design Document | 14 | Audrey | 0 | 4 | Done | 2021-11-12 | 2021-12-08 | Audrey | LL Design
Compile Logging LL Design Document | 15 | Michael | 0 | 4 | Done | 2021-11-12 | 2021-12-08 | Audrey | LL Design
UM Business Requirements | 1 | Joseph | 1 | 5 | Done | 2021-11-24 | 2021-12-08 | Audrey | BRD
Logging Business Requirements | 2 | Brad | 1 | 5 | Done | 2021-11-24 | 2021-12-08 | Audrey | BRD
UM Site Map | 3 | Joseph | 2 | 5 | Done | 2021-11-24 | 2021-12-08 | Audrey | Site Map
Logging test plan | 4 | Albert | 0.5 | 5 | Done | 2021-11-24 | 2021-12-08 | Audrey | Test Plan
UM class diagram (UML) | 5 | Joseph | 8 | 5 | Done | 2021-11-24 | 2021-12-08 | Audrey | LL Design
Logging class diagram | 6 | Brad | 7 | 5 | Done | 2021-11-24 | 2021-12-08 | Audrey | LL Design
UM sequence diagram | 7 | Audrey | 5 | 5 | Done | 2021-11-24 | 2021-12-08 | Audrey | LL Design
Logging behavioral diagram | 8 | Michael | 3 | 5 | Done | 2021-11-24 | 2021-12-08 | Audrey | LL Design
UM interfaces to other components | 9 | Albert | 2 | 5 | Done | 2021-11-24 | 2021-12-08 | Audrey | LL Design
Logging interfaces to other components | 10 | Brad | 1 | 5 | Done | 2021-11-24 | 2021-12-08 | Audrey | LL Design
UM Feature Pseudocode | 11 | Albert | 6 | 5 | Done | 2021-11-24 | 2021-12-08 | Audrey | LL Design
Logging Feature Pseudocode | 12 | Michael | 6 | 5 | Done | 2021-11-24 | 2021-12-08 | Audrey | LL Design
Compile UM LL Design Document | 13 | Audrey | 2 | 5 | Done | 2021-11-24 | 2021-12-08 | Audrey | LL Design
Compile Logging LL Design Document | 14 | Michael | 2 | 5 | Done | 2021-11-24 | 2021-12-08 | Audrey | LL Design
Update BRD (feedback) | 15 | Joseph | 2 | 5 | Done | 2021-11-24 | 2021-12-08 | Michael | BRD
Update HL Design (feedback) | 16 | Brad | 2 | 5 | Done | 2021-11-24 | 2021-12-08 | Michael | HL Design
Update Network Diagram (feedback) | 17 | Albert | 2 | 5 | Done | 2021-11-24 | 2021-12-08 | Michael | Network Diagram
Update Project Plan (feedback) | 18 | Brad | 2 | 5 | Done | 2021-11-24 | 2021-12-08 | Michael | Project Plan
Update Site Map (feedback) | 19 | Audrey | 2 | 5 | Done | 2021-11-24 | 2021-12-08 | Michael | Site Map
Update Tech Spec (feedback) | 20 | Audrey | 2 | 5 | Done | 2021-11-24 | 2021-12-08 | Michael | Tech Spec
Update Test Plan (feedback) | 21 | Michael | 2 | 5 | Done | 2021-11-24 | 2021-12-08 | Michael | Test Plan
Archiving (BRD) | 22 | Michael | 2 | 5 | Done | 2021-11-24 | 2021-12-08 | Michael | Core Requirements
Archiving (Sitemap) | 23 | Michael | 2 | 5 | Done | 2021-11-24 | 2021-12-08 | Michael | Core Requirements
Archiving (Test Plan) | 24 | Michael | 2 | 5 | Done | 2021-11-24 | 2021-12-08 | Michael | Core Requirements
Error Handling (BRD) | 25 | Albert | 2 | 5 | Done | 2021-11-24 | 2021-12-08 | Michael | BRD
Error Handling (Sitemap) | 26 | Albert | 2 | 5 | Done | 2021-11-24 | 2021-12-08 | Michael | Site Map
Error Handling (Test plan) | 27 | Albert | 2 | 5 | Done | 2021-11-24 | 2021-12-08 | Michael | Test Plan
Logging (Sitemap) | 28 | Brad | 2 | 5 | Done | 2021-11-24 | 2021-12-08 | Michael | Core Requirements
Usage Analysis Dashboard (BRD) | 29 | Audrey | 2 | 5 | Done | 2021-11-24 | 2021-12-08 | Michael | Core Requirements
Usage Analysis Dashboard (Sitemap) | 30 | Brad | 2 | 5 | Done | 2021-11-24 | 2021-12-08 | Michael | Core Requirements
Usage Analysis Dashboard (Test Plan) | 31 | Audrey | 2 | 5 | Done | 2021-11-24 | 2021-12-08 | Michael | Core Requirements
User Access Control (BRD) | 32 | Joseph | 2 | 5 | Done | 2021-11-24 | 2021-12-08 | Michael | Core Requirements
User Access Control (Sitemap) | 33 | Joseph | 2 | 5 | Done | 2021-11-24 | 2021-12-08 | Michael | Core Requirements
User Access Control (Test Plan) | 34 | Joseph | 2 | 5 | Done | 2021-11-24 | 2021-12-08 | Michael | Core Requirements
User Management (Sitemap) | 35 | Audrey | 2 | 5 | Done | 2021-11-24 | 2021-12-08 | Michael | Core Requirements
Login (BRD) | 36 | Audrey | 1 | 5 | Done | 2021-11-24 | 2021-12-08 | Michael | Core Requirements
Login (Test Plan) | 37 | Audrey | 1 | 5 | Done | 2021-11-24 | 2021-12-08 | Michael | Core Requirements
Logout (BRD) | 38 | Brad | 1 | 5 | Done | 2021-11-24 | 2021-12-08 | Michael | Core Requirements
Logout (Test Plan) | 39 | Brad | 1 | 5 | Done | 2021-11-24 | 2021-12-08 | Michael | Core Requirements
Registration (BRD) | 40 | Albert | 1 | 5 | Done | 2021-11-24 | 2021-12-08 | Michael | Core Requirements
Registration (Test Plan) | 41 | Albert | 1 | 5 | Done | 2021-11-24 | 2021-12-08 | Michael | Core Requirements
UM Business Requirements | 1 | Joseph | 1 | 6 | Done | 2021-12-14 | 2021-12-15 | Audrey | BRD
Logging class diagram | 2 | Brad | 3.5 | 6 | Done | 2021-12-14 | 2021-12-15 | Audrey | LL Design
UM sequence diagram | 3 | Audrey | 4 | 6 | Done | 2021-12-14 | 2021-12-15 | Audrey | LL Design | 7 |  |  | UM
Tech approval: unit testing | 4 | Michael | 4 | 6 | Done | 2021-12-14 | 2021-12-15 | Audrey | LL Design | 7 | Albert | 20.5 | UM
Logging behavioral diagram | 5 | Michael | 1 | 6 | Done | 2021-12-14 | 2021-12-15 | Audrey | LL Design | 5 | Audrey | 35 | Logging
UM interfaces to other components | 6 | Albert | 2 | 6 | Done | 2021-12-14 | 2021-12-15 | Audrey | LL Design | 9 | Brad | 41.25 | UM
Logging interfaces to other components | 7 | Brad | 0.5 | 6 | Done | 2021-12-14 | 2021-12-15 | Audrey | LL Design | 10 | Joseph | 23.5 | Logging
UM Feature Pseudocode | 8 | Albert | 2 | 6 | Done | 2021-12-14 | 2021-12-15 | Audrey | LL Design | 590 | Michael | 23
Logging Feature Pseudocode | 9 | Michael | 2 | 6 | Done | 2021-12-14 | 2021-12-15 | Audrey | LL Design | 38 | Actual Total | 143.25
BRD: Authorize | 10 | Audrey | 1 | 6 | Done | 2021-12-14 | 2021-12-15 | Michael | Core Requirements |  |  |  | 43.75
Test: Authorize | 11 | Audrey | 1 | 6 | Done | 2021-12-14 | 2021-12-15 | Michael | Core Requirements |  | Expected Total | 218.75
Site Map: Authorize | 12 | Audrey | 1 | 6 | Done | 2021-12-14 | 2021-12-15 | Michael | Core Requirements
BRD: Account Deletion | 13 | Joseph | 1 | 6 | Done | 2021-12-14 | 2021-12-15 | Michael | Core Requirements
Test Cases: Account Deletion | 14 | Joseph | 1 | 6 | Done | 2021-12-14 | 2021-12-15 | Michael | Core Requirements
Tech approval: ORM | 15 | Joseph | 4 | 6 | Done | 2021-12-14 | 2021-12-15 | Audrey | LL Design
Tech Approval: Cron | 16 | Brad | 4 | 6 | Done | 2021-12-14 | 2021-12-15 | Audrey | LL Design
Implementation: Authorization | 17 | Albert | 2 | 6 | Done | 2021-12-14 | 2021-12-15 | Michael | Core Requirements
Implementation: Authenication | 18 | Audrey | 2 | 6 | Done | 2021-12-14 | 2021-12-15 | Michael | Core Requirements
UM Implementation: Model class: User Account | 19 | Audrey | 1 | 6 | Done | 2021-12-14 | 2021-12-15 | Audrey | UM
UM Implementation: Create accounts | 20 | Joseph | 1 | 6 | Done | 2021-12-14 | 2021-12-15 | Audrey | UM
UM Implementation: Update accounts | 21 | Albert | 1 | 6 | Done | 2021-12-14 | 2021-12-15 | Audrey | UM
UM Implementation: Delete accounts | 22 | Audrey | 1 | 6 | Done | 2021-12-14 | 2021-12-15 | Audrey | UM
UM Implementation: Enable and disable accounts | 23 | Joseph | 1 | 6 | Done | 2021-12-14 | 2021-12-15 | Audrey | UM
UM Implementation: Execute bulk operations | 24 | Albert | 4 | 6 | Done | 2021-12-14 | 2021-12-15 | Audrey | UM
Logging Implementation: Model class: Log | 25 | Brad | 1 | 6 | Done | 2021-12-14 | 2021-12-15 | Brad | Logging
Logging Implementation | 26 | Brad | 8 | 6 | Done | 2021-12-14 | 2021-12-15 | Brad | Logging
Archiving Implementation | 27 | Michael | 4 | 6 | Done | 2021-12-14 | 2021-12-15 | Brad | Logging
Tests: Authorization | 28 | Albert | 2 | 6 | Done | 2021-12-14 | 2021-12-15 | Michael | Core Requirements
Tests: Authentication | 29 | Audrey | 2 | 6 | Done | 2021-12-14 | 2021-12-15 | Michael | Core Requirements
UM Tests: Create | 30 | Joseph | 2 | 6 | Done | 2021-12-14 | 2021-12-15 | Audrey | UM
UM Tests: Update | 31 | Albert | 2 | 6 | Done | 2021-12-14 | 2021-12-15 | Audrey | UM
UM Tests: Delete | 32 | Audrey | 2 | 6 | Done | 2021-12-14 | 2021-12-15 | Audrey | UM
UM Tests: Enable/disable | 33 | Joseph | 2 | 6 | Done | 2021-12-14 | 2021-12-15 | Audrey | UM
UM Tests: Execute bulk operations | 34 | Albert | 2 | 6 | Done | 2021-12-14 | 2021-12-15 | Audrey | UM
Logging Tests | 35 | Michael | 4 | 6 | Done | 2021-12-14 | 2021-12-15 | Brad | Logging
Archiving Tests | 36 | Brad | 2 | 6 | Done | 2021-12-14 | 2021-12-15 | Brad | Logging
Update BRD (feedback) | 37 | Joseph | 2 | 6 | Done | 2021-12-14 | 2021-12-15 | Michael | BRD
Update Test Plan (feedback) | 38 | Michael | 2 | 6 | Done | 2021-12-14 | 2021-12-15 | Michael | Test Plan
Archiving (BRD) | 39 | Michael | 1 | 6 | Done | 2021-12-14 | 2021-12-15 | Michael | Core Requirements
Archiving (Test Plan) | 40 | Michael | 1 | 6 | Done | 2021-12-14 | 2021-12-15 | Michael | Core Requirements
User Access Control (BRD) | 41 | Audrey | 2 | 6 | Done | 2021-12-14 | 2021-12-15 | Michael | Core Requirements
User Access Control (Sitemap) | 42 | Joseph | 1.5 | 6 | Done | 2021-12-14 | 2021-12-15 | Michael | Core Requirements
User Access Control (Test Plan) | 43 | Joseph | 1.5 | 6 | Done | 2021-12-14 | 2021-12-15 | Michael | Core Requirements
Registration (BRD) | 44 | Albert | 1 | 6 | Done | 2021-12-14 | 2021-12-15 | Michael | Core Requirements
Registration (Test Plan) | 45 | Albert | 1 | 6 | Done | 2021-12-14 | 2021-12-15 | Michael | Core Requirements
Compile UM LL Design Document | 46 | Audrey | 2 | 6 | Done | 2021-12-14 | 2021-12-15 | Audrey | LL Design
Compile Logging LL Design Document | 47 | Michael | 2 | 6 | Done | 2021-12-14 | 2021-12-15 | Audrey | LL Design
Review BRD, Tech Spec | 48 | Albert | 1 | 6 | Done | 2021-12-14 | 2021-12-15 | Michael | Core Requirements
Review LL Design Logging, Project Plan | 49 | Audrey | 1 | 6 | Done | 2021-12-14 | 2021-12-15 | Michael | Core Requirements
Review LL Design UM, Network Diagram | 50 | Brad | 1 | 6 | Done | 2021-12-14 | 2021-12-15 | Michael | Core Requirements
Review Test Plan | 51 | Joseph | 1 | 6 | Done | 2021-12-14 | 2021-12-15 | Michael | Core Requirements
Review Site Map, HL Design | 52 | Michael | 1 | 6 | Done | 2021-12-14 | 2021-12-15 | Michael | Core Requirements
Address git repo: clean up files | 1 | Brad | 2 | 7 | Done | 2022-01-22 | 2022-01-22 | Michael | Feedback
Address test parity (tests should pass when desired result happens) | 2 | Michael | 6 | 7 | Done | 2022-01-22 | 2022-01-22 | Michael | Feedback
Tech Approval: HTML | 3 | Michael | 6 | 7 | Done | 2022-01-22 | 2022-01-22 | Michael | Tech Spec
Tech Approval: CSS | 4 | Michael | 6 | 7 | Done | 2022-01-22 | 2022-01-22 | Michael | Tech Spec
Registration Behavioral Diagram | 5 | Albert | 12 | 7 | Done | 2022-01-22 | 2022-01-22 | Albert | Registration
Registration Class Diagram | 6 | Albert | 8 | 7 | Done | 2022-01-22 | 2022-01-22 | Albert | Registration
Login Behavioral Diagram | 7 | Audrey | 12 | 7 | Done | 2022-01-22 | 2022-01-22 | Audrey | Login
Login Class Diagram | 8 | Audrey | 8 | 7 | Done | 2022-01-22 | 2022-01-22 | Audrey | Login
Logout Behavior Diagram | 9 | Brad | 12 | 7 | Done | 2022-01-22 | 2022-01-22 | Brad | Logout
Logout Class Diagram | 10 | Michael | 8 | 7 | Done | 2022-01-22 | 2022-01-22 | Brad | Logout
Error Handling Behavior Diagram | 11 | Joseph | 12 | 7 | Done | 2022-01-22 | 2022-01-22 | Joseph | Error Handling
Error Handling Class Diagram | 12 | Joseph | 8 | 7 | Done | 2022-01-22 | 2022-01-22 | Joseph | Error Handling
Registration backend implementation | 13 | Albert | 4 | 7 | Done | 2022-01-22 | 2022-01-22 | Albert | Registration
Registration frontend implementation | 14 | Albert | 4 | 7 | Done | 2022-01-22 | 2022-01-22 | Albert | Registration
Login backend implementation | 15 | Audrey | 4 | 7 | Done | 2022-01-22 | 2022-01-22 | Audrey | Login
Login frontend implementation | 16 | Audrey | 4 | 7 | Done | 2022-01-22 | 2022-01-22 | Audrey | Login
Logout backend implementation | 17 | Brad | 4 | 7 | Done | 2022-01-22 | 2022-01-22 | Brad | Logout
Logout frontend implementation | 18 | Brad | 4 | 7 | Done | 2022-01-22 | 2022-01-22 | Brad | Logout
Error Handling backend implementation | 19 | Joseph | 4 | 7 | Done | 2022-01-22 | 2022-01-22 | Joseph | Error Handling
Error Handling frontend implementation | 20 | Joseph | 4 | 7 | Done | 2022-01-22 | 2022-01-22 | Joseph | Error Handling
Registration Testing | 21 | Albert | 4 | 7 | Done | 2022-01-22 | 2022-01-22 | Albert | Registration
Login Testing | 22 | Audrey | 4 | 7 | Done | 2022-01-22 | 2022-01-22 | Audrey | Login
Logout Testing | 23 | Brad | 4 | 7 | Done | 2022-01-22 | 2022-01-22 | Brad | Logout
Error Handling Testing | 24 | Joseph | 4 | 7 | Done | 2022-01-22 | 2022-01-22 | Joseph | Error Handling
Code Review Assignments (Meeting) | 25 | None | 0 | 7 | Done | 2022-01-17 | 2022-01-17 | None | N/A
New Feature for Jacob | 1 | Jacob | 1 | 8 | Done | 2022-02-05 | 2022-02-05 | Albert | BRD
New Feature for Devarsh | 2 | Devarsh | 1 | 8 | Done | 2022-02-05 | 2022-02-05 | Albert | BRD
New Feature for SzeMan | 3 | SzeMan | 1 | 8 | Done | 2022-02-05 | 2022-02-05 | Albert | BRD
New Feature for Joseph | 4 | Joseph | 1 | 8 | Done | 2022-02-05 | 2022-02-05 | Albert | BRD
BRD for GPA Calc | 5 | Jacob | 2 | 8 | Done | 2022-02-05 | 2022-02-05 | Albert | BRD
BRD for Book Selling | 6 | Jacob | 2 | 8 | Done | 2022-02-05 | 2022-02-05 | Albert | BRD
BRD for Automated Testing | 7 | Joseph | 2 | 8 | Done | 2022-02-05 | 2022-02-05 | Albert | BRD
BRD for Event Planning | 8 | SzeMan | 2 | 8 | Done | 2022-02-05 | 2022-02-05 | Albert | BRD
BRD for Recipe Sharing | 9 | Devarsh | 2 | 8 | Done | 2022-02-05 | 2022-02-05 | Albert | BRD
Update Project Plan | 10 | Brad | 2 | 8 | Done | 2022-02-05 | 2022-02-05 | Brad | Project Plan
Update project plan to account for code reviews | 11 | Brad | 1 | 8 | Done | 2022-01-29 | 2022-01-29 | Brad | Project Plan | 94
Address test parity (tests should pass when desired result happens) | 12 | Michael | 6 | 8 | Done | 2022-02-05 | 2022-02-05 | Michael | Feedback | 94 | Albert | 15
Tech Approval: HTML | 13 | Michael | 4 | 8 | Done | 2022-02-05 | 2022-02-05 | Michael | Tech Spec | 94 | Audrey | 11
Tech Approval: Jobs API | 14 | Albert | 6 | 8 | Done | 2022-02-05 | 2022-02-05 | Michael | Tech Spec |  | Brad | 29
Tech Approval: CSS | 15 | Michael | 4 | 8 | Done | 2022-02-05 | 2022-02-05 | Michael | Tech Spec | 94
Registration Behavioral Diagram | 16 | Albert | 2 | 8 | Done | 2022-02-05 | 2022-02-05 | Albert | Registration | 94 | Joseph | 17
Registration Class Diagram | 17 | Albert | 6 | 8 | Done | 2022-02-05 | 2022-02-05 | Albert | Registration | #REF! | Michael | 22
Login Behavioral Diagram | 18 | Audrey | 1 | 8 | Done | 2022-02-05 | 2022-02-05 | Audrey | Login | 470 | Actual Total | 94
Login Class Diagram | 19 | Audrey | 1 | 8 | Done | 2022-02-05 | 2022-02-05 | Audrey | Login |  |  |  | 18.8
Logout Behavior Diagram | 20 | Brad | 11 | 8 | Done | 2022-02-05 | 2022-02-05 | Brad | Logout |  | Expected Total | 94
Logout Class Diagram | 21 | Michael | 8 | 8 | Done | 2022-02-05 | 2022-02-05 | Brad | Logout
Error Handling Behavior Diagram | 22 | Joseph | 8 | 8 | Done | 2022-02-05 | 2022-02-05 | Joseph | Error Handling |  | 120
Error Handling Class Diagram | 23 | Joseph | 4 | 8 | Done | 2022-02-05 | 2022-02-05 | Joseph | Error Handling
Registration backend implementation | 24 | Brad | 4 | 8 | Done | 2022-02-05 | 2022-02-05 | Albert | Registration
Registration frontend implementation | 25 | Brad | 4 | 8 | Done | 2022-02-05 | 2022-02-05 | Albert | Registration
Login backend implementation | 26 | Audrey | 4 | 8 | Done | 2022-02-05 | 2022-02-05 | Audrey | Login
Login frontend implementation | 27 | Audrey | 4 | 8 | Done | 2022-02-05 | 2022-02-05 | Audrey | Login
Logout backend implementation | 28 | Brad | 4 | 8 | Done | 2022-02-05 | 2022-02-05 | Brad | Logout
Logout frontend implementation | 29 | Brad | 4 | 8 | Done | 2022-02-05 | 2022-02-05 | Brad | Logout
Error Handling backend implementation | 30 | Joseph | 3 | 8 | Done | 2022-02-05 | 2022-02-05 | Joseph | Error Handling
Error Handling frontend implementation | 31 | Joseph | 1 | 8 | Done | 2022-02-05 | 2022-02-05 | Joseph | Error Handling
Registration Testing | 32 | Albert | 1 | 8 | Done | 2022-02-05 | 2022-02-05 | Albert | Registration
Login Testing | 33 | Audrey | 1 | 8 | Done | 2022-02-05 | 2022-02-05 | Audrey | Login
Logout Testing | 34 | Brad | 1 | 8 | Done | 2022-02-05 | 2022-02-05 | Brad | Logout
Error Handling Testing | 35 | Joseph | 1 | 8 | Done | 2022-02-05 | 2022-02-05 | Joseph | Error Handling
Copy home page & example from original site map to second page | 1 | Brad | 0.25 | 9 | Done | 2022-02-19 | 2022-02-19 | Audrey | Site map
Recipe Sharing Site Map | 2 | Devarsh | 1 | 9 | Done | 2022-02-19 | 2022-02-19 | Devarsh | Recipe Sharing
Book Selling Site Map | 3 | Jacob | 1 | 9 | Done | 2022-02-19 | 2022-02-19 | Jacob | Book Selling |  | Member | SP
Grade Calculator Site Map | 4 | Jacob | 1 | 9 | Done | 2022-02-19 | 2022-02-19 | Jacob | Grade Calculator |  | Albert | 0
Event Planning Site Map | 5 | Sze | 1 | 9 | Done | 2022-02-19 | 2022-02-19 | Sze | Event Planning |  | Audrey | 0
Review Recipe Sharing Test Plan | 6 | Devarsh | 0.25 | 9 | Done | 2022-02-19 | 2022-02-19 | Devarsh | Recipe Sharing |  | Brad | 0
Book Selling Test Plan | 7 | Jacob | 2 | 9 | Done | 2022-02-19 | 2022-02-19 | Jacob | Book Selling |  | Devarsh | 20
Grade Calculator Test Plan | 8 | Jacob | 2 | 9 | Done | 2022-02-19 | 2022-02-19 | Jacob | Grade Calculator |  | Jacob | 0
Review Event Planning Test Plan | 9 | Sze | 0.25 | 9 | Done | 2022-02-19 | 2022-02-19 | Sze | Event Planning |  | Joseph | 0
Automated Moderating Test Plan | 10 | Joseph | 0.5 | 9 | Done | 2022-02-19 | 2022-02-19 | Joseph | Automated Moderating |  | Michael | 0
Address test parity (tests should pass when desired result happens) (UM) | 11 | Audrey | 1 | 9 | Done | 2022-02-19 | 2022-02-19 | Audrey | Feedback |  | Sze | 14
Address test parity (tests should pass when desired result happens) (Archiving) | 12 | Michael | 2 | 9 | Done | 2022-02-19 | 2022-02-19 | Michael | Feedback |  | Expected total | 190.75
Address test parity (tests should pass when desired result happens) (Logging) | 13 | Brad | 2 | 9 | Done | 2022-02-19 | 2022-02-19 | Brad | Feedback |  | Actual total | 34
Tech Approval: HTML | 14 | Michael | 3 | 9 | Done | 2022-02-19 | 2022-02-19 | Michael | Tech Specs |  | Unassigned | 156.75
Tech Approval: Jobs API | 15 | Albert | 3.5 | 9 | Done | 2022-02-19 | 2022-02-19 | Michael | Tech Specs |  | Expected SP/person | 23.8438
Tech Approval: CSS | 16 | Michael | 3 | 9 | Done | 2022-02-19 | 2022-02-19 | Michael | Tech Specs
Registration Behavior Diagram | 17 | Albert | 2 | 9 | Done | 2022-02-19 | 2022-02-19 | Albert | Registration
Email verification behavior diagram | 18 | Joseph | 6 | 9 | Done | 2022-02-19 | 2022-02-19 | Albert | Registration
Registration Class Diagram | 19 | Albert | 4 | 9 | Done | 2022-02-19 | 2022-02-19 | Albert | Registration
Email verification class/database diagram | 20 | Audrey | 2 | 9 | Done | 2022-02-19 | 2022-02-19 | Albert | Registration
Authentication Tokens/authentication cookies class/database diagram | 21 | Michael | 3 | 9 | Done | 2022-02-19 | 2022-02-19 | Audrey | Authentication
Login Behavior Diagram | 22 | Audrey | 1 | 9 | Done | 2022-02-19 | 2022-02-19 | Audrey | Login
Login Class Diagram | 23 | Audrey | 1 | 9 | Done | 2022-02-19 | 2022-02-19 | Audrey | Login
Logout Behavior Diagram | 24 | Brad | 10 | 9 | Done | 2022-02-19 | 2022-02-19 | Brad | Logout
Logout Class Diagram | 25 | Michael | 8 | 9 | Done | 2022-02-19 | 2022-02-19 | Brad | Logout
Review login for error handling | 26 | Jacob | 4 | 9 | Done | 2022-02-19 | 2022-02-19 | Audrey | Login
Review registration for error handling | 27 | Jacob | 4 | 9 | Done | 2022-02-19 | 2022-02-19 | Albert | Registration
Review logout for error handling | 28 | Joseph | 4 | 9 | Done | 2022-02-19 | 2022-02-19 | Brad | Logout
User Management frontend implementation (single CRUD operations) | 29 | Jacob | 4 | 9 | Done | 2022-02-19 | 2022-02-19 | Audrey | UM
User Management frontend implementation (file upload for bulk operations) | 30 | Jacob | 4 | 9 | Done | 2022-02-19 | 2022-02-19 | Audrey | UM
User Management frontend implementation (bulk CRUD operations) | 31 | Jacob | 4 | 9 | Done | 2022-02-19 | 2022-02-19 | Audrey | UM
Registration Tests | 32 | Albert | 4 | 9 | Done | 2022-02-19 | 2022-02-19 | Albert | Registration
Email verification tests | 33 | Audrey | 4 | 9 | Done | 2022-02-19 | 2022-02-19 | Albert | Registration
Login Tests | 34 | Audrey | 3.5 | 9 | Done | 2022-02-19 | 2022-02-19 | Audrey | Login
Logout Tests | 35 | Brad | 4 | 9 | Done | 2022-02-19 | 2022-02-19 | Brad | Logout
Registration backend implementation | 36 | Joseph | 4 | 9 | Done | 2022-02-19 | 2022-02-19 | Albert | Registration
Registration frontend implementation | 37 | Albert | 6 | 9 | Done | 2022-02-19 | 2022-02-19 | Albert | Registration
Email verification backend implementation | 38 | Michael | 4 | 9 | Done | 2022-02-19 | 2022-02-19 | Albert | Registration
Email verification frontend implementation | 39 | Audrey | 4 | 9 | Done | 2022-02-19 | 2022-02-19 | Albert | Registration
Login backend implementation | 40 | Audrey | 2.5 | 9 | Done | 2022-02-19 | 2022-02-19 | Audrey | Login
Login frontend implementation | 41 | Audrey | 3 | 9 | Done | 2022-02-19 | 2022-02-19 | Audrey | Login
Logout backend implementation | 42 | Brad | 4 | 9 | Done | 2022-02-19 | 2022-02-19 | Brad | Logout
Logout frontend implementation | 43 | Brad | 4 | 9 | Done | 2022-02-19 | 2022-02-19 | Brad | Logout
Login error handling implementation | 44 | Audrey | 4 | 9 | Done | 2022-02-19 | 2022-02-19 | Audrey | Login
Logout error handling implementation | 45 | Brad | 4 | 9 | Done | 2022-02-19 | 2022-02-19 | Brad | Logout
Registration error handling implementation | 46 | Joseph | 4 | 9 | Done | 2022-02-19 | 2022-02-19 | Albert | Registration
Usage Analysis Dashboard Behavior Diagrams | 47 | Sze | 4 | 9 | Done | 2022-02-19 | 2022-02-19 | Sze | Usage Analysis Dashboard
Usage Analysis Dashboard Class/database diagram | 48 | Sze | 2 | 9 | Done | 2022-02-19 | 2022-02-19 | Sze | Usage Analysis Dashboard
Usage Analysis Dashboard Query Tests | 49 | Sze | 3 | 9 | Done | 2022-02-19 | 2022-02-19 | Sze | Usage Analysis Dashboard
Usage Analysis Dashboard Graph/chart tests? | 50 | Sze | 4 | 9 | Done | 2022-02-19 | 2022-02-19 | Sze | Usage Analysis Dashboard
Usage Analysis Dashboard Backend implementation Query AS02.1 | 51 | Sze | 1 | 9 | Done | 2022-02-19 | 2022-02-19 | Sze | Usage Analysis Dashboard
Usage Analysis Dashboard Backend implementation Query AS02.2 | 52 | Sze | 1 | 9 | Done | 2022-02-19 | 2022-02-19 | Sze | Usage Analysis Dashboard
Usage Analysis Dashboard Backend implementation Query AS02.3 | 53 | Sze | 1 | 9 | Done | 2022-02-19 | 2022-02-19 | Sze | Usage Analysis Dashboard
Usage Analysis Dashboard Backend implementation Query AS02.4 | 54 | Sze | 1 | 9 | Done | 2022-02-19 | 2022-02-19 | Sze | Usage Analysis Dashboard
Usage Analysis Dashboard Backend implementation Query AS02.5 | 55 | Sze | 1 | 9 | Done | 2022-02-19 | 2022-02-19 | Sze | Usage Analysis Dashboard
Usage Analysis Dashboard Backend implementation Query AS02.6 | 56 | Sze | 1 | 9 | Done | 2022-02-19 | 2022-02-19 | Sze | Usage Analysis Dashboard
Usage Analysis Dashboard Frontend implementation Bar graphs | 57 | Sze | 4 | 9 | Done | 2022-02-19 | 2022-02-19 | Sze | Usage Analysis Dashboard
Usage Analysis Dashboard Frontend implementation Trend charts | 58 | Sze | 4 | 9 | Done | 2022-02-19 | 2022-02-19 | Sze | Usage Analysis Dashboard
User Access Control Behavior Diagrams | 59 | Devarsh | 4 | 9 | Done | 2022-02-19 | 2022-02-19 | Devarsh | User Access Control
User Access Control Class/database diagram | 60 | Devarsh | 2 | 9 | Done | 2022-02-19 | 2022-02-19 | Devarsh | User Access Control
User Access Control Tests | 61 | Devarsh | 4 | 9 | Done | 2022-02-19 | 2022-02-19 | Devarsh | User Access Control
User Access Control Backend implementation | 62 | Devarsh | 6 | 9 | Done | 2022-02-19 | 2022-02-19 | Devarsh | User Access Control
User Access Control Frontend implementation for access denial message | 63 | Devarsh | 2 | 9 | Done | 2022-02-19 | 2022-02-19 | Devarsh | User Access Control
User Access Control Frontend implementation for access denial redirection | 64 | Devarsh | 2 | 9 | Done | 2022-02-19 | 2022-02-19 | Devarsh | User Access Control

## Sprint Planning
Sprint 0 | 2021-09-21
| WI | Assigned | SP | Task Breakdown | SP | Assigned | Team Capacity | Team Member | Capacity
| Project Plan | Audrey | 33 | Introduction | 1 | Audrey | 50 | Albert | 10
|  |  |  | Needs and Problems | 2 | Michael | In Capacity | Audrey | 10
|  |  |  | Goals and Objective | 1 | Joseph |  | Brad | 10
|  |  |  | Feature: Schedule Builder | 3 | Brad |  | Joseph | 10
|  |  |  | Feature: Schedule Comparison | 3 | Brad |  | Michael | 10
|  |  |  | Feature: Course Difficulty | 3 | Michael
|  |  |  | Feature: Matching | 3 | Audrey
|  |  |  | Feture: Student Discounts | 3 | Albert
|  |  |  | Feature: Aid | 3 | Joseph
|  |  |  | Feature: Career Opps | 3 | Albert
|  |  |  | Feature: Schedule of Classes | 3 | Michael
|  |  |  | Feature: Messaging | 3 | Brad
|  |  |  | Obstacles and Solutions | 2 | Albert
|  | TOTAL SP Value | 33
Sprint 1 | 2021-09-28
| WI | Assigned | SP | Task Breakdown | SP | Assigned | Team Capacity | Team Member | Capacity
| BRD | Albert | 37 | Executive Summary | 0.5 | Joseph | 73 | Albert | 16
|  |  |  | Project Description | 0.5 | Joseph | In Capacity | Audrey | 15
|  |  |  | In Scope | 1 | Audrey |  | Brad | 20
|  |  |  | Out of Scope | 1 | Michael |  | Joseph | 10
|  |  |  | Process - Builder | 2 | Brad |  | Michael | 12
|  |  |  | Process - Course Difficulty | 2 | Michael
|  |  |  | Process - Matching | 2 | Audrey
|  |  |  | Process - Career Opportuinty | 2 | Albert
|  |  |  | Process - Aid | 2 | Joseph
|  |  |  | Process - Student Discount | 2 | Albert
|  |  |  | Process - Comparison | 2 | Brad
|  |  |  | Requirements - Builder | 2 | Brad
|  |  |  | Requirements - Course Difficulty | 2 | Michael
|  |  |  | Requirements - Matching | 2 | Audrey
|  |  |  | Requirements - Career Opportuinty | 2 | Albert
|  |  |  | Requirements - Aid | 2 | Joseph
|  |  |  | Requirements - Student Discount | 2 | Albert
|  |  |  | Requirements - Comparison | 2 | Brad
|  |  |  | Reuquirements - Messaging | 2 | Brad
|  |  |  | Requirements - Schedule of Classes | 2 | Michael
|  |  |  | Requirements - Core | 1 | Michael
|  |  |  | Glossary | 0.5 | Audrey
|  |  |  | Document History | 0.5 | Audrey
| Site Map | Audrey | 8.5 | Error Handling | 4 | Audrey
|  |  |  | View - Builder | 0.5 | Brad
|  |  |  | View Comparison | 0.5 | Brad
|  |  |  | View - Course Difficulty | 0.5 | Michael
|  |  |  | View - Matching | 0.5 | Audrey
|  |  |  | View - Student Discount | 0.5 | Albert
|  |  |  | View - Aid | 0.5 | Joseph
|  |  |  | View - Career Opportunity | 0.5 | Albert
|  |  |  | View - Schedule of Classes | 0.5 | Michael
|  |  |  | View - Messaging | 0.5 | Brad
| HL Design | Brad | 7 | Software | 3 | Brad
|  |  |  | Hardware | 3 | Brad
|  |  |  | Choose Software and Hardware | 1 | Brad
| Tech Spec | Michael | 4 | OS Requirements | 1 | Albert
|  |  |  | Project Requirements | 1.5 | Audrey
|  |  |  | Product Requirements | 1.5 | Michael
|  | TOTAL SP Value | 56.5
Sprint 2 | 2021-10-12
| WI | Assigned | SP | Task Breakdown | SP | Assigned | Team Capacity | Team Member | Capacity
| Test Cases | Joseph | 30 | Phone calls: career center | 1 | Joseph | 40 | Albert | 8
|  |  |  | Phone calls: financial aid | 1 | Joseph | In Capacity | Audrey | 8
|  |  |  | Phone calls: David Brown (schedule of classes) | 1 | Joseph |  | Brad | 8
|  |  |  | Test cases: Schedule Building | 3 | Brad |  | Joseph | 8
|  |  |  | Test cases: Discounts | 3 | Albert |  | Michael | 8
|  |  |  | Test cases: Matching | 3 | Audrey
|  |  |  | Test cases: Aid | 3 | Joseph
|  |  |  | Test cases: Course Difficulty | 3 | Michael
|  |  |  | Test cases: Careers | 3 | Albert
|  |  |  | Test cases: Schedule of Classes | 3 | Michael
|  |  |  | Test cases: Messaging | 3 | Audrey
|  |  |  | Test cases: Registration | 1 | Michael
|  |  |  | Test cases: Login | 1 | Michael
|  |  |  | Test cases: Logout | 1 | Michael
|  | TOTAL SP Value | 30
Sprint 3 | 2021-10-20
| WI | Assigned | SP | Task Breakdown | SP | Assigned | Team Capacity | Team Member | Capacity
| Test Plan | Michael | 22 | Test case data: student discounts, careers | 2 | Albert | 90 | Albert | 18
|  |  |  | Test case data: matching, messaging | 2 | Audrey | In Capacity | Audrey | 18
|  |  |  | Test case data: schedules, classes | 2 | Brad |  | Brad | 18
|  |  |  | Test case data: aid | 2 | Joseph |  | Joseph | 18
|  |  |  | Test case data: course rating, registration, login, logout | 2 | Michael |  | Michael | 18
|  |  |  | Test plan: testing schedule | 4 | Audrey
|  |  |  | Detail testing environment | 4 | Michael
|  |  |  | Progression and Regression Testing details | 4 | Joseph
| Network Diagram | Albert | 26 | Information gathering: aid, careers, schedule of classes | 4 | Joseph
|  |  |  | Network Diagram: Choose server provider | 4 | Brad
|  |  |  | Network Diagram: Node system specs | 2 | Joseph
|  |  |  | Network Diagram: IPs/URLs of external servers | 4 | Albert
|  |  |  | Network Diagram: Requests | 4 | Audrey
|  |  |  | Network Diagram: Responses | 4 | Michael
|  |  |  | Network Diagram: 3rd party services & servers | 4 | Albert
| Project Plan | Brad | 22 | Determine feature development order | 4 | Brad
|  |  |  | Determine critical path tasks | 4 | Audrey
|  |  |  | Plan deployment process | 4 | Michael
|  |  |  | Risk Identification | 3 | Brad
|  |  |  | Risk Mitigation | 2 | Michael
|  |  |  | Schedule Project Milestones | 2 | Joseph
|  |  |  | Schedule Sprints | 2 | Albert
|  |  |  | Validate schedule with team | 1 | Brad
| Roadmap | Brad | 2 | Generate Roadmap from schedule | 2 | Albert
|  | TOTAL SP Value | 72
Sprint 4 | 2021-11-04
| WI | Assigned | SP | Task Breakdown | SP | Assigned | Team Capacity | Team Member | Capacity
| LL Desgin | Audrey | 71 | UM Business Requirements | 4 | Joseph | 80 | Albert | 16
|  |  |  | Logging Business Requirements | 4 | Brad | In Capacity | Audrey | 16
|  |  |  | UM Site Map | 3 | Joseph |  | Brad | 16
|  |  |  | UM test plan | 4 | Audrey |  | Joseph | 16
|  |  |  | Logging test plan | 4 | Albert |  | Michael | 16
|  |  |  | UM class diagram (UML) | 8 | Joseph
|  |  |  | Logging class diagram | 8 | Brad
|  |  |  | UM behavioral diagram | 8 | Audrey
|  |  |  | Logging behavioral diagram | 8 | Michael
|  |  |  | UM interfaces to other components | 2 | Albert
|  |  |  | Logging interfaces to other components | 2 | Brad
|  |  |  | UM Feature Pseudocode | 6 | Albert
|  |  |  | Logging Feature Pseudocode | 6 | Michael
|  |  |  | Compile UM LL Design Document | 2 | Audrey
|  |  |  | Compile Logging LL Design Document | 2 | Michael
|  | TOTAL SP Value | 71
Sprint 5 | 2021-11-14
| WI | Assigned | SP | Task Breakdown | SP | Assigned | Team Capacity | Team Member | Capacity
| LL Desgin | Audrey | 46.5 | UM Business Requirements | 1 | Joseph | 100 | Albert | 20
|  |  |  | Logging Business Requirements | 1 | Brad | In Capacity | Audrey | 20
|  |  |  | UM Site Map | 2 | Joseph |  | Brad | 20
|  |  |  | Logging test plan | 0.5 | Albert |  | Joseph | 20
|  |  |  | UM class diagram (UML) | 8 | Joseph |  | Michael | 20
|  |  |  | Logging class diagram | 7 | Brad
|  |  |  | UM sequence diagram | 5 | Audrey
|  |  |  | Logging behavioral diagram | 3 | Michael
|  |  |  | UM interfaces to other components | 2 | Albert
|  |  |  | Logging interfaces to other components | 1 | Brad
|  |  |  | UM Feature Pseudocode | 6 | Albert
|  |  |  | Logging Feature Pseudocode | 6 | Michael
|  |  |  | Compile UM LL Design Document | 2 | Audrey
|  |  |  | Compile Logging LL Design Document | 2 | Michael
| Core Components | Michael | 48 | Update BRD (feedback) | 2 | Joseph
|  |  |  | Update HL Design (feedback) | 2 | Brad
|  |  |  | Update Network Diagram (feedback) | 2 | Albert
|  |  |  | Update Project Plan (feedback) | 2 | Brad
|  |  |  | Update Site Map (feedback) | 2 | Audrey
|  |  |  | Update Tech Spec (feedback) | 2 | Audrey
|  |  |  | Update Test Plan (feedback) | 2 | Michael
|  |  |  | Archiving (BRD) | 2 | Michael
|  |  |  | Archiving (Sitemap) | 2 | Michael
|  |  |  | Archiving (Test Plan) | 2 | Michael
|  |  |  | Error Handling (BRD) | 2 | Albert
|  |  |  | Error Handling (Sitemap) | 2 | Albert
|  |  |  | Error Handling (Test Plan) | 2 | Albert
|  |  |  | Logging (Sitemap) | 2 | Brad
|  |  |  | Usage Analysis Dashboard (BRD) | 2 | Audrey
|  |  |  | Usage Analysis Dashboard (Sitemap) | 2 | Brad
|  |  |  | Usage Analysis Dashboard (Test Plan) | 2 | Audrey
|  |  |  | User Access Control (BRD) | 2 | Joseph
|  |  |  | User Access Control (Sitemap) | 2 | Joseph
|  |  |  | User Access Control (Test Plan) | 2 | Joseph
|  |  |  | User Management (Sitemap) | 2 | Audrey
|  |  |  | Registration (BRD) | 1 | Albert
|  |  |  | Registration (Test Plan) | 1 | Albert
|  |  |  | Login (BRD) | 1 | Audrey
|  |  |  | Login (Test Plan) | 1 | Audrey
|  |  |  | Logout (BRD) | 1 | Brad
|  |  |  | Logout (Test Plan) | 1 | Brad
|  | TOTAL SP Value | 94.5
Sprint 6 | 2021-11-28
| WI | Assigned | SP | Task Breakdown | SP | Assigned | Team Capacity | Team Member | Capacity
| LL Design | Audrey | 31 | Tech approval: unit testing | 4 | Michael | 112 | Albert | 22
|  |  |  | Tech approval: ORM | 4 | Joseph | In Capacity | Audrey | 22
|  |  |  | Tech Approval: Cron | 4 | Brad |  | Brad | 22
|  |  |  | Logging class diagram | 3.5 | Brad |  | Joseph | 22
|  |  |  | UM sequence diagram | 4 | Audrey |  | Michael | 24
|  |  |  | Logging behavioral diagram | 1 | Michael
|  |  |  | UM interfaces to other components | 2 | Albert
|  |  |  | Logging interfaces to other components | 0.5 | Brad
|  |  |  | UM Feature Pseudocode | 2 | Albert
|  |  |  | Logging Feature Pseudocode | 2 | Michael
|  |  |  | Compile UM LL Design Document | 2 | Audrey
|  |  |  | Compile Logging LL Design Document | 2 | Michael
| Core Components | Michael | 32 | UM Business Requirements | 1 | Joseph
|  |  |  | Update BRD (feedback) | 2 | Joseph
|  |  |  | Update Test Plan (feedback) | 2 | Michael
|  |  |  | BRD: Authorize | 1 | Audrey
|  |  |  | Test: Authorize | 1 | Audrey
|  |  |  | Site Map: Authorize | 1 | Audrey
|  |  |  | BRD: Account Deletion | 1 | Joseph
|  |  |  | Test Cases: Account Deletion | 1 | Joseph
|  |  |  | Implementation: Authorization | 2 | Albert
|  |  |  | Implementation: Authenication | 2 | Audrey
|  |  |  | Tests: Authorization | 2 | Albert
|  |  |  | Tests: Authentication | 2 | Audrey
|  |  |  | Archiving (BRD) | 1 | Michael
|  |  |  | Archiving (Test Plan) | 1 | Michael
|  |  |  | User Access Control (BRD) | 2 | Audrey
|  |  |  | User Access Control (Sitemap) | 1.5 | Joseph
|  |  |  | User Access Control (Test Plan) | 1.5 | Joseph
|  |  |  | Registration (BRD) | 1 | Albert
|  |  |  | Registration (Test Plan) | 1 | Albert
|  |  |  | Review BRD, Tech Spec | 1 | Albert
|  |  |  | Review LL Design Logging, Project Plan | 1 | Audrey
|  |  |  | Review LL Design UM, Network Diagram | 1 | Brad
|  |  |  | Review Test Plan | 1 | Joseph
|  |  |  | Review Site Map, HL Design | 1 | Michael
| UM | Audrey | 19 | UM Implementation: Model class: User Account | 1 | Audrey
|  |  |  | UM Implementation: Create | 1 | Joseph
|  |  |  | UM Implementation: Update | 1 | Albert
|  |  |  | UM Implementation: Delete | 1 | Audrey
|  |  |  | UM Implementation: Enable/disable | 1 | Joseph
|  |  |  | UM Implementation: Execute bulk operations | 4 | Albert
|  |  |  | UM Tests: Create | 2 | Joseph
|  |  |  | UM Tests: Update | 2 | Albert
|  |  |  | UM Tests: Delete | 2 | Audrey
|  |  |  | UM Tests: Enable/disable | 2 | Joseph
|  |  |  | UM Tests: Execute bulk operations | 2 | Albert
| Logging | Brad | 19 | Logging Implementation: Model class: Log | 1 | Brad
|  |  |  | Logging Implementation | 8 | Brad
|  |  |  | Archiving Implementation | 4 | Michael
|  |  |  | Logging Tests | 4 | Michael
|  |  |  | Archiving Tests | 2 | Brad
|  | TOTAL SP Value | 101
Sprint 7 | 2022-01-10
| WI | Assigned | SP | Task Breakdown | SP | Assigned | Team Capacity | Team Member | Capacity
| Registration | Albert | 32 | Registration Class Diagram | 8 | Albert | 160 | Albert | 33
|  |  |  | Registration Behavioral Diagram | 12 | Albert | In Capacity | Audrey | 33
|  |  |  | Registration Backend Implemtation | 4 | Albert |  | Brad | 30
|  |  |  | Registration Frontend Implemtation | 4 | Albert |  | Joseph | 33
|  |  |  | Registration Testing | 4 | Albert |  | Michael | 31
| Login | Audrey | 32 | Login Class Diagram | 8 | Audrey
|  |  |  | Login Behavioral Diagram | 12 | Audrey
|  |  |  | Login Backend Implemtation | 4 | Audrey
|  |  |  | Login Frontend Implemtation | 4 | Audrey
|  |  |  | Login Testing | 4 | Audrey
| Logout | Brad | 32 | Logout Class Diagram | 8 | Michael
|  |  |  | Logout Behavioral Diagram | 12 | Brad
|  |  |  | Logout Backend Implemtation | 4 | Brad
|  |  |  | Logout Frontend Implemtation | 4 | Brad
|  |  |  | Logout Testing | 4 | Brad
| Error Handling | Joseph | 32 | Error Handling Class Diagram | 8 | Joseph
|  |  |  | Error Handling Behavioral Diagram | 12 | Joseph
|  |  |  | Error Handling Backend Implemtation | 4 | Joseph
|  |  |  | Error Handling Frontend Implemtation | 4 | Joseph
|  |  |  | Error Handling Testing | 4 | Joseph
| Tech Spec | Michael | 12 | Tech Approval: HTML | 6 | Michael
|  |  |  | Tech Approval: CSS | 6 | Michael
| Feedback | Michael | 8 | Address git repo: clean up files | 2 | Brad
|  |  |  | Address test parity (tests should pass when desired result happens) | 6 | Michael
|  | TOTAL SP Value | 148
Sprint 8 | 2022-01-24
| WI | Assigned | SP | Task Breakdown | SP | Assigned | Team Capacity | Team Member | Capacity
| Registration | Albert | 17 | Registration Class Diagram | 6 | Albert | 125 | Albert | 16
|  |  |  | Registration Behavioral Diagram | 2 | Albert | In Capacity | Audrey | 12
|  |  |  | Registration Backend Implemtation | 4 | Brad |  | Brad | 32
|  |  |  | Registration Frontend Implemtation | 4 | Brad |  | Devarsh | 5
|  |  |  | Registration Testing | 1 | Albert |  | Jacob | 7
| Login | Audrey | 11 | Login Class Diagram | 1 | Audrey |  | Joseph | 23
|  |  |  | Login Behavioral Diagram | 1 | Audrey |  | Michael | 25
|  |  |  | Login Backend Implemtation | 4 | Audrey |  | SzeMan | 5
|  |  |  | Login Frontend Implemtation | 4 | Audrey
|  |  |  | Login Testing | 1 | Audrey
| Logout | Brad | 28 | Logout Class Diagram | 8 | Michael
|  |  |  | Logout Behavioral Diagram | 11 | Brad
|  |  |  | Logout Backend Implemtation | 4 | Brad
|  |  |  | Logout Frontend Implemtation | 4 | Brad
|  |  |  | Logout Testing | 1 | Brad
| Error Handling | Joseph | 17 | Error Handling Class Diagram | 4 | Joseph
|  |  |  | Error Handling Behavioral Diagram | 8 | Joseph
|  |  |  | Error Handling Backend Implemtation | 3 | Joseph
|  |  |  | Error Handling Frontend Implemtation | 1 | Joseph
|  |  |  | Error Handling Testing | 1 | Joseph
| Tech Spec | Michael | 14 | Tech Approval: HTML | 4 | Michael
|  |  |  | Tech Approval: CSS | 4 | Michael
|  |  |  | Tech Approval: Jobs API | 6 | Albert
| Feedback | Michael | 6 | Address test parity (tests should pass when desired result happens) | 6 | Michael
| Project Plan | Brad | 3 | Update project plan to account for code reviews | 1 | Brad
|  |  |  | Update Prokect Plan | 2 | Brad
| BRD | Albert | 14 | New Feature for Jacob | 1 | Jacob
|  |  |  | New Feature for Joseph | 1 | Joseph
|  |  |  | New Feature for Devarsh | 1 | Devarsh
|  |  |  | New Feature for SzeMan | 1 | SzeMan
|  |  |  | BRD for Book Selling | 2 | Jacob
|  |  |  | BRD for Event Plannig | 2 | SzeMan
|  |  |  | BRD for Automated Moderating | 2 | Joseph
|  |  |  | BRD for GPA Calulator | 2 | Jacob
|  |  |  | BRD for Recipe Sharing | 2 | Devarsh
|  | TOTAL SP Value | 110
Sprint 9 | 2022-02-07
| WI | Assigned | SP | Task Breakdown | SP | Assigned | Team Capacity | Team Member | Capacity
| Registration | Albert | 48 | Registration Class Diagram | 4 | Albert | 200 | Albert | 20
|  |  |  | Registration Behavioral Diagram | 2 | Albert | In Capacity | Audrey | 27
|  |  |  | Registration Backend Implemtation | 4 | Joseph |  | Brad | 29
|  |  |  | Registration Frontend Implemtation | 6 | Albert |  | Devarsh | 23
|  |  |  | Registration Testing | 4 | Albert |  | Jacob | 27
|  |  |  | Email verification behavior diagram | 6 | Joseph |  | Joseph | 20
|  |  |  | Email verification class/database diagram | 2 | Audrey |  | Michael | 24
|  |  |  | Email verification tests | 4 | Audrey |  | SzeMan | 30
|  |  |  | Email verification backend implementation | 4 | Michael
|  |  |  | Email verification frontend implementation | 4 | Audrey
|  |  |  | Review registration for error handling | 4 | Jacob
|  |  |  | Registration error handling implementation | 4 | Joseph
| Login | Audrey | 22 | Login Class Diagram | 1 | Audrey
|  |  |  | Login Behavioral Diagram | 1 | Audrey
|  |  |  | Login Backend Implemtation | 2.5 | Audrey
|  |  |  | Login Frontend Implemtation | 3 | Audrey
|  |  |  | Login Testing | 3.5 | Audrey
|  |  |  | Authentication Tokens/authentication cookies class/database diagram | 3 | Michael
|  |  |  | Review login for error handling | 4 | Jacob
|  |  |  | Login error handling implementation | 4 | Audrey
| Logout | Brad | 38 | Logout Class Diagram | 8 | Michael
|  |  |  | Logout Behavioral Diagram | 10 | Brad
|  |  |  | Logout Backend Implemtation | 4 | Brad
|  |  |  | Logout Frontend Implemtation | 4 | Brad
|  |  |  | Logout Testing | 4 | Brad
|  |  |  | Review logout for error handling | 4 | Joseph
|  |  |  | Logout error handling implementation | 4 | Brad
| Tech Spec | Michael | 9.5 | Tech Approval: HTML | 3 | Michael
|  |  |  | Tech Approval: CSS | 3 | Michael
|  |  |  | Tech Approval: Jobs API | 3.5 | Albert
| Feedback | Michael | 5 | Address test parity (tests should pass when desired result happens) (UM) | 1 | Audrey
|  |  |  | Address test parity (tests should pass when desired result happens) (Archiving) | 2 | Michael
|  |  |  | Address test parity (tests should pass when desired result happens) (Logging) | 2 | Brad
| Automated Moderating | Joseph | 0.5 | Automated Moderating Test Plan | 0.5 | Joseph
| Book Selling | Jacob | 3 | Book Selling Site Map | 1 | Jacob
|  |  |  | Book Selling Test Plan | 2 | Jacob
| Event Planning | SzeMan | 1.25 | Event Planning Site Map | 1 | SzeMan
|  |  |  | Review Event Planning Test Plan | 0.25 | SzeMan
| Grade Calculator | Jacob | 3 | Grade Calculator Site Map | 1 | Jacob
|  |  |  | Grade Calculator Test Plan | 2 | Jacob
| Recipe Sharing | Devrsh | 1.25 | Recipe Sharing Site Map | 1 | Devarsh
|  |  |  | Review Recipe Sharing Test Plan | 0.25 | Devarsh
| Site Map | Audrey | 0.25 | Copy home page & example from original site map to second page | 0.25 | Brad
| User Management | Audrey | 12 | User Management frontend implementation (single CRUD operations) | 4 | Jacob
|  |  |  | User Management frontend implementation (file upload for bulk operations) | 4 | Jacob
|  |  |  | User Management frontend implementation (bulk CRUD operations) | 4 | Jacob
| Usage Analysis Dashboard | SzeMan | 27 | Usage Analysis Dashboard Behavior Diagrams | 4 | SzeMan
|  |  |  | Usage Analysis Dashboard Class/database diagram | 2 | SzeMan
|  |  |  | Usage Analysis Dashboard Query Tests | 3 | SzeMan
|  |  |  | Usage Analysis Dashboard Graph/chart tests? | 4 | SzeMan
|  |  |  | Usage Analysis Dashboard Backend implementation Query AS02.1 | 1 | SzeMan
|  |  |  | Usage Analysis Dashboard Backend implementation Query AS02.2 | 1 | SzeMan
|  |  |  | Usage Analysis Dashboard Backend implementation Query AS02.3 | 1 | SzeMan
|  |  |  | Usage Analysis Dashboard Backend implementation Query AS02.4 | 1 | SzeMan
|  |  |  | Usage Analysis Dashboard Backend implementation Query AS02.5 | 1 | SzeMan
|  |  |  | Usage Analysis Dashboard Backend implementation Query AS02.6 | 1 | SzeMan
|  |  |  | Usage Analysis Dashboard Frontend implementation Bar graphs | 4 | SzeMan
|  |  |  | Usage Analysis Dashboard Frontend implementation Trend charts | 4 | SzeMan
| User Access Control | Devarsh | 20 | User Access Control Behavior Diagrams | 4 | Devarsh
|  |  |  | User Access Control Class/database diagram | 2 | Devarsh
|  |  |  | User Access Control Tests | 4 | Devarsh
|  |  |  | User Access Control Backend implementation | 6 | Devarsh
|  |  |  | User Access Control Frontend implementation for access denial message | 2 | Devarsh
|  |  |  | User Access Control Frontend implementation for access denial redirection | 2 | Devarsh
|  | TOTAL SP Value | 190.75
Sprint 10 | 2022-02-21
| WI | Assigned | SP | Task Breakdown | SP | Assigned | Team Capacity | Team Member | Capacity
| Registration | Albert | 25.5 | Registration Class Diagram | 2 | Albert | 250 | Albert | 35
|  |  |  | Registration Backend Implemtation | 1.5 | Joseph | In Capacity | Audrey | 35
|  |  |  | Registration Frontend Implemtation | 6 | Albert |  | Brad | 40
|  |  |  | Registration Testing | 4 | Albert |  | Devarsh | 23
|  |  |  | Email verification behavior diagram | 2 | Joseph |  | Jacob | 30
|  |  |  | Email verification tests | 2 | Audrey |  | Joseph | 30
|  |  |  | Email verification backend implementation | 4 | Michael |  | Michael | 35
|  |  |  | Email verification frontend implementation | 2.5 | Audrey |  | SzeMan | 22
|  |  |  | Registration error handling implementation | 1.5 | Joseph
| Login | Audrey | 6.5 | Login Backend Implemtation | 0.5 | Audrey
|  |  |  | Login Frontend Implemtation | 1 | Audrey
|  |  |  | Login Testing | 1 | Audrey
|  |  |  | Authentication Tokens/authentication cookies class/database diagram | 2 | Michael
|  |  |  | Login error handling implementation | 2 | Audrey
| Logout | Brad | 18 | Logout Backend Implemtation | 4 | Brad
|  |  |  | Logout Frontend Implemtation | 4 | Brad
|  |  |  | Logout Testing | 4 | Brad
|  |  |  | Review logout for error handling | 2 | Joseph
|  |  |  | Logout error handling implementation | 4 | Brad
| Tech Spec | Michael | 4 | Tech Approval: HTML | 2 | Michael
|  |  |  | Tech Approval: CSS | 2 | Michael
| Feedback | Michael | 2 | Address test parity (tests should pass when desired result happens) (Archiving) | 2 | Michael
| Recipe Sharing | Devrsh | 1.25 | Recipe Sharing Site Map | 1 | Devarsh
|  |  |  | Review Recipe Sharing Test Plan | 0.25 | Devarsh
| User Management | Audrey | 7 | User Management frontend implementation (single CRUD operations) | 2 | Jacob
|  |  |  | User Management frontend implementation (file upload for bulk operations) | 3 | Jacob
|  |  |  | User Management frontend implementation (bulk CRUD operations) | 2 | Jacob
| Usage Analysis Dashboard | SzeMan | 21 | Usage Analysis Dashboard Query Tests | 3 | SzeMan
|  |  |  | Usage Analysis Dashboard Graph/chart tests? | 4 | SzeMan
|  |  |  | Usage Analysis Dashboard Backend implementation Query AS02.1 | 1 | SzeMan
|  |  |  | Usage Analysis Dashboard Backend implementation Query AS02.2 | 1 | SzeMan
|  |  |  | Usage Analysis Dashboard Backend implementation Query AS02.3 | 1 | SzeMan
|  |  |  | Usage Analysis Dashboard Backend implementation Query AS02.4 | 1 | SzeMan
|  |  |  | Usage Analysis Dashboard Backend implementation Query AS02.5 | 1 | SzeMan
|  |  |  | Usage Analysis Dashboard Backend implementation Query AS02.6 | 1 | SzeMan
|  |  |  | Usage Analysis Dashboard Frontend implementation Bar graphs | 4 | SzeMan
|  |  |  | Usage Analysis Dashboard Frontend implementation Trend charts | 4 | SzeMan
| User Access Control | Devarsh | 20 | User Access Control Behavior Diagrams | 4 | Devarsh
|  |  |  | User Access Control Class/database diagram | 2 | Devarsh
|  |  |  | User Access Control Tests | 4 | Devarsh
|  |  |  | User Access Control Backend implementation | 6 | Devarsh
|  |  |  | User Access Control Frontend implementation for access denial message | 2 | Devarsh
|  |  |  | User Access Control Frontend implementation for access denial redirection | 2 | Devarsh
| Schedule Builder | Brad | 24 | Schedule Builder Behavior Diagrams | 5 | Brad
|  |  |  | Schedule Builder Class Diagrams | 2 | Brad
|  |  |  | Schedule Builder Database Diagrams | 1 | Brad
|  |  |  | Schedule Builder Tests | 4 | Brad
|  |  |  | Schedule Builder Backend implementation | 8 | Brad
|  |  |  | Schedule Builder Frontend implementation | 4 | Brad
| Student Discounts | Albert | 22 | Student Discounts Behavior Diagrams | 5 | Albert
|  |  |  | Student Discounts Class Diagrams | 2 | Albert
|  |  |  | Student Discounts Database Diagrams | 1 | Albert
|  |  |  | Student Discounts Tests | 4 | Albert
|  |  |  | Student Discounts Backend implementation | 6 | Albert
|  |  |  | Student Discounts Frontend implementation | 4 | Albert
| Messages | Audrey | 22 | Messages Behavior Diagrams | 5 | Audrey
|  |  |  | Messages Class Diagrams | 2 | Audrey
|  |  |  | Messages Database Diagrams | 1 | Audrey
|  |  |  | Messages Tests | 4 | Audrey
|  |  |  | Messages Backend implementation | 6 | Audrey
|  |  |  | Messages Frontend implementation | 4 | Audrey
| GPA Calculator | Jacob | 23 | GPA Calculator Behavior Diagrams | 5 | Jacob
|  |  |  | GPA Calculator Class Diagrams | 2 | Jacob
|  |  |  | GPA Calculator Database Diagrams | 1 | Jacob
|  |  |  | GPA Calculator Tests | 4 | Jacob
|  |  |  | GPA Calculator Backend implementation | 4 | Jacob
|  |  |  | GPA Calculator Frontend implementation | 7 | Jacob
| Automated Moderating | Joseph | 20.25 | Automated Moderating Behavior Diagrams | 5 | Joseph
|  |  |  | Automated Moderating Class Diagrams | 2 | Joseph
|  |  |  | Automated Moderating Database Diagrams | 1 | Joseph
|  |  |  | Automated Moderating Tests | 4 | Joseph
|  |  |  | Automated Moderating Backend implementation | 4 | Joseph
|  |  |  | Automated Moderating Frontend implementation | 4 | Joseph
|  |  |  | Automated Moderating Test Plan | 0.25 | Joseph
| Schedule of Classes | Michael | 22 | Schedule of Classes Behavior Diagrams | 5 | Michael
|  |  |  | Schedule of Classes Class Diagrams | 2 | Michael
|  |  |  | Schedule of Classes Database Diagrams | 1 | Michael
|  |  |  | Schedule of Classes Tests | 4 | Michael
|  |  |  | Schedule of Classes Backend implementation | 6 | Michael
|  |  |  | Schedule of Classes Frontend implementation | 4 | Michael
|  | TOTAL SP Value | 238.5

## Sprint 10
Sprint 10
| Start Date | 2022-02-22 |  | Day of Sprint | Actual Effort |  |  | Day of Sprint | Forecast | Actual
| End Date | 2022-03-05 |  | 0 | 238.5 |  |  | 0 | 238.5 | 238.5
| Sprint Length | 12 |  | 1 |  |  |  | 1 | 218.625 | 238.5
| Team Size | 8 |  | 2 |  |  |  | 2 | 198.75 | 238.5
| Team Capacity | 250 |  | 3 |  |  |  | 3 | 178.875 | 238.5
| Total Sprint SP | 238.5 |  | 4 |  |  |  | 4 | 159 | 238.5
| SP/Day | 19.875 |  | 5 |  |  |  | 5 | 139.125 | 238.5
|  |  |  | 6 |  |  |  | 6 | 119.25 | 238.5
|  |  |  | 7 |  |  |  | 7 | 99.375 | 238.5
|  |  |  | 8 |  |  |  | 8 | 79.5 | 238.5
|  |  |  | 9 |  |  |  | 9 | 59.625 | 238.5
|  |  |  | 10 |  |  |  | 10 | 39.75 | 238.5
|  |  |  | 11 |  |  |  | 11 | 19.875 | 238.5
|  |  |  | 12 |  |  |  | 12 | 0 | 238.5
|  |  |  | t | w | t | f | s | s | m | t | w | t | f | s
Who | Tasks | Day of Sprint (hours worked)
|  |  | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
Albert
| Registration Class Diagram | 2 | 0: 0
| Registration Tests | 4 | 0: 0
| Registration frontend implementation | 6 | 0: 0
| Student Discounts Behavior Diagrams | 5 | 0: 0
| Student Discounts Class diagrams | 2 | 0: 0
| Student Discounts Database diagrams | 1 | 0: 0
| Student Discounts Tests | 4 | 0: 0
| Student Discounts Backend implementation | 6 | 0: 0
| Student Discounts Frontend Implementation | 4 | 0: 0
SP Decrement |  |  | 0: 0
Audrey
| Email verification tests | 2 | 0: 0
| Login Tests | 1 | 0: 0
| Email verification frontend implementation | 2.5 | 0: 0
| Login backend implementation | 0.5 | 0: 0
| Login frontend implementation | 1 | 0: 0
| Login error handling implementation | 2 | 0: 0
| Message Behavior Diagrams | 5 | 0: 0
| Message Class diagrams | 2 | 0: 0
| Message Database diagrams | 1 | 0: 0
| Message Tests | 4 | 0: 0
| Message Backend implementation | 6 | 0: 0
| Message Frontend Implementation | 4 | 0: 0
SP Decrement |  |  | 0: 0
Brad
| Logout Tests | 4 | 0: 0
| Logout backend implementation | 4 | 0: 0
| Logout frontend implementation | 4 | 0: 0
| Logout error handling implementation | 4 | 0: 0
| Schedule Builder Behavior Diagrams | 5 | 0: 0
| Schedule Builder Class diagrams | 2 | 0: 0
| Schedule Builder Database diagrams | 1 | 0: 0
| Schedule Builder Tests | 4 | 0: 0
| Schedule Builder Backend implementation | 8 | 0: 0
| Schedule Builder Frontend Implementation | 4 | 0: 0
SP Decrement |  |  | 0: 0
Devarsh
| Recipe Sharing Site Map | 1 | 0: 0
| Review Recipe Sharing Test Plan | 0.25 | 0: 0
| User Access Control Behavior Diagrams | 4 | 0: 0
| User Access Control Class/database diagram | 2 | 0: 0
| User Access Control Tests | 4 | 0: 0
| User Access Control Backend implementation | 6 | 0: 0
| User Access Control Frontend implementation for access denial message | 2 | 0: 0
| User Access Control Frontend implementation for access denial redirection | 2 | 0: 0
SP Decrement |  |  | 0: 0
Jacob
| User Management frontend implementation (single CRUD operations) | 2 | 0: 0
| User Management frontend implementation (file upload for bulk operations) | 3 | 0: 0
| User Management frontend implementation (bulk CRUD operations) | 2 | 0: 0
| GPA Calc/Leaderboard Behavior Diagrams | 5 | 0: 0
| GPA Calc/Leaderboard Class diagrams | 2 | 0: 0
| GPA Calc/Leaderboard Database diagrams | 1 | 0: 0
| GPA Calc/Leaderboard Tests | 4 | 0: 0
| GPA Calc/Leaderboard Backend implementation | 4 | 0: 0
| GPA Calc/Leaderboard Frontend Implementation | 7 | 0: 0
SP Decrement |  |  | 0: 0
Joseph
| Automated Moderating Test Plan | 0.25 | 0: 0
| Email verification behavior diagram | 2 | 0: 0
| Review logout for error handling | 2 | 0: 0
| Registration backend implementation | 1.5 | 0: 0
| Registration error handling implementation | 1.5 | 0: 0
| Automated Moderting Behavior Diagrams | 5 | 0: 0
| Automated Moderting Class diagrams | 2 | 0: 0
| Automated Moderting Database diagrams | 1 | 0: 0
| Automated Moderting Tests | 4 | 0: 0
| Automated Moderting Backend implementation | 4 | 0: 0
| Automated Moderting Frontend Implementation | 4 | 0: 0
SP Decrement |  |  | 0: 0
Michael
| Tech Approval: HTML | 2 | 0: 0
| Address test parity (tests should pass when desired result happens) (Archiving) | 2 | 0: 0
| Tech Approval: CSS | 2 | 0: 0
| Authentication Tokens/authentication cookies class/database diagram | 2 | 0: 0
| Email verification backend implementation | 4 | 0: 0
| Schedule of Classes Behavior Diagrams | 5 | 0: 0
| Schedule of Classes Class diagrams | 2 | 0: 0
| Schedule of Classes Database diagrams | 1 | 0: 0
| Schedule of Classes Tests | 4 | 0: 0
| Schedule of Classes Backend implementation | 6 | 0: 0
| Schedule of Classes Frontend Implementation | 4 | 0: 0
SP Decrement |  |  | 0: 0
SzeMan
| Usage Analysis Dashboard Query Tests | 3 | 0: 0
| Usage Analysis Dashboard Graph/chart tests? | 4 | 0: 0
| Usage Analysis Dashboard Backend implementation Query AS02.1 | 1 | 0: 0
| Usage Analysis Dashboard Backend implementation Query AS02.2 | 1 | 0: 0
| Usage Analysis Dashboard Backend implementation Query AS02.3 | 1 | 0: 0
| Usage Analysis Dashboard Backend implementation Query AS02.4 | 1 | 0: 0
| Usage Analysis Dashboard Backend implementation Query AS02.5 | 1 | 0: 0
| Usage Analysis Dashboard Backend implementation Query AS02.6 | 1 | 0: 0
| Usage Analysis Dashboard Frontend implementation Bar graphs | 4 | 0: 0
| Usage Analysis Dashboard Frontend implementation Trend charts | 4 | 0: 0
SP Decrement |  |  | 0: 0
Total Change |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Daily Scrum Meeting
Day of Sprint | Who | What did you work on Yesterday? | 2: What are you working on today?; 5: Are You Blocked?
Day 1 | Albert | n/a | bar: 5
| Audrey | n/a | bar: 5
| Brad | n/a | bar: 5
| Devarsh | n/a | bar: 5
| Jacob | n/a | bar: 5
| Joseph | n/a | bar: 5
| Michael | n/a | bar: 5
| SzeMan | n/a | bar: 5
Day 2 | Albert | bar: 5
Audrey | bar: 5
Brad | bar: 5
Devarsh | bar: 5
Jacob | bar: 5
Joseph | bar: 5
Michael | bar: 5
SzeMan | bar: 5
Day 3 | Albert | bar: 5
Audrey | bar: 5
Brad | bar: 5
Devarsh | bar: 5
Jacob | bar: 5
Joseph | bar: 5
Michael | bar: 5
SzeMan | bar: 5
Day 4 | Albert | Tech Approval: Jobs API | bar: 5
Audrey | bar: 5
Brad | bar: 5
Devarsh | bar: 5
Jacob | bar: 5
Joseph | bar: 5
Michael | bar: 5
SzeMan | bar: 5
Day 5 | Albert | bar: 5
Audrey | bar: 5
Brad | bar: 5
Devarsh | bar: 5
Jacob | bar: 5
Joseph | bar: 5
Michael | bar: 5
SzeMan | bar: 5
Day 6 | Albert | bar: 5
Audrey | bar: 5
Brad | bar: 5
Devarsh | bar: 5
Jacob | bar: 5
Joseph | bar: 5
Michael | bar: 5
SzeMan | bar: 5
Day 7 | Albert | bar: 5
Audrey | bar: 5
Brad | bar: 5
Devarsh | bar: 5
Jacob | bar: 5
Joseph | bar: 5
Michael | bar: 5
SzeMan | bar: 5
Day 8 | Albert | bar: 5
Audrey | bar: 5
Brad | bar: 5
Devarsh | bar: 5
Jacob | bar: 5
Joseph | bar: 5
Michael | bar: 5
SzeMan | bar: 5
Day 9 | Albert | bar: 5
Audrey | bar: 5
| Brad | addressed test parity for logging | bar: 5
Devarsh | bar: 5
Jacob | bar: 5
Joseph | bar: 5
Michael | bar: 5
SzeMan | bar: 5
Day 10 | Albert | bar: 5
Audrey | bar: 5
Brad | bar: 5
Devarsh | bar: 5
Jacob | bar: 5
Joseph | bar: 5
Michael | bar: 5
SzeMan | bar: 5
Day 11 | Albert | bar: 5
Audrey | bar: 5
Brad | bar: 5
Devarsh | bar: 5
Jacob | bar: 5
Joseph | bar: 5
Michael | bar: 5
SzeMan | bar: 5
Day 12 | Albert | bar: 5
Audrey | bar: 5
Brad | bar: 5
Devarsh | bar: 5
Jacob | bar: 5
Joseph | bar: 5
Michael | bar: 5
SzeMan | bar: 5

## Sprint 9
Sprint 9
| Start Date | 2022-02-08 |  | Day of Sprint | Actual Effort |  |  | Day of Sprint | Forecast | Actual
| End Date | 2022-02-19 |  | 0 | 190.75 |  |  | 0 | 190.75 | 190.75
| Sprint Length | 12 |  | 1 | 187 |  |  | 1 | 174.8542 | 187
| Team Size | 8 |  | 2 | 180.75 |  |  | 2 | 158.9583 | 180.75
| Team Capacity | 200 |  | 3 | 172 |  |  | 3 | 143.0625 | 172
| Total Sprint SP | 190.75 |  | 4 | 168 |  |  | 4 | 127.1667 | 168
| SP/Day | 15.8958 |  | 5 | 160.5 |  |  | 5 | 111.2708 | 160.5
|  |  |  | 6 | 154.5 |  |  | 6 | 95.375 | 154.5
|  |  |  | 7 | 146 |  |  | 7 | 79.4792 | 146
|  |  |  | 8 | 137 |  |  | 8 | 63.5833 | 137
|  |  |  | 9 | 127 |  |  | 9 | 47.6875 | 127
|  |  |  | 10 | 115.5 |  |  | 10 | 31.7917 | 115.5
|  |  |  | 11 | 103.75 |  |  | 11 | 15.8958 | 103.75
|  |  |  | 12 | 95.25 |  |  | 12 | 0 | 95.25
|  |  |  | t | w | t | f | s | s | m | t | w | t | f | s
Who | Tasks | Day of Sprint (hours worked)
|  |  | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
Albert
| Tech Approval: Jobs API | 3.5 | 0 | 0 | 2 | 3 | 3 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0
| Registration Behavior Diagram | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0
| Registration Class Diagram | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2
| Registration Tests | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Registration frontend implementation | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 19.5 | 7: 0; 8: 0; 9: 0; 10: 0; 11: 0; 12: 0 | 12
SP Decrement |  |  | 0 | 0 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 1 | 1 | 1 | 1 | 7.5
Audrey
| Address test parity (tests should pass when desired result happens) (UM) | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Login Behavior Diagram | 1 | 0 | 0 | 0 | 0 | 1 | 0.5 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0
| Login Class Diagram | 1 | 0 | 0 | 0 | 0 | 0.5 | 0.5 | 0 | 0 | 0.5 | 0 | 0.5 | 0.5 | 0
| Login backend implementation | 2.5 | 0 | 0 | 1 | 0 | 0.5 | 1 | 0 | 0 | 1 | 1 | 1 | 4 | 4
| Login frontend implementation | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0.5 | 1
| Login Tests | 3.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 1
| Email verification class/database diagram | 2 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0.5 | 0.5 | 0
| Email verification frontend implementation | 4 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Email verification tests | 4 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Login error handling implementation | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 9
SP Decrement |  |  | 0 | 1 | 1 | 2 | 0.5 | 1.5 | 0 | 1 | 1.5 | 1.5 | 1 | 3 | 3 | 17
Brad
| Copy home page & example from original site map to second page | 0.25 | 0 | 0.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Address test parity (tests should pass when desired result happens) (Logging) | 2 | 0 | 0 | 1 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0
| Logout Behavior Diagram | 10 | 0 | 0 | 0 | 2 | 0 | 1 | 0 | 0.5 | 2 | 1 | 2 | 1.5 | 0
| Logout Tests | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Logout backend implementation | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Logout frontend implementation | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Logout error handling implementation | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16
SP Decrement |  | 28.25 | 0 | 0.25 | 1 | 1 | 0.25 | 0.5 | 1 | 0.5 | 2.5 | 1 | 3 | 1.25 | 0 | 12.25
Devarsh
| Recipe Sharing Site Map | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Review Recipe Sharing Test Plan | 0.25 | 0 | 0 | 0.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| User Access Control Behavior Diagrams | 4 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0
| User Access Control Class/database diagram | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0
| User Access Control Tests | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1
| User Access Control Backend implementation | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| User Access Control Frontend implementation for access denial message | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| User Access Control Frontend implementation for access denial redirection | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11
SP Decrement |  | 21.25 | 0 | 1 | 0.25 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 10.25
Jacob
| Book Selling Site Map | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Grade Calculator Site Map | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Book Selling Test Plan | 2 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Grade Calculator Test Plan | 2 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| User Management frontend implementation (single CRUD operations) | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0
| User Management frontend implementation (file upload for bulk operations) | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0
| User Management frontend implementation (bulk CRUD operations) | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0
| Review registration for error handling | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 1
| Review login for error handling | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 7
SP Decrement |  | 26 | 0 | 1 | 1 | 2 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 1 | 2 | 19
Joseph
| Automated Moderating Test Plan | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0
| Email verification behavior diagram | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0
| Registration backend implementation | 4 | 0 | 1 | 1 | 1 | 0.5 | 0.5 | 0.5 | 1 | 0.5 | 1 | 1 | 0.5 | 0
| Registration error handling implementation | 4 | 0 | 1 | 1 | 0.5 | 0.5 | 0.5 | 1 | 0 | 0.5 | 1 | 0.5 | 0.5 | 2
| Review logout for error handling | 4 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 7.25
SP Decrement |  | 18.5 | 0 | 0.5 | 1 | 0.75 | 0.5 | 1 | 0.5 | 0.5 | 1.5 | 0.5 | 2 | 2 | 0.5 | 11.25
Michael
| Address test parity (tests should pass when desired result happens) (Archiving) | 2 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1
| Tech Approval: HTML | 3 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Tech Approval: CSS | 3 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Authentication Tokens/authentication cookies class/database diagram | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Logout Class Diagram | 8 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 2 | 0 | 2 | 0
| Email verification backend implementation | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12
SP Decrement |  | 23 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 2 | 0 | 2 | 1 | 2 | 1 | 11
SzeMan
| Event Planning Site Map | 1 | 0 | 0 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Review Event Planning Test Plan | 0.25 | 0 | 0 | 0 | 0 | 0.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Usage Analysis Dashboard Behavior Diagrams | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0
| Usage Analysis Dashboard Class/database diagram | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0.5 | 0.5 | 0
| Usage Analysis Dashboard Query Tests | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Usage Analysis Dashboard Graph/chart tests? | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Usage Analysis Dashboard Backend implementation Query AS02.1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Usage Analysis Dashboard Backend implementation Query AS02.2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Usage Analysis Dashboard Backend implementation Query AS02.3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Usage Analysis Dashboard Backend implementation Query AS02.4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Usage Analysis Dashboard Backend implementation Query AS02.5 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Usage Analysis Dashboard Backend implementation Query AS02.6 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Usage Analysis Dashboard Frontend implementation Bar graphs | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Usage Analysis Dashboard Frontend implementation Trend charts | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21
SP Decrement |  | 28.25 | 0 | 0 | 0.5 | 0.5 | 0.25 | 1 | 1 | 1 | 1 | 1 | 0.5 | 0.5 | 0 | 7.25
Total Change |  |  | 0 | 3.75 | 6.25 | 8.75 | 4 | 7.5 | 6 | 8.5 | 9 | 10 | 11.5 | 11.75 | 8.5
Daily Scrum Meeting
Day of Sprint | Who | What did you work on Yesterday? | 2: What are you working on today?; 5: Are You Blocked?
Day 1 | Albert | n/a | 2: n/a; 5: no
| Audrey | n/a | 2: email verification front end; 5: no
| Brad | n/a | 2: extending site map for new features; 5: no
| Devarsh | n/a | 2: working of recipe sharing site map; 5: no
| Jacob | n/a | 2: book selling site map; 5: no
| Joseph | n/a | 2: registration backend and error handling; 5: no
| Michael | n/a | 2: n/a; 5: no
| SzeMan | n/a | 2: n/a; 5: no
Day 2 | Albert | n/a | 2: n/a; 5: no
| Audrey | email verification front end | 2: email verrifcaiton tests; 5: no
| Brad | extending site map for new features | 2: addressing test parity for logging; 5: no
| Devarsh | n/a | 2: Review Recipe Sharing Test plan; 5: no
| Jacob | book selling site map | 2: grade calculator site map; 5: no
| Joseph | registration backend and error handling | 2: registration backend and error handling; 5: no
| Michael | n/a | 2: Address test parity (tests should pass when desired result happens) (Archiving); 5: no
| SzeMan | n/a | 2: n/a; 5: no
Day 3 | Albert | n/a | 2: Tech Approval: Jobs API; 5: no
| Audrey | email verrifcaiton tests | 2: Address test parity (tests should pass when desired result happens) (UM), email verification class; 5: no
| Brad | addressing test parity for logging | 2: logout behavior diagram; 5: no
| Devarsh | Review Recipe Sharing Test plan | 2: start working on User Access Control Behavior diagrams; 5: no
| Jacob | grade calculator site map | 2: book selling test plan; 5: no
| Joseph | registration backend and error handling | 2: registration backend and error handling; 5: no
| Michael | Address test parity (tests should pass when desired result happens) (Archiving) | 2: html and css tech approval; 5: no
| SzeMan | n/a | 2: event planing site map; 5: no
Day 4 | Albert | Tech Approval: Jobs API | 2: Tech Approval: Jobs API; 5: no
| Audrey | Address test parity (tests should pass when desired result happens) (UM), email verification class | 2: Login Behavior Diagram, login class, login backend; 5: no
| Brad | logout behavior diagram | 2: address test parity for logging; 5: no
| Devarsh | start working on User Access Control Behavior diagrams | 2: still working on UAC Behavior diagrams; 5: no
| Jacob | book selling test plan | 2: grade calculator test plan; 5: no
| Joseph | registration backend and error handling | 2: registration backend and error handling; 5: no
| Michael | html and css tech approval | 2: html tech approval; 5: no
| SzeMan | event planing site map | 2: event planing site map; 5: no
Day 5 | Albert | Tech Approval: Jobs API | 2: Tech Approval: Jobs API; 5: no
| Audrey | Login Behavior Diagram, login class, login backend | 2: Login Behavior Diagram, login class; 5: no
| Brad | address test parity for logging | 2: logout behavior diagram & classes; 5: no
| Devarsh | still working on UAC Behavior diagrams | 2: still working on UAC Behavior diagrams; 5: no
| Jacob | grade calculator test plan | 2: book selling test plan; 5: no
| Joseph | registration backend and error handling | 2: registration backend and error handling, review logout errors; 5: no
| Michael | html tech approval | 2: logout class diagram; 5: no
| SzeMan | event planing site map | 2: review test plan; 5: no
Day 6 | Albert | Tech Approval: Jobs API | 2: Tech Approval: Jobs API; 5: no
| Audrey | Login Behavior Diagram, login class | 2: n/a; 5: no
| Brad | logout behavior diagram & classes | 2: logging test parity; 5: no
| Devarsh | still working on UAC Behavior diagrams | 2: still working on UAC Behavior diagrams; 5: no
| Jacob | book selling test plan | 2: user management frontend; 5: no
| Joseph | registration backend and error handling, review logout errors | 2: registration backend and error handling, review logout errors; 5: no
| Michael | logout class diagram | 2: n/a; 5: no
| SzeMan | review test plan | 2: behavioral diagram; 5: no
Day 7 | Albert | Tech Approval: Jobs API | 2: Tech Approval: Jobs API; 5: no
| Audrey | n/a | 2: login backend, email verification; 5: no
| Brad | logging test parity | 2: logout behavior diagram; 5: no
| Devarsh | still working on UAC Behavior diagrams | 2: UAC Class/database diagram; 5: no
| Jacob | user management frontend | 2: user management frontend and check registration for errors; 5: no
| Joseph | registration backend and error handling, review logout errors | 2: registration backend; 5: no
| Michael | n/a | 2: logout class diagram; 5: no
| SzeMan | behavioral diagram | 2: behavioral diagram; 5: no
Day 8 | Albert | Tech Approval: Jobs API | 2: Tech Approval: Jobs API; 5: no
| Audrey | login backend, email verification | 2: login backend and class; 5: no
| Brad | logout behavior diagram | 2: addressed test parity for logging, logout behavior diagram; 5: no
| Devarsh | UAC Class/database diagram | 2: N/A; 5: no
| Jacob | user management frontend and check registration for errors | 2: user management frontend and check registration for errors; 5: no
| Joseph | registration backend | 2: registation backend and error handling; 5: no
| Michael | logout class diagram | 2: n/a; 5: no
| SzeMan | behavioral diagram | 2: behavioral diagram; 5: no
Day 9 | Albert | Tech Approval: Jobs API | 2: registration behavioral diagram; 5: no
| Audrey | login backend and class | 2: login backend and frontend; 5: no
| Brad | addressed test parity for logging | 2: logout behavior diagram; 5: no
| Devarsh | N/A | 2: still working on UAC Class/database diagram; 5: no
| Jacob | user management frontend and check registration for errors | 2: error handling login and registration; 5: no
| Joseph | registation backend and error handling | 2: registation backend and error handling; 5: no
| Michael | n/a | 2: logout class diagram; 5: no
| SzeMan | behavioral diagram | 2: Usage Analysis Dashboard database diagram; 5: no
Day 10 | Albert | registration behavioral diagram | 2: registration behavioral diagram; 5: no
| Audrey | login backend and frontend | 2: login in backend, class, email verificaiton; 5: no
| Brad | logout behavior diagram | 2: logout behavior diagram; 5: no
| Devarsh | still working on UAC Class/database diagram | 2: start working on UAC Test; 5: no
| Jacob | error handling login and registration | 2: user management frontend and review login for error handling; 5: no
| Joseph | registation backend and error handling | 2: registation backend and error handling; 5: no
| Michael | logout class diagram | 2: Address test parity (tests should pass when desired result happens) (Archiving); 5: no
| SzeMan | Usage Analysis Dashboard database diagram | 2: Usage Analysis Dashboard database diagram; 5: no
Day 11 | Albert | registration behavioral diagram | 2: registration class diagram; 5: no
| Audrey | login in backend, class, email verificaiton | 2: login in backend, frontend, tests, email verificaiton; 5: no
| Brad | logout behavior diagram | 2: logout behavior diagram; 5: no
| Devarsh | start working on UAC Test | 2: still working on UAC Test; 5: no
| Jacob | user management frontend and review login for error handling | 2: review login for error handling; 5: no
| Joseph | registation backend and error handling | 2: automated moderating test plan, registration backend and error handling, review logout; 5: no
| Michael | Address test parity (tests should pass when desired result happens) (Archiving) | 2: logout class diagram; 5: no
| SzeMan | Usage Analysis Dashboard database diagram | 2: Usage Analysis Dashboard database diagram; 5: no
Day 12 | Albert | registration class diagram | 2: registration class diagram; 5: no
| Audrey | login in backend, frontend, tests, email verificaiton | 2: login in backend, frontend, tests; 5: no
| Brad | logout behavior diagram | 2: login backend; 5: no
| Devarsh | still working on UAC Test | 2: still working on UAC Test; 5: no
| Jacob | review login for error handling | 2: review login for error handling; 5: no
| Joseph | automated moderating test plan, registration backend and error handling, review logout | 2: registration backend and error handling; 5: no
| Michael | logout class diagram | 2: Address test parity (tests should pass when desired result happens) (Archiving); 5: no
| SzeMan | Usage Analysis Dashboard database diagram | 2: n/a; 5: no

## Sprint 8
Sprint 8
| Start Date | 2022-01-25 |  | Day of Sprint | Actual Effort |  |  | Day of Sprint | Forecast | Actual
| End Date | 2022-02-05 |  | 0 | 110 |  |  | 0 | 110 | 110
| Sprint Length | 12 |  | 1 | 106.5 |  |  | 1 | 100.8333 | 106.5
| Team Size | 5 |  | 2 | 103.5 |  |  | 2 | 91.6667 | 103.5
| Team Capacity | 125 |  | 3 | 101 |  |  | 3 | 82.5 | 101
| Total Sprint SP | 110 |  | 4 | 100.5 |  |  | 4 | 73.3333 | 100.5
| SP/Day | 9.1667 |  | 5 | 97.5 |  |  | 5 | 64.1667 | 97.5
|  |  |  | 6 | 94.75 |  |  | 6 | 55 | 94.75
|  |  |  | 7 | 93 |  |  | 7 | 45.8333 | 93
|  |  |  | 8 | 90.5 |  |  | 8 | 36.6667 | 90.5
|  |  |  | 9 | 85.75 |  |  | 9 | 27.5 | 85.75
|  |  |  | 10 | 83.75 |  |  | 10 | 18.3333 | 83.75
|  |  |  | 11 | 78.75 |  |  | 11 | 9.1667 | 78.75
|  |  |  | 12 | 74.75 |  |  | 12 | 0 | 74.75
|  |  |  | t | w | t | f | s | s | m | t | w | t | f | s
Who | Tasks | Day of Sprint (hours worked)
|  |  | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
Albert |  |  | 7: 0; 8: 0; 9: 0; 10: 0; 11: 0; 12: 0
| Registration Behavioral Diagram | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Registrion Class Diagram | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0
| Registration Testing | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Tech Approval: Jobs API | 6 | 0 | 1 | 0 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0
SP Decrement |  |  | 0 | 0.5 | 0 | 1 | 0.5 | 0.5 | 1 | 1 | 1 | 0 | 0 | 0 | 0
Audrey
| Login Behavioral Diagram | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Login Class Diagram | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Login backend implementation | 4 | 0 | 0 | 2 | 1 | 0 | 1 | 1.5 | 1 | 0 | 0 | 0 | 0 | 0
| Login frontend implementation | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5 | 1 | 0 | 0 | 0 | 0 | 0
| Login Testing | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SP Decrement |  |  | 0 | 0 | 1 | 0.5 | 0 | 0.5 | 1 | 0 | 0 | 0 | 0 | 0 | 0
Brad
| Update project plan to account for code reviews | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0
| Logout Behavior Diagram | 11 | 0 | 2 | 1 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Logout backend implementation | 4 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0
| Logout frontend implementation | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Registration backend implementation | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Registration frontend implementation | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Logout Testing | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Update project plan | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1
SP Decrement |  |  | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0.25 | 0.25 | 0.25 | 0 | 1 | 1
Devarsh
| New feature for Devarsh | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0
| BRD for Recipe Sharing | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1
SP Decrement |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1
Jacob
| New feature for Jacob | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0
| BRD for GPA Calculator | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0
| BRD for Book Selling | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 1
SP Decrement |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1
Joseph
| Error Handling Behavior Diagram | 8 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Error Handling Class Diagram | 4 | 0 | 1 | 1 | 2 | 0 | 1 | 1.5 | 1 | 0 | 0 | 0 | 0 | 0
| Error Handling backend implementation | 3 | 0 | 0 | 0 | 1 | 0 | 0.5 | 0 | 0.5 | 1 | 0.5 | 0 | 0 | 0
| Error Handling frontend implementation | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Error Handling Testing | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| New feature for Joseph | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0
| BRD for Automated testing | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0
SP Decrement |  |  | 0 | 1 | 1 | 1 | 0 | 1 | 0.75 | 0.5 | 0.25 | 1.5 | 1 | 1 | 0
Michael
| Address test parity (tests should pass when desired result happens) | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Tech Approval: HTML | 4 | 0 | 2 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Tech Approval: CSS | 4 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Logout Class Diagram | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SP Decrement |  |  | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SzeMan
| New feature for SzeMan | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0
| BRD for Event Planning | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1
SP Decrement |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1
Total Change |  |  | 0 | 3.5 | 3 | 2.5 | 0.5 | 3 | 2.75 | 1.75 | 2.5 | 4.75 | 2 | 5 | 4
Daily Scrum Meeting
Day of Sprint | Who | What did you work on Yesterday? | 2: What are you working on today?; 5: Are You Blocked?
Day 1 | Albert | n/a | 2: api jobs tech approval; 5: no
| Audrey | n/a | 2: n/a; 5: no
| Brad | n/a | 2: logout behvioral diagram; 5: no
| Devarsh | n/a | 2: n/a; 5: no
| Jacob | n/a | 2: n/a; 5: no
| Joseph | n/a | 2: error handling behavioral and class diagram; 5: no
| Michael | n/a | 2: html tech approval; 5: no
| SzeMan | n/a | 2: n/a; 5: no
Day 2 | Albert | api jobs tech approval | 2: n/a; 5: no
| Audrey | n/a | 2: login backend; 5: no
| Brad | logout behvioral diagram | 2: logout behavioral and backend; 5: no
| Devarsh | n/a | 2: n/a; 5: no
| Jacob | n/a | 2: n/a; 5: no
| Joseph | error handling behavioral and class diagram | 2: error handling behavioral and class diagram; 5: no
| Michael | html tech approval | 2: html and css tech approval; 5: no
| SzeMan | n/a | 2: n/a; 5: no
Day 3 | Albert | n/a | 2: Tech Approval: Jobs API; 5: no
| Audrey | login backend | 2: login backend and tests; 5: no
| Brad | logout behavioral and backend | 2: logout behavior diagram and backend; 5: no
| Devarsh | n/a | 2: n/a; 5: no
| Jacob | n/a | 2: n/a; 5: no
| Joseph | error handling behavioral and class diagram | 2: error handling behavioral and class diagram; 5: no
| Michael | html and css tech approval | 2: html and css tech approval; 5: no
| SzeMan | n/a | 2: n/a; 5: no
Day 4 | Albert | Tech Approval: Jobs API | 2: Tech Approval: Jobs API; 5: no
| Audrey | login backend and tests | 2: n/a; 5: no
| Brad | logout behavior diagram and backend | 2: n/a; 5: no
| Devarsh | n/a | 2: n/a; 5: no
| Jacob | n/a | 2: n/a; 5: no
| Joseph | error handling behavioral and class diagram | 2: n/a; 5: no
| Michael | html and css tech approval | 2: n/a; 5: no
| SzeMan | n/a | 2: n/a; 5: no
Day 5 | Albert | Tech Approval: Jobs API | 2: Tech Approval: Jobs API; 5: no
| Audrey | n/a | 2: Login backend login tests; 5: no
| Brad | n/a | 2: n/a; 5: no
| Devarsh | n/a | 2: n/a; 5: no
| Jacob | n/a | 2: n/a; 5: no
| Joseph | n/a | 2: error handling class and backend; 5: no
| Michael | n/a | 2: html and css tech approval; 5: no
| SzeMan | n/a | 2: n/a; 5: no
Day 6 | Albert | Tech Approval: Jobs API | 2: Tech Approval: Jobs API; 5: no
| Audrey | Login backend login tests | 2: login backend and frontend; 5: no
| Brad | n/a | 2: logout backend; 5: no
| Devarsh | n/a | 2: n/a; 5: no
| Jacob | n/a | 2: n/a; 5: no
| Joseph | error handling class and backend | 2: error handling class; 5: no
| Michael | html and css tech approval | 2: n/a; 5: no
| SzeMan | n/a | 2: n/a; 5: no
Day 7 | Albert | Tech Approval: Jobs API | bar: 5
| Audrey | login backend and frontend | 2: login backend, frontend; 5: no
| Brad | logout backend | 2: update project plan; 5: no
| Devarsh | n/a | 2: new feature devarsh; 5: no
| Jacob | n/a | 2: new feature jacob; 5: no
| Joseph | error handling class | 2: error handling class, backend, and new feature; 5: no
| Michael | n/a | 2: n/a; 5: no
| SzeMan | n/a | 2: new feature szeman; 5: no
Day 8 | Albert |  | 5: yes
| Audrey | login backend, frontend | 2: n/a; 5: yes
| Brad | update project plan | 2: update project plan; 5: yes
| Devarsh | new feature devarsh | 2: new feature devarsh; 5: no
| Jacob | new feature jacob | 2: new feature jacob; 5: no
| Joseph | error handling class, backend, and new feature | 2: error handling class, backend, and new feature; 5: yes
| Michael | n/a | 2: n/a; 5: yes
| SzeMan | new feature szeman | 2: new feature szeman; 5: no
Day 9 | Albert |  | 5: yes
| Audrey | n/a | 2: n/a; 5: yes
| Brad | update project plan | 2: update project plan; 5: yes
| Devarsh | new feature devarsh | 2: new feature devarsh; 5: no
| Jacob | new feature jacob | 2: brd for new features; 5: no
| Joseph | error handling class, backend, and new feature | 2: error handling class, backend, and new feature; 5: yes
| Michael | n/a | 2: n/a; 5: yes
| SzeMan | new feature szeman | 2: new feature szeman; 5: no
Day 10 | Albert |  | 5: yes
| Audrey | n/a | 2: n/a; 5: yes
| Brad | update project plan | 2: n/a; 5: yes
| Devarsh | new feature devarsh | 2: n/a; 5: no
| Jacob | brd for new features | 2: brd; 5: no
| Joseph | error handling class, backend, and new feature | 2: brd; 5: yes
| Michael | n/a | 2: n/a; 5: yes
| SzeMan | new feature szeman | 2: n/a; 5: no
Day 11 | Albert |  | 5: yes
| Audrey | n/a | 2: n/a; 5: yes
| Brad | n/a | 2: update project plan; 5: yes
| Devarsh | n/a | 2: brd; 5: no
| Jacob | brd | 2: brd; 5: no
| Joseph | brd | 2: brd; 5: yes
| Michael | n/a | 2: n/a; 5: yes
| SzeMan | n/a | 2: brd; 5: no
Day 12 | Albert |  | 5: yes
| Audrey | n/a | 2: n/a; 5: yes
| Brad | update project plan | 2: update project plan; 5: yes
| Devarsh | brd | 2: brd; 5: no
| Jacob | brd | 2: brd; 5: no
| Joseph | brd | 2: brd; 5: yes
| Michael | n/a | 2: n/a; 5: yes
| SzeMan | brd | 2: brd; 5: no

## Sprint 7
Sprint 7
| Start Date | 2022-01-11 |  | Day of Sprint | Actual Effort |  |  | Day of Sprint | Forecast | Actual
| End Date | 2022-01-22 |  | 0 | 148 |  |  | 0 | 148 | 148
| Sprint Length | 12 |  | 1 | 148 |  |  | 1 | 135.6667 | 148
| Team Size | 5 |  | 2 | 142 |  |  | 2 | 123.3333 | 142
| Team Capacity | 160 |  | 3 | 138 |  |  | 3 | 111 | 138
| Total Sprint SP | 148 |  | 4 | 130 |  |  | 4 | 98.6667 | 130
| SP/Day | 12.3333 |  | 5 | 127 |  |  | 5 | 86.3333 | 127
|  |  |  | 6 | 125 |  |  | 6 | 74 | 125
|  |  |  | 7 | 121 |  |  | 7 | 61.6667 | 121
|  |  |  | 8 | 115.5 |  |  | 8 | 49.3333 | 115.5
|  |  |  | 9 | 110.5 |  |  | 9 | 37 | 110.5
|  |  |  | 10 | 109.5 |  |  | 10 | 24.6667 | 109.5
|  |  |  | 11 | 108.5 |  |  | 11 | 12.3333 | 108.5
|  |  |  | 12 | 103 |  |  | 12 | 0 | 103
|  |  |  | t | w | t | f | s | s | m | t | w | t | f | s
Who | Tasks | Day of Sprint (hours worked)
|  |  | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
Albert
| Registration Behavioral Diagram | 12 | 0 | 0 | 2 | 2 | 3 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 1
| Registrion Class Diagram | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0
| Registration backend implementation | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Registration frontend implementation | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Registration Testing | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SP Decrement |  |  | 0 | 0 | 2 | 2 | 3 | 1 | 1 | 1 | 0.5 | 1 | 0 | 0 | 0.5 | 12
Audrey
| Login Behavioral Diagram | 12 | 0 | 0 | 1.5 | 1.5 | 1.5 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 2
| Login Class Diagram | 8 | 0 | 0 | 0.5 | 0.5 | 0.5 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 2
| Login backend implementation | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 0 | 0
| Login frontend implementation | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Login Testing | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SP Decrement |  |  | 0 | 0 | 4 | 2 | 3 | 0 | 0 | 2 | 3 | 2 | 0 | 0 | 2 | 18
Brad
| Address git repo: clean up files | 2 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0
| Logout Behavior Diagram | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 4
| Logout backend implementation | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Logout frontend implementation | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Logout Testing | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SP Decrement |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 3
Joseph
| Error Handling Behavior Diagram | 12 | 0 | 1 | 0.5 | 0.5 | 1 | 1 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1
| Error Handling Class Diagram | 8 | 0 | 0 | 0 | 0 | 0 | 1 | 1.5 | 0 | 1 | 1.5 | 0 | 0.5 | 2 |  | 4
| Error Handling backend implementation | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Error Handling frontend implementation | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Error Handling Testing | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SP Decrement |  |  | 0 | 0 | 0 | 0 | 1 | 2 | 1 | 0 | 1 | 1 | 0 | 0 | 2 | 8
Michael
| Address test parity (tests should pass when desired result happens) | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Tech Approval: HTML | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0
| Tech Approval: CSS | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0
| Logout Class Diagram | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SP Decrement |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 4
Total Change |  |  | 0 | 0 | 6 | 4 | 8 | 3 | 2 | 4 | 5.5 | 5 | 1 | 1 | 5.5
Daily Scrum Meeting
Day of Sprint | Who | What did you work on Yesterday? | 2: What are you working on today?; 5: Are You Blocked?
Day 1 | Albert | n/a | 2: n/a; 5: no
| Audrey | n/a | 2: n/a; 5: no
| Brad | n/a | 2: Address git repo: clean up files; 5: no
| Joseph | n/a | 2: n/a; 5: no
| Michael | n/a | 2: n/a; 5: no
Day 2 | Albert | n/a | 2: Registration Behavioral Diagram; 5: no
| Audrey | n/a | 2: login behavioral diagram and class diagram; 5: no
| Brad | None | 2: Address git repo: clean up files; 5: no
| Joseph | n/a | 2: error handling behavior diagram; 5: no
| Michael | n/a | 2: n/a; 5: no
Day 3 | Albert | Registration Behavioral Diagram | 2: Registration Behavioral Diagram; 5: no
| Audrey | login behavioral diagram and class diagram | 2: login behavioral diagram and class diagram; 5: no
| Brad | None | 2: Address git repo: clean up files; 5: no
| Joseph | error handling behavior diagram | 2: error handling behavior diagram; 5: no
| Michael | n/a | 2: n/a; 5: no
Day 4 | Albert | Registration Behavioral Diagram | 2: Registration Behavioral Diagram; 5: no
| Audrey | login behavioral diagram and class diagram | 2: login behavioral diagram and class diagram; 5: no
| Brad | None | 2: Address git repo: clean up files; 5: no
| Joseph | error handling behavior diagram | 2: error handling behavior diagram; 5: no
| Michael | n/a | 2: n/a; 5: no
Day 5 | Albert | Registration Behavioral Diagram | 2: n/a; 5: no
| Audrey | login behavioral diagram and class diagram | 2: n/a; 5: no
| Brad | Address git repo: clean up files | 2: n/a; 5: no
| Joseph | error handling behavior diagram | 2: error handling class diagram; 5: no
| Michael | n/a | 2: n/a; 5: no
Day 6 | Albert | n/a | 2: n/a; 5: no
| Audrey | n/a | 2: n/a; 5: no
| Brad | n/a | 2: n/a; 5: no
| Joseph | error handling class diagram | 2: n/a; 5: no
| Michael | n/a | 2: n/a; 5: no
Day 7 | Albert | n/a | 2: n/a; 5: no
| Audrey | n/a | 2: login behavioral diagram and class diagram; 5: no
| Brad | n/a | 2: n/a; 5: no
| Joseph | n/a | 2: error handling class diagram; 5: no
| Michael | n/a | 2: HTML tech approval; 5: no
Day 8 | Albert | n/a | 2: Registration Behavioral Diagram; 5: no
| Audrey | login behavioral diagram and class diagram | 2: login behavioral diagram and class diagram; 5: no
| Brad | n/a | 2: research into web sessions and asp.net startup scripts; 5: no
| Joseph | error handling class diagram | 2: n/a; 5: no
| Michael | HTML tech approval | 2: n/a; 5: no
Day 9 | Albert | Registration Behavioral Diagram | 2: Registration Behavioral Diagram; 5: no
| Audrey | login behavioral diagram and class diagram | 2: login behavioral, class diagram and beckend; 5: no
| Brad | research into web sessions and asp.net startup scripts | 2: research into asp.net sessions and startup scripts; 5: no
| Joseph | n/a | 2: error handling class diagram; 5: no
| Michael | n/a | 2: HTML tech approval; 5: no
Day 10 | Albert | Registration Behavioral Diagram | 2: Registrion Class Diagram; 5: no
| Audrey | login behavioral, class diagram and beckend | 2: n/a; 5: no
| Brad | research into asp.net sessions and startup scripts | 2: n/a; 5: no
| Joseph | error handling class diagram | 2: error handling class diagram; 5: no
| Michael | HTML tech approval | 2: CSS tech approval; 5: no
Day 11 | Albert | Registrion Class Diagram | 2: Registrion Class Diagram; 5: no
| Audrey | n/a | 2: n/a; 5: no
| Brad | n/a | 2: n/a; 5: no
| Joseph | error handling class diagram | 2: error handling backend; 5: no
| Michael | CSS tech approval | 2: css tech approval; 5: no
Day 12 | Albert | Registrion Class Diagram | 2: Registrion Class Diagram; 5: no
| Audrey | n/a | 2: login behovioral and class diagram; 5: no
| Brad | n/a | 2: logout behavioral diagram; 5: no
| Joseph | error handling backend | 2: error handling class diagram; 5: no
| Michael | css tech approval | 2: n/a; 5: no

## Albert
Sprint 0 | proposal | [6 empty] | Sprint | SP | Hours Worked | Over/Under
| Start Date | 2021-09-22 |  | Day of Sprint | Forecast | Actual Effort | Hours Worked | 0 | 8 | 13 | 5
| End Date | 2021-09-27 |  | 0 | 8 | 8 | 0 | 1 | 10 | 24 | 14
| Sprint Length | 6 |  | 1 | 6.67 | 7 | 2 | 2 | 6 | 9 | 3
|  |  |  | 2 | 5.34 | 7 | 0 | 3 | 14 | 24 | 10
| Capacity | 10 |  | 3 | 4.01 | 7 | 1 | 4 | 12 | 6.5 | -5.5
| Total Sprint SP | 8 |  | 4 | 2.68 | 4 | 4 | 5 | 18.5 | 15 | -3.5
| SP/Day | 1.33 |  | 5 | 1.35 | 2.5 | 3 | 6 | 20 | 38.5 | 18.5
|  |  |  | 6 | 0 | 0 | 3 | 7 | 32 | 15 | -17
[6 empty] | Total = | 13 | 8 | 15 | 17 | 2
[6 empty] | Over effort = | 5 | 9 | 19.5 | 24 | 4.5
[8 empty] | 10 | 34 | 0 | -34
11
12
13
Sprint 1 | milestone 1 | [6 empty] | 14
| Start Date | 2021-09-29 |  | Day of Sprint | Forecast | Actual Effort | Hours Worked
| End Date | 2021-10-05 |  | 0 | 10 | 10 | 0
| Sprint Length | 7 |  | 1 | 8.5714 | 9 | 3
|  |  |  | 2 | 7.1429 | 9 | 0
| Capacity | 16 |  | 3 | 5.7143 | 7 | 4
| Total Sprint SP | 10 |  | 4 | 4.2857 | 6 | 3
| SP/Day | 1.4286 |  | 5 | 2.8571 | 4 | 5
|  |  |  | 6 | 1.4286 | 3 | 3
|  |  |  | 7 | 0 | 0 | 6
[6 empty] | Total = | 24
[6 empty] | Over effort = | 14
Sprint 2 | test plan
| Start Date | 2021-10-13 |  | Day of Sprint | Forecast | Actual Effort | Hours Worked
| End Date | 2021-10-18 |  | 0 | 6 | 6 | 0
| Sprint Length | 6 |  | 1 | 5 | 6 | 0
|  |  |  | 2 | 4 | 6 | 0
| Capacity | 8 |  | 3 | 3 | 5 | 1
| Total Sprint SP | 6 |  | 4 | 2 | 4 | 3
| SP/Day | 1 |  | 5 | 1 | 2 | 3
|  |  |  | 6 | 0 | 0 | 3
[6 empty] | Total = | 10
[6 empty] | Over effort = | 4
Sprint 3 | milestone 2
| Start Date | 2021-10-21 |  | Day of Sprint | Forecast | Actual Effort | Hours Worked
| End Date | 2021-10-26 |  | 0 | 14 | 14 | 0
| Sprint Length | 6 |  | 1 | 11.6667 | 14 | 0
|  |  |  | 2 | 9.3333 | 13 | 2
| Capacity | 18 |  | 3 | 7 | 12 | 3
| Total Sprint SP | 14 |  | 4 | 4.6667 | 8 | 8
| SP/Day | 2.3333 |  | 5 | 2.3333 | 4 | 6
|  |  |  | 6 | 0 | 0 | 5
[6 empty] | Total = | 24
[6 empty] | Over effort = | 10
Sprint 4 | UM, Logging | on older docs | and LL
| Start Date | 2021-11-05 |  | Day of Sprint | Forecast | Actual Effort | Hours Worked
| End Date | 2021-11-12 |  | 0 | 12 | 12 | 0
| Sprint Length | 8 |  | 1 | 10.5 | 11.5 | 1
|  |  |  | 2 | 9 | 11.5 | 0
| Capacity | 16 |  | 3 | 7.5 | 11.5 | 0
| Total Sprint SP | 12 |  | 4 | 6 | 10.5 | 2
| SP/Day | 1.5 |  | 5 | 4.5 | 10.5 | 0
|  |  |  | 6 | 3 | 9 | 1.5
|  |  |  | 7 | 1.5 | 8.5 | 1
|  |  |  | 8 | 0 | 8 | 1
[6 empty] | Total = | 6.5
[6 empty] | Over effort = | -5.5
Sprint 5 | sprint 4 + | core comp
| Start Date | 2021-11-14 |  | Day of Sprint | Forecast | Actual Effort | Hours Worked
| End Date | 2021-11-19 |  | 0 | 18.5 | 18.5 | 0
| Sprint Length | 10 |  | 1 | 16.65 | 17 | 2
|  |  |  | 2 | 14.8 | 15.75 | 2
| Capacity | 20 |  | 3 | 12.95 | 14.5 | 2
| Total Sprint SP | 18.5 |  | 4 | 11.1 | 14.5 | 0
| SP/Day | 1.85 |  | 5 | 9.25 | 12.5 | 2
|  |  |  | 6 | 7.4 | 10.5 | 2
|  |  |  | 7 | 5.55 | 8.5 | 2
|  |  |  | 8 | 3.7 | 8 | 1
|  |  |  | 9 | 1.85 | 7.5 | 1
|  |  |  | 10 | 0 | 6 | 1
[6 empty] | Total = | 15
[6 empty] | Over effort = | -3.5
Sprint 6 | sprint 5 + | codes
| Start Date | 2021-11-29 |  | Day of Sprint | Forecast | Actual Effort | Hours Worked
| End Date | 2021-12-14 |  | 0 | 20 | 20 | 0
| Sprint Length | 16 |  | 1 | 18.75 | 20 | 1
|  |  |  | 2 | 17.5 | 19.5 | 1
| Capacity | 22 |  | 3 | 16.25 | 18.5 | 1.5
| Total Sprint SP | 20 |  | 4 | 15 | 17.5 | 0
| SP/Day | 1.25 |  | 5 | 13.75 | 17.5 | 0
|  |  |  | 6 | 12.5 | 17.5 | 0
|  |  |  | 7 | 11.25 | 17.5 | 0
|  |  |  | 8 | 10 | 17 | 1
|  |  |  | 9 | 8.75 | 15.5 | 5
|  |  |  | 10 | 7.5 | 14.5 | 2
|  |  |  | 11 | 6.25 | 14 | 1
|  |  |  | 12 | 5 | 11 | 5
|  |  |  | 13 | 3.75 | 9 | 5
|  |  |  | 14 | 2.5 | 6 | 5
|  |  |  | 15 | 1.25 | 3 | 5
|  |  |  | 16 | 0 | 0 | 6
[6 empty] | Total = | 38.5
[6 empty] | Over effort = | 18.5
Sprint 7 | 1st half core
| Start Date | 2022-01-11 |  | Day of Sprint | Forecast | Actual Effort | Hours Worked
| End Date | 2022-01-22 |  | 0 | 32 | 32 | 0
| Sprint Length | 12 |  | 1 | 29.3333 | 32 | 0
|  |  |  | 2 | 26.6667 | 30 | 3
| Capacity | 33 |  | 3 | 24 | 28 | 3
| Total Sprint SP | 32 |  | 4 | 21.3333 | 25 | 3
| SP/Day | 2.6667 |  | 5 | 18.6667 | 24 | 1
|  |  |  | 6 | 16 | 23 | 1
|  |  |  | 7 | 13.3333 | 22 | 1
|  |  |  | 8 | 10.6667 | 21.5 | 1
|  |  |  | 9 | 8 | 20.5 | 1
|  |  |  | 10 | 5.3333 | 20.5 | 0
|  |  |  | 11 | 2.6667 | 20.5 | 0
|  |  |  | 12 | 0 | 20 | 1
[6 empty] | Total = | 15
[6 empty] | Over effort = | -17
Sprint 8 | 1st half core
| Start Date | 2022-01-25 |  | Day of Sprint | Forecast | Actual Effort | Hours Worked
| End Date | 2022-02-05 |  | 0 | 15 | 15 | 0
| Sprint Length | 12 |  | 1 | 13.75 | 14.5 | 1
|  |  |  | 2 | 12.5 | 14.5 | 0
| Capacity | 16 |  | 3 | 11.25 | 13.5 | 3
| Total Sprint SP | 15 |  | 4 | 10 | 13 | 3
| SP/Day | 1.25 |  | 5 | 8.75 | 12.5 | 3
|  |  |  | 6 | 7.5 | 11.5 | 3
|  |  |  | 7 | 6.25 | 10.5 | 2
|  |  |  | 8 | 5 | 9.5 | 2
|  |  |  | 9 | 3.75 | 9.5 | 0
|  |  |  | 10 | 2.5 | 9.5 | 0
|  |  |  | 11 | 1.25 | 9.5 | 0
|  |  |  | 12 | 0 | 9.5 | 0
[6 empty] | Total = | 17
[6 empty] | Over effort = | 2
Sprint 9 | 1st half core
| Start Date | 2022-02-08 |  | Day of Sprint | Forecast | Actual Effort | Hours Worked
| End Date | 2022-02-19 |  | 0 | 19.5 | 19.5 | 0
| Sprint Length | 12 |  | 1 | 17.875 | 19.5 | 0
|  |  |  | 2 | 16.25 | 19 | 2
| Capacity | 20 |  | 3 | 14.625 | 18.5 | 3
| Total Sprint SP | 19.5 |  | 4 | 13 | 18 | 3
| SP/Day | 1.625 |  | 5 | 11.375 | 17.5 | 2
|  |  |  | 6 | 9.75 | 17 | 2
|  |  |  | 7 | 8.125 | 16.5 | 2
|  |  |  | 8 | 6.5 | 16 | 2
|  |  |  | 9 | 4.875 | 15 | 2
|  |  |  | 10 | 3.25 | 14 | 2
|  |  |  | 11 | 1.625 | 13 | 2
|  |  |  | 12 | 0 | 12 | 2
[6 empty] | Total = | 24
[6 empty] | Over effort = | 4.5
Sprint 10 | team code review feature
| Start Date | 2022-02-22 |  | Day of Sprint | Forecast | Actual Effort | Hours Worked
| End Date | 2022-03-05 |  | 0 | 34 | 34 | 0
| Sprint Length | 12 |  | 1 | 31.1667
|  |  |  | 2 | 28.3333
| Capacity | 35 |  | 3 | 25.5
| Total Sprint SP | 34 |  | 4 | 22.6667
| SP/Day | 2.8333 |  | 5 | 19.8333
|  |  |  | 6 | 17
|  |  |  | 7 | 14.1667
|  |  |  | 8 | 11.3333
|  |  |  | 9 | 8.5
|  |  |  | 10 | 5.6667
|  |  |  | 11 | 2.8333
|  |  |  | 12 | 0
[6 empty] | Total = | 0
[6 empty] | Over effort = | -34

## Audrey
Sprint 0 | proposal | [6 empty] | Sprint | SP | Hours Worked | Over/Under
| Start Date | 2021-09-22 |  | Day of Sprint | Forecast | Actual Effort | Hours Worked | 0 | 4 | 16 | 12
| End Date | 2021-09-27 |  | 0 | 4 | 4 | 0 | 1 | 12 | 27 | 15
| Sprint Length | 6 |  | 1 | 3.33 | 3 | 1 | 2 | 6 | 11 | 5
|  |  |  | 2 | 2.66 | 3 | 1 | 3 | 14 | 20 | 6
| Capacity | 10 |  | 3 | 1.99 | 1 | 4 | 4 | 14 | 11.5 | -2.5
| Total Sprint SP | 4 |  | 4 | 1.32 | 1 | 1 | 5 | 19 | 17.5 | -1.5
| SP/Day | 0.67 |  | 5 | 0.65 | 0.5 | 4 | 6 | 20 | 40.75 | 20.75
|  |  |  | 6 | 0 | 0 | 5 | 7 | 32 | 16 | -16
[6 empty] | Total = | 16 | 8 | 11 | 11 | 0
[6 empty] | Over Effort = | 12 | 9 | 26 | 30 | 4
[8 empty] | 10 | 31 | 0 | -31
11
12
13
Sprint 1 | milestone 1 | [6 empty] | 14
| Start Date | 2021-09-29 |  | Day of Sprint | Forecast | Actual Effort | Hours Worked
| End Date | 2021-10-05 |  | 0 | 12 | 12 | 0
| Sprint Length | 7 |  | 1 | 10.2857 | 11 | 2
|  |  |  | 2 | 8.5714 | 11 | 0
| Capacity | 15 |  | 3 | 6.8571 | 9 | 4
| Total Sprint SP | 12 |  | 4 | 5.1429 | 8 | 3
| SP/Day | 1.7143 |  | 5 | 3.4286 | 5 | 6
|  |  |  | 6 | 1.7143 | 2 | 6
|  |  |  | 7 | 0 | 0 | 6
[6 empty] | Total = | 27
[6 empty] | Over Effort = | 15
Sprint 2 | test plan
| Start Date | 2021-10-13 |  | Day of Sprint | Forecast | Actual Effort | Hours Worked
| End Date | 2021-10-18 |  | 0 | 6 | 6 | 0
| Sprint Length | 6 |  | 1 | 5 | 6 | 0
|  |  |  | 2 | 4 | 6 | 0
| Capacity | 8 |  | 3 | 3 | 3 | 4
| Total Sprint SP | 6 |  | 4 | 2 | 2 | 3
| SP/Day | 1 |  | 5 | 1 | 1 | 2
|  |  |  | 6 | 0 | 0 | 2
[6 empty] | Total = | 11
[6 empty] | Over Effort = | 5
Sprint 3 | project plan | network diagram
| Start Date | 2021-10-21 |  | Day of Sprint | Forecast | Actual Effort | Hours Worked
| End Date | 2021-10-26 |  | 0 | 14 | 14 | 0
| Sprint Length | 6 |  | 1 | 11.6667 | 14 | 0
|  |  |  | 2 | 9.3333 | 13 | 2
| Capacity | 18 |  | 3 | 7 | 11 | 2.5
| Total Sprint SP | 14 |  | 4 | 4.6667 | 7 | 4
| SP/Day | 2.3333 |  | 5 | 2.3333 | 4 | 3.5
|  |  |  | 6 | 0 | 0 | 8
[6 empty] | Total = | 20
[6 empty] | Over Effort = | 6
Sprint 4 | UM, Logging | on older docs | and LL
| Start Date | 2021-11-05 |  | Day of Sprint | Forecast | Actual Effort | Hours Worked
| End Date | 2021-11-12 |  | 0 | 14 | 14 | 0
| Sprint Length | 8 |  | 1 | 12.25 | 13.5 | 1
|  |  |  | 2 | 10.5 | 13.5 | 0
| Capacity | 16 |  | 3 | 8.75 | 13.5 | 0
| Total Sprint SP | 14 |  | 4 | 7 | 13 | 1.5
| SP/Day | 1.75 |  | 5 | 5.25 | 13 | 0
|  |  |  | 6 | 3.5 | 12 | 2
|  |  |  | 7 | 1.75 | 10.5 | 3
|  |  |  | 8 | 0 | 7 | 4
[6 empty] | Total = | 11.5
[6 empty] | Over effort = | -2.5
Sprint 5 | sprint 4 + | core comp
| Start Date | 2021-11-14 |  | Day of Sprint | Forecast | Actual Effort | Hours Worked
| End Date | 2021-11-19 |  | 0 | 19 | 19 | 0
| Sprint Length | 10 |  | 1 | 17.1 | 18.5 | 1.5
|  |  |  | 2 | 15.2 | 17.5 | 2
| Capacity | 20 |  | 3 | 13.3 | 15 | 2
| Total Sprint SP | 19 |  | 4 | 11.4 | 15 | 0
| SP/Day | 1.9 |  | 5 | 9.5 | 15 | 0
|  |  |  | 6 | 7.6 | 14 | 2
|  |  |  | 7 | 5.7 | 13 | 2
|  |  |  | 8 | 3.8 | 13 | 0
|  |  |  | 9 | 1.9 | 12 | 2.5
|  |  |  | 10 | 0 | 6 | 5.5
[6 empty] | Total = | 17.5
[6 empty] | Over effort = | -1.5
Sprint 6 | sprint 5 + | codes
| Start Date | 2021-11-29 |  | Day of Sprint | Forecast | Actual Effort | Hours Worked
| End Date | 2021-12-14 |  | 0 | 20 | 20 | 0
| Sprint Length | 16 |  | 1 | 18.75 | 19 | 2
|  |  |  | 2 | 17.5 | 19 | 0
| Capacity | 22 |  | 3 | 16.25 | 18.75 | 2
| Total Sprint SP | 20 |  | 4 | 15 | 18.5 | 2
| SP/Day | 1.25 |  | 5 | 13.75 | 18.5 | 0
|  |  |  | 6 | 12.5 | 18.5 | 0
|  |  |  | 7 | 11.25 | 18.5 | 0
|  |  |  | 8 | 10 | 18 | 5
|  |  |  | 9 | 8.75 | 16 | 6
|  |  |  | 10 | 7.5 | 12 | 3
|  |  |  | 11 | 6.25 | 11.5 | 2
|  |  |  | 12 | 5 | 10 | 1
|  |  |  | 13 | 3.75 | 9 | 5
|  |  |  | 14 | 2.5 | 7 | 3.25
|  |  |  | 15 | 1.25 | 5.5 | 4
|  |  |  | 16 | 0 | 0 | 5.5
[6 empty] | Total = | 40.75
[6 empty] | Over effort = | 20.75
Sprint 7 | 1st half core
| Start Date | 2022-01-11 |  | Day of Sprint | Forecast | Actual Effort | Hours Worked
| End Date | 2022-01-22 |  | 0 | 32 | 32 | 0
| Sprint Length | 12 |  | 1 | 29.3333 | 32 | 0
|  |  |  | 2 | 26.6667 | 28 | 2
| Capacity | 33 |  | 3 | 24 | 26 | 2
| Total Sprint SP | 32 |  | 4 | 21.3333 | 23 | 2
| SP/Day | 2.6667 |  | 5 | 18.6667 | 23 | 0
|  |  |  | 6 | 16 | 23 | 0
|  |  |  | 7 | 13.3333 | 21 | 2
|  |  |  | 8 | 10.6667 | 18 | 2
|  |  |  | 9 | 8 | 16 | 2
|  |  |  | 10 | 5.3333 | 16 | 0
|  |  |  | 11 | 2.6667 | 16 | 0
|  |  |  | 12 | 0 | 14 | 4
[6 empty] | Total = | 16
[6 empty] | Over effort = | -16
Sprint 8 | 1st half core
| Start Date | 2022-01-25 |  | Day of Sprint | Forecast | Actual Effort | Hours Worked
| End Date | 2022-02-05 |  | 0 | 11 | 11 | 0
| Sprint Length | 12 |  | 1 | 10.0833 | 11 | 0
|  |  |  | 2 | 9.1667 | 10 | 2
| Capacity | 12 |  | 3 | 8.25 | 9.5 | 2
| Total Sprint SP | 11 |  | 4 | 7.3333 | 9.5 | 0
| SP/Day | 0.91667 |  | 5 | 6.4167 | 9 | 2
|  |  |  | 6 | 5.5 | 8 | 3
|  |  |  | 7 | 4.5833 | 8 | 2
|  |  |  | 8 | 3.6667 | 8 | 0
|  |  |  | 9 | 2.75 | 8 | 0
|  |  |  | 10 | 1.8333 | 8 | 0
|  |  |  | 11 | 0.91667 | 8 | 0
|  |  |  | 12 | 0 | 8 | 0
[6 empty] | Total = | 11
[6 empty] | Over effort = | 0
Sprint 9 | 1st half core
| Start Date | 2022-02-08 |  | Day of Sprint | Forecast | Actual Effort | Hours Worked
| End Date | 2022-02-19 |  | 0 | 26 | 26 | 0
| Sprint Length | 12 |  | 1 | 23.8333 | 25 | 1
|  |  |  | 2 | 21.6667 | 24 | 2
| Capacity | 27 |  | 3 | 19.5 | 22 | 2
| Total Sprint SP | 26 |  | 4 | 17.3333 | 21.5 | 2
| SP/Day | 2.1667 |  | 5 | 15.1667 | 20 | 2
|  |  |  | 6 | 13 | 20 | 0
|  |  |  | 7 | 10.8333 | 19 | 1.5
|  |  |  | 8 | 8.6667 | 17.5 | 1.5
|  |  |  | 9 | 6.5 | 16 | 3
|  |  |  | 10 | 4.3333 | 15 | 2
|  |  |  | 11 | 2.1667 | 12 | 6
|  |  |  | 12 | 0 | 9 | 7
[6 empty] | Total = | 30
[6 empty] | Over effort = | 4
Sprint 10 | team code review feature
| Start Date | 2022-02-22 |  | Day of Sprint | Forecast | Actual Effort | Hours Worked
| End Date | 2022-03-05 |  | 0 | 31 | 31 | 0
| Sprint Length | 12 |  | 1 | 28.4167
|  |  |  | 2 | 25.8333
| Capacity | 35 |  | 3 | 23.25
| Total Sprint SP | 31 |  | 4 | 20.6667
| SP/Day | 2.5833 |  | 5 | 18.0833
|  |  |  | 6 | 15.5
|  |  |  | 7 | 12.9167
|  |  |  | 8 | 10.3333
|  |  |  | 9 | 7.75
|  |  |  | 10 | 5.1667
|  |  |  | 11 | 2.5833
|  |  |  | 12 | 0
[6 empty] | Total = | 0
[6 empty] | Over effort = | -31

## Brad
Sprint 0 | proposal | [6 empty] | Sprint | SP | Hours Worked | Over/Under
| Start Date | 2021-09-22 |  | Day of Sprint | Forecast | Actual Effort | Hours Worked | 0 | 9 | 20 | 11
| End Date | 2021-09-27 |  | 0 | 9 | 9 | 0 | 1 | 18.5 | 33 | 14.5
| Sprint Length | 6 |  | 1 | 7.5 | 8 | 2 | 2 | 6 | 5 | -1
|  |  |  | 2 | 6 | 8 | 0 | 3 | 14 | 16 | 2
| Capacity | 10 |  | 3 | 4.5 | 5 | 6 | 4 | 14 | 12.5 | -1.5
| Total Sprint SP | 9 |  | 4 | 3 | 5 | 3 | 5 | 19 | 10 | -9
| SP/Day | 1.5 |  | 5 | 1.5 | 3 | 4 | 6 | 20 | 38 | 18
|  |  |  | 6 | 0 | 0 | 5 | 7 | 26 | 8 | -18
[6 empty] | Total = | 20 | 8 | 31 | 9.5 | -21.5
[6 empty] | Over Effort = | 11 | 9 | 28.25 | 18.25 | -10
[8 empty] | 10 | 40 | 0 | -40
11
12
13
Sprint 1 | milestone 1 | [6 empty] | 14
| Start Date | 2021-09-29 |  | Day of Sprint | Forecast | Actual Effort | Hours Worked
| End Date | 2021-10-05 |  | 0 | 18.5 | 18.5 | 0
| Sprint Length | 7 |  | 1 | 15.8571 | 17.5 | 3
|  |  |  | 2 | 13.2143 | 17.5 | 0
| Capacity | 20 |  | 3 | 10.5714 | 16.5 | 4
| Total Sprint SP | 18.5 |  | 4 | 7.9286 | 14.5 | 6
| SP/Day | 2.6429 |  | 5 | 5.2857 | 9.5 | 6
|  |  |  | 6 | 2.6429 | 5.5 | 7
|  |  |  | 7 | 0 | 0 | 7
[6 empty] | Total = | 33
[6 empty] | Over Effort = | 14.5
Sprint 2 | test plan
| Start Date | 2021-10-13 |  | Day of Sprint | Forecast | Actual Effort | Hours Worked
| End Date | 2021-10-18 |  | 0 | 6 | 6 | 0
| Sprint Length | 6 |  | 1 | 5 | 6 | 0
|  |  |  | 2 | 4 | 6 | 0
| Capacity | 8 |  | 3 | 3 | 5 | 1
| Total Sprint SP | 6 |  | 4 | 2 | 5 | 0
| SP/Day | 1 |  | 5 | 1 | 3 | 2
|  |  |  | 6 | 0 | 1 | 2
[6 empty] | Total = | 5
[6 empty] | Over Effort = | -1
Sprint 3 | project plan | network diagram
| Start Date | 2021-10-21 |  | Day of Sprint | Forecast | Actual Effort | Hours Worked
| End Date | 2021-10-26 |  | 0 | 14 | 14 | 0
| Sprint Length | 6 |  | 1 | 11.6667 | 12 | 1.5
|  |  |  | 2 | 9.3333 | 9 | 3.5
| Capacity | 18 |  | 3 | 7 | 8.25 | 0.5
| Total Sprint SP | 14 |  | 4 | 4.6667 | 5.25 | 4.75
| SP/Day | 2.3333 |  | 5 | 2.3333 | 1 | 3.75
|  |  |  | 6 | 0 | 0 | 2
[6 empty] | Total = | 16
[6 empty] | Over Effort = | 2
Sprint 4 | UM, Logging | on older docs | and LL
| Start Date | 2021-11-05 |  | Day of Sprint | Forecast | Actual Effort | Hours Worked
| End Date | 2021-11-12 |  | 0 | 14 | 14 | 0
| Sprint Length | 8 |  | 1 | 12.25 | 13 | 1
|  |  |  | 2 | 10.5 | 13 | 0
| Capacity | 16 |  | 3 | 8.75 | 13 | 1.25
| Total Sprint SP | 14 |  | 4 | 7 | 12 | 3
| SP/Day | 1.75 |  | 5 | 5.25 | 12 | 0
|  |  |  | 6 | 3.5 | 11 | 3
|  |  |  | 7 | 1.75 | 11 | 0
|  |  |  | 8 | 0 | 9 | 4.25
[6 empty] | Total = | 12.5
[6 empty] | Over effort = | -1.5
Sprint 5 | sprint 4 + | core comp
| Start Date | 2021-11-15 |  | Day of Sprint | Forecast | Actual Effort | Hours Worked
| End Date | 2021-11-24 |  | 0 | 19 | 19 | 0
| Sprint Length | 10 |  | 1 | 17.1 | 19 | 0
|  |  |  | 2 | 15.2 | 17 | 1
| Capacity | 20 |  | 3 | 13.3 | 14 | 1.5
| Total Sprint SP | 19 |  | 4 | 11.4 | 12 | 2
| SP/Day | 1.9 |  | 5 | 9.5 | 10 | 1
|  |  |  | 6 | 7.6 | 8.5 | 1.5
|  |  |  | 7 | 5.7 | 6.25 | 1.75
|  |  |  | 8 | 3.8 | 4 | 1.25
|  |  |  | 9 | 1.9 | 4 | 0
|  |  |  | 10 | 0 | 4 | 0
[6 empty] | Total = | 10
[6 empty] | Over effort = | -9
Sprint 6 | sprint 5 + | codes
| Start Date | 2021-11-29 |  | Day of Sprint | Forecast | Actual Effort | Hours Worked
| End Date | 2021-12-14 |  | 0 | 20 | 20 | 0
| Sprint Length | 16 |  | 1 | 18.75 | 20 | 0
|  |  |  | 2 | 17.5 | 18 | 4
| Capacity | 22 |  | 3 | 16.25 | 17.5 | 4
| Total Sprint SP | 20 |  | 4 | 15 | 17 | 2
| SP/Day | 1.25 |  | 5 | 13.75 | 16.5 | 2
|  |  |  | 6 | 12.5 | 16.5 | 0
|  |  |  | 7 | 11.25 | 15.5 | 3
|  |  |  | 8 | 10 | 15 | 6
|  |  |  | 9 | 8.75 | 14 | 4
|  |  |  | 10 | 7.5 | 14 | 0
|  |  |  | 11 | 6.25 | 14 | 0
|  |  |  | 12 | 5 | 12 | 2.5
|  |  |  | 13 | 3.75 | 12 | 0
|  |  |  | 14 | 2.5 | 11 | 1
|  |  |  | 15 | 1.25 | 5 | 5
|  |  |  | 16 | 0 | 0 | 4.5
[6 empty] | Total = | 38
[6 empty] | Over effort = | 18
Sprint 7 | 1st half core
| Start Date | 2022-01-11 |  | Day of Sprint | Forecast | Actual Effort | Hours Worked
| End Date | 2022-01-22 |  | 0 | 26 | 26 | 0
| Sprint Length | 12 |  | 1 | 23.8333 | 26 | 0
|  |  |  | 2 | 21.6667 | 26 | 0
| Capacity | 30 |  | 3 | 19.5 | 26 | 0
| Total Sprint SP | 26 |  | 4 | 17.3333 | 25 | 2
| SP/Day | 2.1667 |  | 5 | 15.1667 | 25 | 0
|  |  |  | 6 | 13 | 25 | 0
|  |  |  | 7 | 10.8333 | 25 | 0
|  |  |  | 8 | 8.6667 | 24 | 2
|  |  |  | 9 | 6.5 | 24 | 0
|  |  |  | 10 | 4.3333 | 24 | 0
|  |  |  | 11 | 2.1667 | 24 | 0
|  |  |  | 12 | 0 | 23 | 4
[6 empty] | Total = | 8
[6 empty] | Over effort = | -18
Sprint 8 | 1st half core
| Start Date | 2022-01-25 |  | Day of Sprint | Forecast | Actual Effort | Hours Worked
| End Date | 2022-02-05 |  | 0 | 31 | 31 | 0
| Sprint Length | 12 |  | 1 | 28.4167 | 30 | 2
|  |  |  | 2 | 25.8333 | 30 | 2
| Capacity | 32 |  | 3 | 23.25 | 30 | 1.5
| Total Sprint SP | 31 |  | 4 | 20.6667 | 30 | 0
| SP/Day | 2.5833 |  | 5 | 18.0833 | 30 | 0
|  |  |  | 6 | 15.5 | 30 | 1
|  |  |  | 7 | 12.9167 | 29.75 | 1
|  |  |  | 8 | 10.3333 | 29.5 | 1
|  |  |  | 9 | 7.75 | 29.25 | 1
|  |  |  | 10 | 5.1667 | 29.25 | 0
|  |  |  | 11 | 2.5833 | 28.25 | 0
|  |  |  | 12 | 0 | 27.25 | 0
[6 empty] | Total = | 9.5
[6 empty] | Over effort = | -21.5
Sprint 9 | 1st half core
| Start Date | 2022-02-08 |  | Day of Sprint | Forecast | Actual Effort | Hours Worked
| End Date | 2022-02-19 |  | 0 | 28.25 | 28.25 | 0
| Sprint Length | 12 |  | 1 | 25.8958 | 28 | 0.25
|  |  |  | 2 | 23.5417 | 27 | 1
| Capacity | 29 |  | 3 | 21.1875 | 26 | 2
| Total Sprint SP | 28.25 |  | 4 | 18.8333 | 25.75 | 2
| SP/Day | 2.3542 |  | 5 | 16.4792 | 25.25 | 1
|  |  |  | 6 | 14.125 | 24.25 | 2
|  |  |  | 7 | 11.7708 | 23.75 | 0.5
|  |  |  | 8 | 9.4167 | 21.25 | 2
|  |  |  | 9 | 7.0625 | 20.25 | 1
|  |  |  | 10 | 4.7083 | 17.25 | 2
|  |  |  | 11 | 2.3542 | 16 | 1.5
|  |  |  | 12 | 0 | 16 | 3
[6 empty] | Total = | 18.25
[6 empty] | Over effort = | -10
Sprint 10 | team code review feature
| Start Date | 2022-02-22 |  | Day of Sprint | Forecast | Actual Effort | Hours Worked
| End Date | 2022-03-05 |  | 0 | 40 | 40 | 0
| Sprint Length | 12 |  | 1 | 36.6667
|  |  |  | 2 | 33.3333
| Capacity | 40 |  | 3 | 30
| Total Sprint SP | 40 |  | 4 | 26.6667
| SP/Day | 3.3333 |  | 5 | 23.3333
|  |  |  | 6 | 20
|  |  |  | 7 | 16.6667
|  |  |  | 8 | 13.3333
|  |  |  | 9 | 10
|  |  |  | 10 | 6.6667
|  |  |  | 11 | 3.3333
|  |  |  | 12 | 0
[6 empty] | Total = | 0
[6 empty] | Over effort = | -40

## Devarsh
Sprint 8 | 1st half core | [5 empty] | Sprint | SP | Hours Worked | Over/Under
| Start Date | 2022-01-25 | Day of Sprint | Forecast | Actual Effort | Hours Worked | 8 | 3 | 6 | 3
| End Date | 2022-02-05 | 0 | 3 | 3 | 0 | 9 | 21.25 | 10.25 | -11
| Sprint Length | 12 | 1 | 2.75 | 3 | 0 | 10 | 21.25 | 0 | -21.25
|  |  | 2 | 2.5 | 3 | 0 | 11
| Capacity | 5 | 3 | 2.25 | 3 | 0 | 12
| Total Sprint SP | 3 | 4 | 2 | 3 | 0 | 13
| SP/Day | 0.25 | 5 | 1.75 | 3 | 0
|  |  | 6 | 1.5 | 3 | 0
|  |  | 7 | 1.25 | 3 | 1
|  |  | 8 | 1 | 3 | 1
|  |  | 9 | 0.75 | 2 | 1
|  |  | 10 | 0.5 | 2 | 1
|  |  | 11 | 0.25 | 1 | 1
|  |  | 12 | 0 | 0 | 1
[5 empty] | Total = | 6
[5 empty] | Over effort = | 3
Sprint 9 | 1st half core
| Start Date | 2022-02-08 | Day of Sprint | Forecast | Actual Effort | Hours Worked
| End Date | 2022-02-19 | 0 | 21.25 | 21.25 | 0
| Sprint Length | 12 | 1 | 19.4792 | 20.25 | 1
|  |  | 2 | 17.7083 | 20 | 0.25
| Capacity | 23 | 3 | 15.9375 | 18 | 1
| Total Sprint SP | 21.25 | 4 | 14.1667 | 18 | 1
| SP/Day | 1.7708 | 5 | 12.3958 | 18 | 1
|  |  | 6 | 10.625 | 16 | 1
|  |  | 7 | 8.8542 | 15 | 1
|  |  | 8 | 7.0833 | 15 | 0
|  |  | 9 | 5.3125 | 14 | 1
|  |  | 10 | 3.5417 | 13 | 1
|  |  | 11 | 1.7708 | 12 | 1
|  |  | 12 | 0 | 11 | 1
[5 empty] | Total = | 10.25
[5 empty] | Over effort = | -11
Sprint 10 | team code review feature
| Start Date | 2022-02-22 | Day of Sprint | Forecast | Actual Effort | Hours Worked
| End Date | 2022-03-05 | 0 | 21.25 | 21.25 | 0
| Sprint Length | 12 | 1 | 19.4792
|  |  | 2 | 17.7083
| Capacity | 23 | 3 | 15.9375
| Total Sprint SP | 21.25 | 4 | 14.1667
| SP/Day | 1.7708 | 5 | 12.3958
|  |  | 6 | 10.625
|  |  | 7 | 8.8542
|  |  | 8 | 7.0833
|  |  | 9 | 5.3125
|  |  | 10 | 3.5417
|  |  | 11 | 1.7708
|  |  | 12 | 0
[5 empty] | Total = | 0
[5 empty] | Over effort = | -21.25

## Jacob
Sprint 8 | 1st half core | [5 empty] | Sprint | SP | Hours Worked | Over/Under
| Start Date | 2022-01-25 | Day of Sprint | Forecast | Actual Effort | Hours Worked | 8 | 5 | 7 | 2
| End Date | 2022-02-05 | 0 | 5 | 5 | 0 | 9 | 26 | 19 | -7
| Sprint Length | 12 | 1 | 4.5833 | 5 | 0 | 10 | 30 | 0 | -30
|  |  | 2 | 4.1667 | 5 | 0 | 11
| Capacity | 7 | 3 | 3.75 | 5 | 0 | 12
| Total Sprint SP | 5 | 4 | 3.3333 | 5 | 0 | 13
| SP/Day | 0.41667 | 5 | 2.9167 | 5 | 0
|  |  | 6 | 2.5 | 5 | 0
|  |  | 7 | 2.0833 | 5 | 1
|  |  | 8 | 1.6667 | 4 | 1
|  |  | 9 | 1.25 | 3 | 1
|  |  | 10 | 0.83333 | 2 | 2
|  |  | 11 | 0.41667 | 1 | 1
|  |  | 12 | 0 | 0 | 1
[5 empty] | Total = | 7
[5 empty] | Over effort = | 2
Sprint 9 | 1st half core
| Start Date | 2022-02-08 | Day of Sprint | Forecast | Actual Effort | Hours Worked
| End Date | 2022-02-19 | 0 | 26 | 26 | 0
| Sprint Length | 12 | 1 | 23.8333 | 25 | 1
|  |  | 2 | 21.6667 | 24 | 1
| Capacity | 27 | 3 | 19.5 | 22 | 2
| Total Sprint SP | 26 | 4 | 17.3333 | 21 | 1
| SP/Day | 2.1667 | 5 | 15.1667 | 20 | 1
|  |  | 6 | 13 | 18 | 2
|  |  | 7 | 10.8333 | 16 | 2
|  |  | 8 | 8.6667 | 14 | 2
|  |  | 9 | 6.5 | 12 | 2
|  |  | 10 | 4.3333 | 10 | 2
|  |  | 11 | 2.1667 | 9 | 1
|  |  | 12 | 0 | 7 | 2
[5 empty] | Total = | 19
[5 empty] | Over effort = | -7
Sprint 10 | team code review feature
| Start Date | 2022-02-22 | Day of Sprint | Forecast | Actual Effort | Hours Worked
| End Date | 2022-03-05 | 0 | 30 | 30 | 0
| Sprint Length | 12 | 1 | 27.5
|  |  | 2 | 25
| Capacity | 30 | 3 | 22.5
| Total Sprint SP | 30 | 4 | 20
| SP/Day | 2.5 | 5 | 17.5
|  |  | 6 | 15
|  |  | 7 | 12.5
|  |  | 8 | 10
|  |  | 9 | 7.5
|  |  | 10 | 5
|  |  | 11 | 2.5
|  |  | 12 | 0
[5 empty] | Total = | 0
[5 empty] | Over effort = | -30

## Joseph
Sprint 0 | proposal | [6 empty] | Sprint | SP | Hours Worked | Over/Under
| Start Date | 2021-09-22 |  | Day of Sprint | Forecast | Actual Effort | Hours Worked | 0 | 4 | 18 | 14
| End Date | 2021-09-27 |  | 0 | 4 | 4 | 0 | 1 | 5.5 | 24 | 18.5
| Sprint Length | 6 |  | 1 | 3.33 | 4 | 1 | 2 | 6 | 11 | 5
|  |  |  | 2 | 2.66 | 4 | 0 | 3 | 14 | 28 | 14
| Capacity | 10 |  | 3 | 1.99 | 2 | 6 | 4 | 15 | 13 | -2
| Total Sprint SP | 4 |  | 4 | 1.32 | 2 | 1 | 5 | 19 | 10.75 | -8.25
| SP/Day | 0.67 |  | 5 | 0.65 | 0 | 5 | 6 | 19 | 31.5 | 12.5
|  |  |  | 6 | 0 | 0 | 5 | 7 | 32 | 12 | -20
[6 empty] | Total = | 18 | 8 | 20 | 17 | -3
[6 empty] | Over Effort = | 14 | 9 | 18.5 | 17.75 | -0.75
[8 empty] | 10 | 27.25 | 0 | -27.25
11
12
13
Sprint 1 | milestone 1 | [6 empty] | 14
| Start Date | 2021-09-29 |  | Day of Sprint | Forecast | Actual Effort | Hours Worked
| End Date | 2021-10-05 |  | 0 | 5.5 | 5.5 | 0
| Sprint Length | 7 |  | 1 | 4.7143 | 5 | 2
|  |  |  | 2 | 3.9286 | 5 | 0
| Capacity | 10 |  | 3 | 3.1429 | 4 | 2
| Total Sprint SP | 5.5 |  | 4 | 2.3571 | 3 | 3
| SP/Day | 0.78571 |  | 5 | 1.5714 | 2 | 5
|  |  |  | 6 | 0.78571 | 1 | 6
|  |  |  | 7 | 0 | 0 | 6
[6 empty] | Total = | 24
[6 empty] | Over Effort = | 18.5
Sprint 2 | test plan
| Start Date | 2021-10-13 |  | Day of Sprint | Forecast | Actual Effort | Hours Worked
| End Date | 2021-10-18 |  | 0 | 6 | 6 | 0
| Sprint Length | 6 |  | 1 | 5 | 6 | 0
|  |  |  | 2 | 4 | 6 | 0
| Capacity | 8 |  | 3 | 3 | 3 | 4
| Total Sprint SP | 6 |  | 4 | 2 | 2 | 3
| SP/Day | 1 |  | 5 | 1 | 1 | 2
|  |  |  | 6 | 0 | 0 | 2
[6 empty] | Total = | 11
[6 empty] | Over Effort = | 5
Sprint 3 | project plan | network diagram
| Start Date | 2021-10-21 |  | Day of Sprint | Forecast | Actual Effort | Hours Worked
| End Date | 2021-10-26 |  | 0 | 14 | 14 | 0
| Sprint Length | 6 |  | 1 | 11.6667 | 14 | 0
|  |  |  | 2 | 9.3333 | 13 | 6.5
| Capacity | 18 |  | 3 | 7 | 10 | 5
| Total Sprint SP | 14 |  | 4 | 4.6667 | 7 | 4
| SP/Day | 2.3333 |  | 5 | 2.3333 | 4 | 5
|  |  |  | 6 | 0 | 0 | 7.5
[6 empty] | Total = | 28
[6 empty] | Over Effort = | 14
Sprint 4 | UM, Logging | on older docs | and LL
| Start Date | 2021-11-05 |  | Day of Sprint | Forecast | Actual Effort | Hours Worked
| End Date | 2021-11-12 |  | 0 | 15 | 15 | 0
| Sprint Length | 8 |  | 1 | 13.125 | 15 | 1
|  |  |  | 2 | 11.25 | 15 | 1
| Capacity | 16 |  | 3 | 9.375 | 15 | 1
| Total Sprint SP | 15 |  | 4 | 7.5 | 15 | 2
| SP/Day | 1.875 |  | 5 | 5.625 | 14 | 2
|  |  |  | 6 | 3.75 | 13 | 2
|  |  |  | 7 | 1.875 | 12 | 2
|  |  |  | 8 | 0 | 11 | 2
[6 empty] | Total = | 13
[6 empty] | Over effort = | -2
Sprint 5 | sprint 4 + | core comp
| Start Date | 2021-11-14 |  | Day of Sprint | Forecast | Actual Effort | Hours Worked
| End Date | 2021-11-19 |  | 0 | 19 | 19 | 0
| Sprint Length | 10 |  | 1 | 17.1 | 17 | 1
|  |  |  | 2 | 15.2 | 16.5 | 0.5
| Capacity | 20 |  | 3 | 13.3 | 15.5 | 1
| Total Sprint SP | 19 |  | 4 | 11.4 | 15.5 | 0
| SP/Day | 1.9 |  | 5 | 9.5 | 14.75 | 1.25
|  |  |  | 6 | 7.6 | 14.25 | 0.5
|  |  |  | 7 | 5.7 | 13.75 | 0.5
|  |  |  | 8 | 3.8 | 13.25 | 0.75
|  |  |  | 9 | 1.9 | 12.25 | 0.75
|  |  |  | 10 | 0 | 8 | 4.5
[6 empty] | Total = | 10.75
[6 empty] | Over effort = | -8.25
Sprint 6 | sprint 5 + | codes
| Start Date | 2021-11-29 |  | Day of Sprint | Forecast | Actual Effort | Hours Worked
| End Date | 2021-12-14 |  | 0 | 19 | 19 | 0
| Sprint Length | 16 |  | 1 | 17.8125 | 18.75 | 1
|  |  |  | 2 | 16.625 | 18.5 | 2
| Capacity | 22 |  | 3 | 15.4375 | 18.25 | 1
| Total Sprint SP | 19 |  | 4 | 14.25 | 18 | 2
| SP/Day | 1.1875 |  | 5 | 13.0625 | 18 | 0.5
|  |  |  | 6 | 11.875 | 18 | 0
|  |  |  | 7 | 10.6875 | 17.75 | 2
|  |  |  | 8 | 9.5 | 17.75 | 4
|  |  |  | 9 | 8.3125 | 17.75 | 0
|  |  |  | 10 | 7.125 | 15.25 | 4
|  |  |  | 11 | 5.9375 | 13 | 2.5
|  |  |  | 12 | 4.75 | 9 | 3
|  |  |  | 13 | 3.5625 | 6.25 | 2
|  |  |  | 14 | 2.375 | 4.75 | 2.5
|  |  |  | 15 | 1.1875 | 2.25 | 3
|  |  |  | 16 | 0 | 0 | 2
[6 empty] | Total = | 31.5
[6 empty] | Over effort = | 12.5
Sprint 7 | 1st half core
| Start Date | 2022-01-11 |  | Day of Sprint | Forecast | Actual Effort | Hours Worked
| End Date | 2022-01-22 |  | 0 | 32 | 32 | 0
| Sprint Length | 12 |  | 1 | 29.3333 | 32 | 1
|  |  |  | 2 | 26.6667 | 32 | 0.5
| Capacity | 33 |  | 3 | 24 | 32 | 0.5
| Total Sprint SP | 32 |  | 4 | 21.3333 | 31 | 1
| SP/Day | 2.6667 |  | 5 | 18.6667 | 29 | 2
|  |  |  | 6 | 16 | 28 | 2
|  |  |  | 7 | 13.3333 | 28 | 0
|  |  |  | 8 | 10.6667 | 27 | 1
|  |  |  | 9 | 8 | 26 | 1.5
|  |  |  | 10 | 5.3333 | 26 | 0
|  |  |  | 11 | 2.6667 | 26 | 0.5
|  |  |  | 12 | 0 | 24 | 2
[6 empty] | Total = | 12
[6 empty] | Over effort = | -20
Sprint 8 | 1st half core
| Start Date | 2022-01-25 |  | Day of Sprint | Forecast | Actual Effort | Hours Worked
| End Date | 2022-02-05 |  | 0 | 20 | 20 | 0
| Sprint Length | 12 |  | 1 | 18.3333 | 19 | 2
|  |  |  | 2 | 16.6667 | 18 | 2
| Capacity | 23 |  | 3 | 15 | 17 | 3
| Total Sprint SP | 20 |  | 4 | 13.3333 | 17 | 0
| SP/Day | 1.6667 |  | 5 | 11.6667 | 16 | 1.5
|  |  |  | 6 | 10 | 15.25 | 1.5
|  |  |  | 7 | 8.3333 | 14.75 | 1.5
|  |  |  | 8 | 6.6667 | 14.5 | 1
|  |  |  | 9 | 5 | 13 | 2.5
|  |  |  | 10 | 3.3333 | 12 | 1
|  |  |  | 11 | 1.6667 | 11 | 1
|  |  |  | 12 | 0 | 11 | 0
[6 empty] | Total = | 17
[6 empty] | Over effort = | -3
Sprint 9 | 1st half core
| Start Date | 2022-02-08 |  | Day of Sprint | Forecast | Actual Effort | Hours Worked
| End Date | 2022-02-19 |  | 0 | 18.5 | 18.5 | 0
| Sprint Length | 12 |  | 1 | 16.9583 | 18 | 2
|  |  |  | 2 | 15.4167 | 17 | 2
| Capacity | 20 |  | 3 | 13.875 | 16.25 | 1.5
| Total Sprint SP | 18.5 |  | 4 | 12.3333 | 15.75 | 1
| SP/Day | 1.5417 |  | 5 | 10.7917 | 14.75 | 1.5
|  |  |  | 6 | 9.25 | 14.25 | 2
|  |  |  | 7 | 7.7083 | 13.75 | 2
|  |  |  | 8 | 6.1667 | 12.25 | 1
|  |  |  | 9 | 4.625 | 11.75 | 0.75
|  |  |  | 10 | 3.0833 | 9.75 | 1.5
|  |  |  | 11 | 1.5417 | 7.75 | 2
|  |  |  | 12 | 0 | 7.25 | 0.5
[6 empty] | Total = | 17.75
[6 empty] | Over effort = | -0.75
Sprint 10 | team code review feature
| Start Date | 2022-02-22 |  | Day of Sprint | Forecast | Actual Effort | Hours Worked
| End Date | 2022-03-05 |  | 0 | 27.25 | 27.25 | 0
| Sprint Length | 12 |  | 1 | 24.9792
|  |  |  | 2 | 22.7083
| Capacity | 30 |  | 3 | 20.4375
| Total Sprint SP | 27.25 |  | 4 | 18.1667
| SP/Day | 2.2708 |  | 5 | 15.8958
|  |  |  | 6 | 13.625
|  |  |  | 7 | 11.3542
|  |  |  | 8 | 9.0833
|  |  |  | 9 | 6.8125
|  |  |  | 10 | 4.5417
|  |  |  | 11 | 2.2708
|  |  |  | 12 | 0
[6 empty] | Total = | 0
[6 empty] | Over effort = | -27.25

## Michael
Sprint 0 | proposal | [6 empty] | Sprint | SP | Hours Worked | Over/Under
| Start Date | 2021-09-22 |  | Day of Sprint | Forecast | Actual Effort | Hours Worked | 0 | 4 | 18 | 14
| End Date | 2021-09-27 |  | 0 | 8 | 8 | 0 | 1 | 11.5 | 28 | 16.5
| Sprint Length | 6 |  | 1 | 6.67 | 7 | 1 | 2 | 6 | 11 | 5
|  |  |  | 2 | 5.33 | 7 | 0 | 3 | 16 | 23 | 7
| Capacity | 10 |  | 3 | 4 | 4 | 6 | 4 | 16 | 8 | -8
| Total Sprint SP | 8 |  | 4 | 2.66 | 4 | 1 | 5 | 19 | 12 | -7
| SP/Day | 0.67 |  | 5 | 1.33 | 2 | 4 | 6 | 22 | 35 | 13
|  |  |  | 6 | 0 | 0 | 5 | 7 | 26 | 8 | -18
[6 empty] | Total = | 17 | 8 | 22 | 6 | -16
[6 empty] | Over Effort = | 14 | 9 | 23 | 14 | -9
[8 empty] | 10 | 34 | 0 | -34
11
12
13
Sprint 1 | milestone 1 | [6 empty] | 14
| Start Date | 2021-09-29 |  | Day of Sprint | Forecast | Actual Effort | Hours Worked
| End Date | 2021-10-05 |  | 0 | 10.5 | 10.5 | 0
| Sprint Length | 7 |  | 1 | 9 | 9.5 | 3
|  |  |  | 2 | 7.5 | 9.5 | 0
| Capacity | 12 |  | 3 | 6 | 7.5 | 7
| Total Sprint SP | 10.5 |  | 4 | 4.5 | 6.5 | 5
| SP/Day | 1.5 |  | 5 | 3 | 4.5 | 5
|  |  |  | 6 | 1.5 | 2.5 | 5
|  |  |  | 7 | 0 | 0 | 5
[6 empty] | Total = | 30
[6 empty] | Over Effort = | 19.5
Sprint 2 | test plan
| Start Date | 2021-10-13 |  | Day of Sprint | Forecast | Actual Effort | Hours Worked
| End Date | 2021-10-18 |  | 0 | 6 | 6 | 0
| Sprint Length | 6 |  | 1 | 5 | 6 | 0
|  |  |  | 2 | 4 | 6 | 0
| Capacity | 8 |  | 3 | 3 | 5 | 1
| Total Sprint SP | 6 |  | 4 | 2 | 4 | 1
| SP/Day | 1 |  | 5 | 1 | 1 | 3
|  |  |  | 6 | 0 | 0 | 1
[6 empty] | Total = | 6
[6 empty] | Over Effort = | 0
Sprint 3 | project plan | network diagram
| Start Date | 2021-10-21 |  | Day of Sprint | Forecast | Actual Effort | Hours Worked
| End Date | 2021-10-26 |  | 0 | 16 | 16 | 0
| Sprint Length | 6 |  | 1 | 13.3333 | 16 | 0
|  |  |  | 2 | 10.6667 | 15 | 2
| Capacity | 18 |  | 3 | 8 | 14 | 1
| Total Sprint SP | 16 |  | 4 | 5.3333 | 11 | 4
| SP/Day | 2.6667 |  | 5 | 2.6667 | 7 | 6
|  |  |  | 6 | 0 | 0 | 10
[6 empty] | Total = | 23
[6 empty] | Over Effort = | 7
Sprint 4 | UM, Logging | on older docs | and LL
| Start Date | 2021-11-05 |  | Day of Sprint | Forecast | Actual Effort | Hours Worked
| End Date | 2021-11-12 |  | 0 | 16 | 16 | 0
| Sprint Length | 8 |  | 1 | 14 | 16 | 0
|  |  |  | 2 | 12 | 16 | 0
| Capacity | 16 |  | 3 | 10 | 16 | 0
| Total Sprint SP | 16 |  | 4 | 8 | 15 | 3
| SP/Day | 2 |  | 5 | 6 | 14 | 2
|  |  |  | 6 | 4 | 12 | 3
|  |  |  | 7 | 2 |  | 0
|  |  |  | 8 | 0 |  | 0
[6 empty] | Total = | 8
[6 empty] | Over effort = | -8
Sprint 5 | sprint 4 + | core comp
| Start Date | 2021-11-14 |  | Day of Sprint | Forecast | Actual Effort | Hours Worked
| End Date | 2021-11-19 |  | 0 | 19 | 19 | 0
| Sprint Length | 10 |  | 1 | 17.1 | 17 | 3
|  |  |  | 2 | 15.2 | 16.5 | 1
| Capacity | 20 |  | 3 | 13.3 | 16 | 1
| Total Sprint SP | 19 |  | 4 | 11.4 | 15.5 | 1
| SP/Day | 1.9 |  | 5 | 9.5 | 15 | 1
|  |  |  | 6 | 7.6 | 14 | 1
|  |  |  | 7 | 5.7 | 12 | 1
|  |  |  | 8 | 3.8 | 11 | 1
|  |  |  | 9 | 1.9 | 10 | 1
|  |  |  | 10 | 0 | 9 | 1
[6 empty] | Total = | 12
[6 empty] | Over effort = | -7
Sprint 6 | sprint 5 + | codes
| Start Date | 2021-11-29 |  | Day of Sprint | Forecast | Actual Effort | Hours Worked
| End Date | 2021-12-14 |  | 0 | 22 | 22 | 0
| Sprint Length | 16 |  | 1 | 20.625 | 21 | 3
|  |  |  | 2 | 19.25 | 20 | 2
| Capacity | 24 |  | 3 | 17.875 | 19 | 2
| Total Sprint SP | 22 |  | 4 | 16.5 | 17 | 2
| SP/Day | 1.375 |  | 5 | 15.125 | 16.5 | 1
|  |  |  | 6 | 13.75 | 16.5 | 0
|  |  |  | 7 | 12.375 | 14.5 | 2
|  |  |  | 8 | 11 | 14 | 1
|  |  |  | 9 | 9.625 | 12 | 3
|  |  |  | 10 | 8.25 | 9 | 3
|  |  |  | 11 | 6.875 | 8 | 1
|  |  |  | 12 | 5.5 | 8 | 0
|  |  |  | 13 | 4.125 | 7 | 2
|  |  |  | 14 | 2.75 | 6 | 2
|  |  |  | 15 | 1.375 | 4 | 5
|  |  |  | 16 | 0 | 0 | 6
[6 empty] | Total = | 35
[6 empty] | Over effort = | 13
Sprint 7 | 1st half core
| Start Date | 2022-01-11 |  | Day of Sprint | Forecast | Actual Effort | Hours Worked
| End Date | 2022-01-22 |  | 0 | 26 | 26 | 0
| Sprint Length | 12 |  | 1 | 23.8333 | 26 | 0
|  |  |  | 2 | 21.6667 | 26 | 0
| Capacity | 31 |  | 3 | 19.5 | 26 | 0
| Total Sprint SP | 26 |  | 4 | 17.3333 | 26 | 0
| SP/Day | 2.1667 |  | 5 | 15.1667 | 26 | 0
|  |  |  | 6 | 13 | 26 | 0
|  |  |  | 7 | 10.8333 | 25 | 2
|  |  |  | 8 | 8.6667 | 25 | 0
|  |  |  | 9 | 6.5 | 24 | 2
|  |  |  | 10 | 4.3333 | 23 | 2
|  |  |  | 11 | 2.1667 | 22 | 2
|  |  |  | 12 | 0 | 22 | 0
[6 empty] | Total = | 8
[6 empty] | Over effort = | -18
Sprint 8 | 1st half core
| Start Date | 2022-01-25 |  | Day of Sprint | Forecast | Actual Effort | Hours Worked
| End Date | 2022-02-05 |  | 0 | 22 | 22 | 0
| Sprint Length | 12 |  | 1 | 20.1667 | 21 | 2
|  |  |  | 2 | 18.3333 | 20 | 2
| Capacity | 25 |  | 3 | 16.5 | 20 | 0
| Total Sprint SP | 22 |  | 4 | 14.6667 | 20 | 0
| SP/Day | 1.8333 |  | 5 | 12.8333 | 19 | 2
|  |  |  | 6 | 11 | 19 | 0
|  |  |  | 7 | 9.1667 | 19 | 0
|  |  |  | 8 | 7.3333 | 19 | 0
|  |  |  | 9 | 5.5 | 19 | 0
|  |  |  | 10 | 3.6667 | 19 | 0
|  |  |  | 11 | 1.8333 | 19 | 0
|  |  |  | 12 | 0 | 19 | 0
[6 empty] | Total = | 6
[6 empty] | Over effort = | -16
Sprint 9 | 1st half core
| Start Date | 2022-02-08 |  | Day of Sprint | Forecast | Actual Effort | Hours Worked
| End Date | 2022-02-19 |  | 0 | 23 | 23 | 0
| Sprint Length | 12 |  | 1 | 21.0833 | 23 | 0
|  |  |  | 2 | 19.1667 | 22 | 1
| Capacity | 24 |  | 3 | 17.25 | 21 | 2
| Total Sprint SP | 23 |  | 4 | 15.3333 | 21 | 1
| SP/Day | 1.9167 |  | 5 | 13.4167 | 20 | 2
|  |  |  | 6 | 11.5 | 20 | 0
|  |  |  | 7 | 9.5833 | 18 | 2
|  |  |  | 8 | 7.6667 | 18 | 0
|  |  |  | 9 | 5.75 | 16 | 2
|  |  |  | 10 | 3.8333 | 15 | 1
|  |  |  | 11 | 1.9167 | 13 | 2
|  |  |  | 12 | 0 | 12 | 1
[6 empty] | Total = | 14
[6 empty] | Over effort = | -9
Sprint 10 | team code review feature
| Start Date | 2022-02-22 |  | Day of Sprint | Forecast | Actual Effort | Hours Worked
| End Date | 2022-03-05 |  | 0 | 34 | 34 | 0
| Sprint Length | 12 |  | 1 | 31.1667
|  |  |  | 2 | 28.3333
| Capacity | 35 |  | 3 | 25.5
| Total Sprint SP | 34 |  | 4 | 22.6667
| SP/Day | 2.8333 |  | 5 | 19.8333
|  |  |  | 6 | 17
|  |  |  | 7 | 14.1667
|  |  |  | 8 | 11.3333
|  |  |  | 9 | 8.5
|  |  |  | 10 | 5.6667
|  |  |  | 11 | 2.8333
|  |  |  | 12 | 0
[6 empty] | Total = | 0
[6 empty] | Over effort = | -34

## SzeMan
Sprint 8 | 1st half core | [5 empty] | Sprint | SP | Hours Worked | Over/Under
| Start Date | 2022-01-25 | Day of Sprint | Forecast | Actual Effort | Hours Worked | 8 | 3 | 5 | 2
| End Date | 2022-02-05 | 0 | 3 | 3 | 0 | 9 | 28.25 | 7.25 | -21
| Sprint Length | 12 | 1 | 2.75 | 3 | 0 | 10 | 21 | 0 | -21
|  |  | 2 | 2.5 | 3 | 0 | 11
| Capacity | 20 | 3 | 2.25 | 3 | 0 | 12
| Total Sprint SP | 3 | 4 | 2 | 3 | 0 | 13
| SP/Day | 0.25 | 5 | 1.75 | 3 | 0
|  |  | 6 | 1.5 | 3 | 0
|  |  | 7 | 1.25 | 3 | 1
|  |  | 8 | 1 | 3 | 1
|  |  | 9 | 0.75 | 2 | 1
|  |  | 10 | 0.5 | 2 | 0
|  |  | 11 | 0.25 | 1 | 1
|  |  | 12 | 0 | 0 | 1
[5 empty] | Total = | 5
[5 empty] | Over effort = | 2
Sprint 9 | 1st half core
| Start Date | 2022-02-08 | Day of Sprint | Forecast | Actual Effort | Hours Worked
| End Date | 2022-02-19 | 0 | 28.25 | 28.25 | 0
| Sprint Length | 12 | 1 | 25.8958 | 28.25 | 0
|  |  | 2 | 23.5417 | 27.75 | 0.5
| Capacity | 30 | 3 | 21.1875 | 27.25 | 0.5
| Total Sprint SP | 28.25 | 4 | 18.8333 | 27 | 0.25
| SP/Day | 2.3542 | 5 | 16.4792 | 26 | 1
|  |  | 6 | 14.125 | 25 | 1
|  |  | 7 | 11.7708 | 24 | 1
|  |  | 8 | 9.4167 | 23 | 1
|  |  | 9 | 7.0625 | 22 | 1
|  |  | 10 | 4.7083 | 21.5 | 0.5
|  |  | 11 | 2.3542 | 21 | 0.5
|  |  | 12 | 0 | 21 | 0
[5 empty] | Total = | 7.25
[5 empty] | Over effort = | -21
Sprint 10 | team code review feature
| Start Date | 2022-02-22 | Day of Sprint | Forecast | Actual Effort | Hours Worked
| End Date | 2022-03-05 | 0 | 21 | 21 | 0
| Sprint Length | 12 | 1 | 19.25
|  |  | 2 | 17.5
| Capacity | 22 | 3 | 15.75
| Total Sprint SP | 21 | 4 | 14
| SP/Day | 1.75 | 5 | 12.25
|  |  | 6 | 10.5
|  |  | 7 | 8.75
|  |  | 8 | 7
|  |  | 9 | 5.25
|  |  | 10 | 3.5
|  |  | 11 | 1.75
|  |  | 12 | 0
[5 empty] | Total = | 0
[5 empty] | Over effort = | -21

## Error Chart
Sprint # | % Error | Expected Hours | Actual Hours | Capacity
0 | 154.5455 | 33 | 84 | 50
1 | 45.1327 | 56.5 | 82 | 73
2 | 23.3333 | 30 | 37 | 40
3 | 54.1667 | 72 | 111 | 90
4 | -27.4648 | 71 | 51.5 | 80
5 | -30.9524 | 94.5 | 65.25 | 100
6 | 81.9307 | 101 | 183.75 | 112
7 | -60.8108 | 148 | 58 | 160
8 | -29.5455 | 110 | 77.5 | 125
9 | -26.3434 | 190.75 | 140.5 | 200
10 |  | 238.5 |  | 250
11
12
13

## Retrospective
Sprint | Date | Who | What did we do well? | What did we do wrong? | How can we improve next time?
0 | 2021-09-27 | Albert | As a team, we have good communcaiton | Didnt ask as many questions to professor as should have | Make sure we have priority on backlog
|  | Audrey | As a team, we have good communcaiton and meet when necessary. | Be more productive when waiting for feedback | Work on other items when waiting for feedback
|  | Brad | As a team, we have good communcaiton | Be more productive when waiting for feedback | send more emails to professor when need help, not jsut wait for office hours
|  | Joseph | As a team, we have good communcaiton. | Didnt complete tasks during sprint | work on other items when waiting for feedback
|  | Michael | As a team, we have good communcaiton | Didn't ask for help as much when needed | Make sure we have priority on backlog
1 | 2021-10-06 | Albert | met more as needed, communicated well | We didn't update the status of tasks as often as we should have. | assigning tasks before begining and continously marking when things are done
|  | Audrey | met more as needed, communicated well, got all tasks done during sprint | we worked on it a lot more then orginially planned | make better estimates of story point values
|  | Brad | met more as needed, communicated well | scrum wasnt to level of detail needed it to be at | make individual burndown charts, improve backlog
|  | Joseph | got all WI done, communicated well | we worked on it a lot more then orginially planned | plan the sprint accordingly, write down meeting inormation
|  | Michael | met more as needed, communicated well | didnt update keep track of how many hours worked each day | make nicer and easier way to see how long worked on each task each day
2 | 2021-10-19 | Albert | did better job on prioritizing items each sprint | not accurately keeping track of hours | at the end of each day, update hours | 1 | what did we do well?
|  | Audrey | improved our use of scrum | didnt communicate as much as could have | Still have meetings on scheduled days, even if its just to say what were going to work on, and ask questions
|  | Brad | more clear view of who was doing what task | didnt communicate as much, started late | plan the next sprint ahead of time in order to begin working on the WI during the first day of the sprint
|  | Joseph | split of tasks more evenly | didnt specify who was in charge of what work item | Clearly note who is in charge of which work item
|  | Michael | actually used our backlog | need to update hours daily, not at the end | Update hours at the end of every day
3 | 2021-10-27 | Albert | updated hours on more daily basis, communciated well | Some tasks were not very clearly defined during sprint planning | make sure everyone understands what they are working on during sprint planning | 2 | what did we do wrong?
|  | Audrey | i think we communicated well, met as needed, and were all made clear on what we needed to do | people working on each others assigned tasks | swap tasks if both parties working more on each others task, make that adjustment during sprint planning
|  | Brad | communicated well and asked for help when needed it from each other | having larger crunch time, working more on tasks in beginning of sprint | work on tasks evenly thorughout sprint to avoid all piling up at end
|  | Joseph | made progress on finding information for our resoruces, asking for help when needed | didnt update backlog on where at in progress for a task | update hours on a daily basis
|  | Michael | helped each other out as needed, did more research | not asking as many questions even though still confuesed on what needs to be done | send more emails when have questions regarding whats due, update backlog when finish a task
4 | 2021-11-13 | Albert | working on task independentely were productive | We didn't meet much often as previous sprints and we had lack of communication | more communication would encourage us to finish our tasks faster | 3 | how can we improve next time?
|  | Audrey | we planned for our sprint better | We didnt meet as much as we normally do, missing two days we typically meet, we didnt finish all the tasks for this sprint | be more productive when we dont meet, keep ourselves accountable, fill out hours after working on task
|  | Brad | Research seemed more productive than in past sprints | Didn't communicate as much, self-starting was difficult | Communicate more to increase hours worked
|  | Joseph | Reserch gathering for UM was good | Need to communicate with group more | Ask more about difficulty in tasks for better understanding
|  | Michael | sprint planning went very well | We did not work on things together, when these tasks required collaboration | Plan specifically what will be worked on during a given meeting or day
5 |  | Albert | prioritized tasks well and helped each other out | We left most of talks to work on them at the end of the sprint, which contributed to uncomplete some of our tasks. Moreover, we didn't updated our hours on our oun sprints daily | Working at least an hour everyday on our own tasks and communicate every day to be aware of each others' progress
|  | Audrey | we did well planning this sprint and leaving knowing we all needed to with breaking up the core components | Since it was Thanksgivng break, we did not communicate as much as we normally would have. Also not asking questions when unsure of a task and fillowing hours out | Communicate to the person who is blocking us and work togehter to make sure the task get completed. Plan out a better schedule as to finish everything during the sprint
|  | Brad | improved our use of scrum | Some tasks not as clearly defined/described in the sprint backlog | Ask for clarification on tasks sooner, break down work more when necessary
|  | Joseph | working on task independentely were productive | Didn't ask for help as much when needed | Make sure we have priority on backlog
|  | Michael | Spring Planning went well | A lot of work was not completed and carried over | Plan more specifically when work will be done
6 |  | Albert | Helped each other out to finish our tasks on time by the end of the sprint | Some of us were blocked for some days which contributed to get behind our sprint tasks | If we notice that we are blocked on a task, we should let everyone know to finish our tasks faster
|  | Audrey | writing code for UM implementations was completed on time as we planned | We didn't update the status of tasks as often as we should have. | at the end of each day, update hours
|  | Brad | spring Planning went well | didnt update keep track of how many hours worked each day | Try to avoid carryover from previous sprint
|  | Joseph | did better job prioritizing items each time | didnt communicate as much as could have | work on other items when waiting for feedback
|  | Michael | We were able to complete our work despite caryover from the previous sprint | Too much work was saved for the last few days | Moving forward we need to be better at completing all tasks in a sprint and not letting things get carried over to the next sprint
7 |  | Albert | We started working on this sprint in advance before the semester began | The sprint ended without finishing all our tasks | communicate more and work together to finish our tasks
|  | Audrey | We communicated when we had questions regarding work another team member did | We did not complete all the work in the sprint, feel like when we dont meet we dont work on the project | Checking in every day to see if people have questions or are blocked
|  | Brad | decent job planning; made some progress during break | Didn't meet or work regularly | Meet & work regularly
|  | Joseph | Good Communication and decent break down of tasks | Did not reach hourly goals | Prioritize other work for progression of project
|  | Michael | Progress was made during break | Did not meet hourly goals | Work more regularly
8 |  | Albert | prioritized tasks well and helped each other out | We didn't update the status of tasks as often as we should have. | assigning tasks before begining working and continously marking when things are done
|  | Audrey | We had to adjust our sprint when met with an unexpected twist | we did not finish eveything we needed to this sprint | break down tasks more, fill out hours
|  | Brad | good integration of new members | Individual tasks may have been too large to be a decent task | Make planning more granular
|  | Devarsh | splitting works and helping each othher | didn't finished new features selections on time | try to have clear conversations before adding something which can help other to know what did u add
|  | Jacob | Handled giving tasks to new people in an efficient manner. | Underestimated new work loads and meeting times for 8 people. | Schedule meetings based on the majority of people's availability and start new tasks right away.
|  | Joseph | Creating new features with new members | Task was on a larger scale than had excpected and having to deal with other difficult classes | Doing more difficult tasks first if possible then moving to easier tasks
|  | Michael | Handled getting new members and shifting focus when needed | Still not completing all work assigned and staying on hourly track | Schedule things into sprint if they come up part of the way through
|  | SzeMan | Clear view on what task we need to do | Task took longer time to finish than expect | Update sprint daily
9 |  | Albert | met more as needed, communicated well | we worked on the sprint a lot more then orginially planned | Working at least an hour everyday on our own tasks and communicate every day to be aware of each others' progress
|  | Audrey | We broke down tasks more efficiently | due to changes from last sprint, it put us behind for this sprint and still feel like we are playing catch up | Prioritize work better in relation to outdiside forces, communicate with team members when not able to finish a task
|  | Brad | Better coordination on core features than in the past | Sprint planning had a small number of unnecessary/poorly defined tasks, leading to re-planning those tasks | Verify tasks with each group member at the end of sprint planning to confirm that everyone knows what they're doing and that each task makes sense
|  | Devarsh | finishing tasks on schedule | lack of communications | all the individual tasks need to discuss with team so all team member know what did you do during a week
|  | Jacob | Meetings were consistant and efficient | Underestimated work load from other classes | Focus more on work that can be finished rather than spending more time finishing an assignment that we are stuck on.
|  | Joseph | Change tasks for a better break down of previous tasks | Not being able to keep up with other classes work load | Focus on doable work where progress can be made
|  | Michael | Much more consistent meetings than in the past | Once we fell behind it was very difficult to catch back up | Get as much work done as possible even if it isn't everything
|  | SzeMan | scheduled new meetings to accomadate new people in group | underestimating time spent on work | have everyone update hours by 9 pm every day
10 |  | Albert
Audrey
Brad
Devarsh
Jacob
Joseph
Michael
SzeMan
11 |  | Albert
Audrey
Brad
Devarsh
Jacob
Joseph
Michael
SzeMan
12 |  | Albert
Audrey
Brad
Devarsh
Jacob
Joseph
Michael
SzeMan
13 |  | Albert
Audrey
Brad
Devarsh
Jacob
Joseph
Michael
SzeMan

## Sprint 6
Sprint 6
| Start Date | 2021-11-29 |  | Day of Sprint | Actual Effort |  |  | Day of Sprint | Forecast | Actual
| End Date | 2021-12-14 |  | 0 | 101 |  |  | 0 | 101 | 101
| Sprint Length | 16 |  | 1 | 98 |  |  | 1 | 94.6875 | 98
| Team Size | 5 |  | 2 | 92.5 |  |  | 2 | 88.375 | 92.5
| Team Capacity | 112 |  | 3 | 86.75 |  |  | 3 | 82.0625 | 86.75
| Total Sprint SP | 101 |  | 4 | 82.5 |  |  | 4 | 75.75 | 82.5
| SP/Day | 6.3125 |  | 5 | 81.5 |  |  | 5 | 69.4375 | 81.5
|  |  |  | 6 | 81.5 |  |  | 6 | 63.125 | 81.5
|  |  |  | 7 | 77.5 |  |  | 7 | 56.8125 | 77.5
|  |  |  | 8 | 74.5 |  |  | 8 | 50.5 | 74.5
|  |  |  | 9 | 68 |  |  | 9 | 44.1875 | 68
|  |  |  | 10 | 59.5 |  |  | 10 | 37.875 | 59.5
|  |  |  | 11 | 56.5 |  |  | 11 | 31.5625 | 56.5
|  |  |  | 12 | 49 |  |  | 12 | 25.25 | 49
|  |  |  | 13 | 42.5 |  |  | 13 | 18.9375 | 42.5
|  |  |  | 14 | 33.5 |  |  | 14 | 12.625 | 33.5
|  |  |  | 15 | 19 |  |  | 15 | 6.3125 | 19
|  |  |  | 16 | 0 |  |  | 16 | 0 | 0
|  |  |  | m | t | w | th | f | s | s | m | t | w | t | f | s | s | m | t
Who | Tasks | Day of Sprint (hours worked)
|  |  | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16
Albert
| UM interfaces to other components | 2 | 0 | 0 | 1 | 0 | 1.5 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0
| UM Feature Pseudocode | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0
| Registration (BRD) | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0
| Registration (Test Plan) | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0
| Review BRD, Tech Spec | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0
| UM Implementation: Update | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0
| UM Implementation: Execute bulk operations | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0
| Implemetation: Authorization | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0
| UM Tests: Bulk Operations | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3
| Tests: Authorization | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3
| Tests: Update | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0
SP Decrement |  |  | 0 | 0 | 0.5 | 1 | 1 | 0 | 0 | 0 | 0.5 | 1.5 | 1 | 0.5 | 3 | 3 | 3 | 3 | 3
Audrey
| UM sequence diagram | 4 | 0 | 2 | 0 | 2 | 2 | 0 | 0 | 0 | 4 | 3.5 | 0.5 | 1.5 | 0.5 | 0 | 0 | 0 | 0
| Compile UM LL Design Document | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 0 | 0 | 0.5 | 0 | 0 | 0 | 0
| Review LL Design Logging, Project Plan | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0.5
| UM Implementation: Model class: User Account | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0.25 | 0 | 0
| UM Implementation: Delete | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 2 | 1
| Implementation: Authentication | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 2 | 2 | 1
| Tests: Authenication | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
| BRD: User Access Control | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
| UM Tests: Delete | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
| BRD: Authorize | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0
| Test Cases: Authorize | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0
| Site Map: Authorize | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0
SP Decrement |  |  | 0 | 1 | 0 | 0.25 | 0.25 | 0 | 0 | 0 | 0.5 | 2 | 4 | 0.5 | 1.5 | 1.5 | 2 | 1.5 | 5
Brad
| Logging class diagram | 3.5 | 0 | 0 | 0 | 4 | 2 | 2 | 0 | 3 | 4 | 2 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0
| Tech Approval: Cron | 4 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Logging interfaces to other components | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Review LL Design UM, Network Diagram | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5
| Logging Implementation: Model class: Log | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0
| Logging Implementation | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 1
| Archiving Tests | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2
SP Decrement |  | 20 | 0 | 0 | 2 | 0.5 | 0.5 | 0.5 | 0 | 1 | 0.5 | 1 | 0 | 0 | 2 | 0 | 1 | 6 | 5
Joseph
| UM Business Requirements | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0
| Update BRD (feedback) | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0
| Tech Approval: ORM | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0
| UM Tests: Enable/disable | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 2
| User Access Control (Sitemap) | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 2
| User Access Control (Test Plan) | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 1 | 1 | 1 | 1 | 2
| Review Test Plan | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 0 | 1 | 1 | 0
| UM Implementation: Create | 1 | 0 | 3 | 2 | 3 | 1 | 3 | 0 | 3 | 2 | 0 | 2 | 0 | 2 | 0 | 1 | 1 | 2
| UM Implementation: Enable/disable | 1 | 0 | 2 | 2 | 3 | 1 | 3 | 0 | 3 | 2 | 0 | 1 | 1 | 2 | 0 | 1 | 0 | 2
| UM Tests: Create | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 1 | 2
| BRD: Account Deletion | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 1 | 2
| Test Cases: Acount Deletion | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
SP Decrement |  | 19 | 0 | 1 | 2 | 3 | 0.5 | 0 | 0 | 1 | 1 | 0 | 0.5 | 1 | 1 | 1 | 2 | 2 | 3
Michael
| Logging behavioral diagram | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Logging Feature Pseudocode | 2 | 0 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Compile Logging LL Design Document | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Update Test Plan (feedback) | 2 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Archiving (BRD) | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Archiving (Test Plan) | 1 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Review Site Map, HL Design | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0
| Archiving Implementation | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 2 | 0
| Logging Tests | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 5
| Tech Approval: Unit Tests | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 0
SP Decrement |  |  | 0 | 1 | 1 | 1 | 2 | 0.5 | 0 | 2 | 0.5 | 2 | 3 | 1 | 0 | 1 | 1 | 2 | 4
|  |  | 0 | 3 | 5.5 | 5.75 | 4.25 | 1 | 0 | 4 | 3 | 6.5 | 8.5 | 3 | 7.5 | 6.5 | 9 | 14.5 | 20
Daily Scrum Meeting
Day of Sprint | Who | What did you work on Yesterday? | 2: What are you working on today?; 5: Are You Blocked?
Day 1 | Albert | n/a | 2: UM interfaces to other components; 5: no
| Audrey | n/a | 2: UM sequence diagram; 5: no
| Brad | n/a | 2: n/a; 5: no
| Joseph | n/a | 2: UM Implementation: Create; 5: no
| Michael | n/a | 2: n/a; 5: no
Day 2 | Albert | UM interfaces to other components | 2: UM interfaces to other components; 5: no
| Audrey | UM sequence diagram | 2: n/a; 5: no
| Brad | n/a | 2: tech approval for unit testing; 5: no
| Joseph | UM Implementation: Create | 2: UM Implementation: Enable/disable; 5: yes
| Michael | n/a | 2: Archiving BRD; 5: no
Day 3 | Albert | UM interfaces to other components | 2: UM Feature Pseudocode; 5: no
| Audrey | n/a | 2: UM sequence diagram; 5: no
| Brad | tech approval for unit testing | 2: Logging design/tech research; 5: no
| Joseph | UM Implementation: Enable/disable | 2: UM Implementation: Create; 5: no
| Michael | Archiving BRD | 2: n/a; 5: no
Day 4 | Albert | UM Feature Pseudocode | 2: UM Feature Pseudocode; 5: no
| Audrey | UM sequence diagram | 2: UM sequence diagram; 5: no
| Brad | Logging design/tech research | 2: Logging tech research; 5: no
| Joseph | UM Implementation: Create | 2: UM Implementation: Enable/disable; 5: yes
| Michael | n/a | 2: Archiving Test Plan; 5: no
Day 5 | Albert | UM Feature Pseudocode | 2: Review BRD, Tech Spec
| Audrey | UM sequence diagram | 2: n/a; 5: no
| Brad | Logging tech research | 2: n/a; 5: no
| Joseph | UM Implementation: Enable/disable | 2: UM Implementation: Create; 5: no
| Michael | Archiving Test Plan | 2: Update Test Plan; 5: no
Day 6 | Albert | Review BRD, Tech Spec | 2: Review BRD, Tech Spec; 5: no
| Audrey | n/a | 2: n/a; 5: no
| Brad | n/a | 2: n/a; 5: no
| Joseph | n/a | 2: n/a; 5: no
| Michael | Update Test Plan (Feedback) | 2: Archiving Pseudocode; 5: no
Day 7 | Albert | Review BRD, Tech Spec | 2: Implemetation: Authorization; 5: no
| Audrey | n/a | 2: n/a; 5: no
| Brad | n/a | 2: Logging test research & prototype; 5: no
| Joseph | n/a | 2: UM Implementaton: Create; 5: no
| Michael | Archiving Pseudocode | 2: n/a; 5: no
Day 8 | Albert | Implemetation: Authorization | 2: Implemetation: Authorization; 5: no
| Audrey | n/a | 2: UM sequence diagram, LL design; 5: no
| Brad | Logging test research & prototype | 2: Logging LL design; 5: no
| Joseph | UM Implementaton: Create | bar: 5
| Michael | n/a | 2: logging behavioral diagram; 5: no
Day 9 | Albert | Implemetation: Authorization | 2: UM Tests: Bulk Operations; 5: no
| Audrey | UM sequence diagram, LL design | 2: UM sequence diagram, LL design, looking over documents; 5: no
| Brad | Logging LL design | 2: Logging, UM LL design; 5: no
Joseph | bar: 5
| Michael | logging behavioral diagram | 2: logging feature pseudocode; 5: no
Day 10 | Albert | UM Tests: Bulk Operations | 2: UM Tests: Bulk Operations; 5: no
| Audrey | UM sequence diagram, LL design, looking over documents | 2: sequence diagram, other document checking, authorzie; 5: no
| Brad | Logging, UM LL design | 2: logging class diagram; 5: no
| Joseph | UM Tests: Bulk Operations | 2: UM Tests: Bulk Operations; 5: no
| Michael | loggind feature pseudocode | 2: Logging Tests; 5: no
Day 11 | Albert | UM Tests: Bulk Operations | 2: Tests: Update; 5: no
| Audrey | sequence diagram, other document checking, authorzie | 2: sequence diagram, other document checking; 5: no
| Brad | n/a | 2: logging class diagram; 5: no
Joseph | bar: 5
| Michael | Logging Tests | 2: Archiving; 5: no
Day 12 | Albert | Tests: Update | 2: Tests: Authorization; 5: no
| Audrey | sequence diagram, other document checking | 2: UM sequence diagram LLdesign; 5: no
| Brad | logging class diagram | 2: logging class diagram & log class for logging implementation; 5: no
| Joseph | UM implentation | 2: Um implementaiton; 5: no
| Michael | Archivng | 2: Test Plan; 5: no
Day 13 | Albert | Tests: Authorization | 2: UM Tests: Bulk Operations; 5: no
| Audrey | UM sequence diagram LLdesign | 2: UM sequence diagram LLdesign; 5: yes
| Brad | logging class diagram & log class for logging implementation | 2: log class for logging implementation; 5: no
| Joseph | Um implementaiton | 2: um tests: Bulk Operations; 5: no
| Michael | Test Plan | 2: archiving; 5: no
Day 14 | Albert | UM Tests: Bulk Operations | 2: UM Implementation: Execute bulk operations; 5: no
| Audrey | UM sequence diagram LLdesign | 2: UM IMlementation; 5: no
| Brad | n/a | 2: log class for logging implementation; 5: no
| Joseph | UM Implementation | 2: UM Implementation; 5: no
| Michael | archiving | 2: logging tests; 5: no
Day 15 | Albert | UM Implementation: Execute bulk operations | 2: Registration (BRD); 5: no
| Audrey | UM IMlementation | 2: UM implementaiton, UM Tests; 5: no
| Brad | log class for logging implementation | 2: logging implementation; 5: no
| Joseph | UM Implementation | 2: UM tests; 5: no
| Michael | logging tests | 2: archiving implementation; 5: no
Day 16 | Albert | Registration (BRD) | 2: Registration (Test Plan); 5: no
| Audrey | UM implementaiton, UM Tests | 2: UM Tests; 5: no
| Brad | logging implementation | 2: logging implementation, archiving tests; 5: no
| Joseph | UM tests | 2: UM Tests; 5: no
| Michael | archiving implementation | 2: logging tests; 5: no

## Sprint 5
Sprint 5
| Start Date | 2021-11-15 |  | Day of Sprint | Actual Effort |  |  | Day of Sprint | Forecast | Actual
| End Date | 2021-11-24 |  | 0 | 94.5 |  |  | 0 | 94.5 | 94.5
| Sprint Length | 10 |  | 1 | 88.5 |  |  | 1 | 85.05 | 88.5
| Team Size | 5 |  | 2 | 83.25 |  |  | 2 | 75.6 | 83.25
| Team Capacity | 100 |  | 3 | 75 |  |  | 3 | 66.15 | 75
| Total Sprint SP | 94.5 |  | 4 | 72.5 |  |  | 4 | 56.7 | 72.5
| SP/Day | 9.45 |  | 5 | 67.25 |  |  | 5 | 47.25 | 67.25
|  |  |  | 6 | 61.25 |  |  | 6 | 37.8 | 61.25
|  |  |  | 7 | 53.5 |  |  | 7 | 28.35 | 53.5
|  |  |  | 8 | 49.25 |  |  | 8 | 18.9 | 49.25
|  |  |  | 9 | 45.75 |  |  | 9 | 9.45 | 45.75
|  |  |  | 10 | 33 |  |  | 10 | 0 | 33
|  |  |  | m | t | w | th | f | s | s | m | t | w
Who | Tasks | SP | Day of Sprint (hours worked)
|  |  | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10
Albert
| Logging test plan | 0.5 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Error Handling (BRD) | 2 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Error Handling (Sitemap) | 2 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0
| Error Handling (Test Plan) | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0
| UM interfaces to other components | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| UM Feature Pseudocode | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Update Network Diagram (feedback) | 2 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1
| Registration (BRD) | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Registration (Test Plan) | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SP Decrement |  |  | 0 | 1.5 | 1.25 | 1.25 | 0 | 2 | 2 | 2 | 0.5 | 0.5 | 1.5
Audrey
| UM sequence diagram | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0
| Compile UM LL Design Document | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0
| Update Site Map (feedback) | 2 | 0 | 0.75 | 0.5 | 0.25 | 0 | 0 | 1 | 0 | 0 | 0 | 1
| Update Tech Spec (feedback) | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 2
| Usage Analysis Dashboard (BRD) | 2 | 0 | 0 | 0.5 | 0.5 | 0 | 0 | 0.5 | 0 | 0 | 0 | 0.5
| Usage Analysis Dashboard (Test Plan) | 2 | 0 | 0 | 0 | 0.25 | 0 | 0 | 0.5 | 1 | 0 | 0 | 0.5
| User Management (Sitemap) | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5
| Login (BRD) | 1 | 0 | 0.75 | 1 | 0.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Login (Test Plan) | 1 | 0 | 0 | 0 | 0.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SP Decrement |  |  | 0 | 0.5 | 1 | 2.5 | 0 | 0 | 1 | 1 | 0 | 1 | 6
Brad
| Logging Business Requirements | 1 | 0 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Logging class diagram | 7 | 0 | 0 | 0 | 0.5 | 1 | 0.5 | 0 | 0 | 0 | 0 | 0
| Logging interfaces to other components | 1 | 0 | 0 | 0 | 0.5 | 1 | 0.5 | 0 | 0 | 0 | 0 | 0
| Update HL Design (feedback) | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 0
| Update Project Plan (feedback) | 2 | 0 | 0 | 0 | 0.5 | 0 | 0 | 0.25 | 1 | 0 | 0 | 0
| Logging (Sitemap) | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0.25 | 0 | 0.25 | 0 | 0
| Usage Analysis Dashboard (Sitemap) | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0.5 | 0.5 | 0 | 0
| Logout (BRD) | 1 | 0 | 0 | 0.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Logout (Test Plan) | 1 | 0 | 0 | 0.25 | 0 | 0 | 0 | 0 | 0.25 | 0 | 0 | 0
SP Decrement |  |  | 0 | 0 | 2 | 3 | 2 | 2 | 1.5 | 2.25 | 2.25 | 0 | 0
Joseph
| UM Business Requirements | 1 | 0 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| UM Site Map | 2 | 0 | 0.5 | 0 | 0.5 | 0 | 0.5 | 0 | 0 | 0.25 | 0 | 0.5
| UM class diagram (UML) | 8 | 0 | 0.5 | 0 | 0.5 | 0 | 0.5 | 0 | 0 | 0.25 | 0.5 | 4
| Update BRD (feedback) | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| User Access Control (BRD) | 2 | 0 | 0 | 0 | 0 | 0 | 0.25 | 0 | 0.5 | 0 | 0 | 0
| User Access Control (Sitemap) | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0.25 | 0 | 0 | 0 | 0
| User Access Control (Test Plan) | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0.25 | 0 | 0.25 | 0.25 | 0
SP Decrement |  |  | 0 | 2 | 0.5 | 1 | 0 | 0.75 | 0.5 | 0.5 | 0.5 | 1 | 4.25
Michael
| Logging behavioral diagram | 3 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Logging Feature Pseudocode | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1
| Compile Logging LL Design Document | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Update Test Plan (feedback) | 2 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0
| Archiving (BRD) | 2 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Archiving (Sitemap) | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Archiving (Test Plan) | 2 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0
SP Decrement |  |  | 0 | 2 | 0.5 | 0.5 | 0.5 | 0.5 | 1 | 2 | 1 | 1 | 1
|  |  | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10
Daily Scrum Meeting
Day of Sprint | Who | What did you work on Yesterday? | 2: What are you working on today?; 5: Are You Blocked?
Day 1 | Albert | n/a | 2: logging test plan; 5: no
| Audrey | n/a | 2: feedback for site map, Login BRD; 5: no
| Brad | n/a | 2: n/a; 5: no
| Joseph | n/a | 2: UM site map, UM class diagram; 5: no
| Michael | n/a | 2: logging behavior diagram, archiving BRD; 5: no
Day 2 | Albert | logging test plan | 2: logging test plan, error handling BRD; 5: no
| Audrey | n/a | 2: feedback for site map, BRD for login and usage management dashboard; 5: no
| Brad | n/a | 2: BRD (Logging, logout), test plan (logout), logging class diagram; 5: no
| Joseph | UM site map, UM class diagram | 2: UM business requirements; 5: no
| Michael | logging behavior diagram, archiving BRD | 2: archiving BRD; 5: no
Day 3 | Albert | logging test plan, error handling BRD | 2: logging test plan, error handling site map; 5: no
| Audrey | feedback for site map, BRD for login and usage management dashboard | 2: feedback for site map, BRD for login and usage management dashboard, test cases for login and UMD; 5: no
| Brad | BRD (Logging, logout), test plan (logout), logging class diagram | 2: feedback (project plan); 5: no
| Joseph | UM business requirements | 2: UM site map, UM class diagram; 5: no
| Michael | archiving BRD | 2: archiving test plan; 5: no
Day 4 | Albert | logging test plan, error handling site map | 2: n/a; 5: no
| Audrey | feedback for site map, BRD for login and usage management dashboard, test cases for login and UMD | 2: n/a; 5: no
| Brad | feedback (project plan) | 2: logging class diagrams, logging to other interfaces; 5: no
| Joseph | UM site map, UM class diagram | 2: n/a; 5: no
| Michael | archiving test plan | 2: n/a; 5: no
Day 5 | Albert | n/a | 2: error handling site map, update network diagram; 5: no
| Audrey | n/a | 2: n/a; 5: no
| Brad | logging class diagrams, logging to other interfaces | 2: logging class diagrams, logging to other interfaces; 5: no
| Joseph | n/a | 2: UM site map, UM class diagram, user access control brd; 5: no
| Michael | n/a | 2: update test plan; 5: no
Day 6 | Albert | error handling site map, update network diagram | 2: error handling site map, update network diagram; 5: no
| Audrey | n/a | 2: update site map, usage analysis dashboard brd and test plan; 5: no
| Brad | logging class diagrams, logging to other interfaces | 2: update project plan, sitemap for looging and usage analysis dashboard; 5: no
| Joseph | UM site map, UM class diagram, user access control brd | 2: user access control test plan and sitemap; 5: no
| Michael | update test plan | 2: update test plan; 5: no
Day 7 | Albert | error handling site map, update network diagram | 2: error handling site map, update network diagram; 5: no
| Audrey | update site map, usage analysis dashboard brd and test plan | 2: update tech spec, usage analysis dashboard test plan; 5: no
| Brad | update project plan, sitemap for looging and usage analysis dashboard | 2: update project plan, sitemap for usage analysis dashboard, logout test plan; 5: no
| Joseph | user access control test plan and sitemap | 2: user access control brd; 5: no
| Michael | update test plan | 2: update test plan; 5: no
Day 8 | Albert | error handling site map, update network diagram | 2: update network diagram; 5: no
| Audrey | update tech spec, usage analysis dashboard test plan | 2: n/a; 5: no
| Brad | update project plan, sitemap for usage analysis dashboard, logout test plan | 2: update HL design, sitemap for logging and usage analysis dashboard; 5: no
| Joseph | user access control brd | 2: UM site map and class diagram, user access control test plan; 5: no
| Michael | update test plan | 2: logging pseudocode; 5: no
Day 9 | Albert | update network diagram | 2: update network diagram; 5: no
| Audrey | n/a | 2: UM sequence diagram, compile LL desgin UM; 5: no
| Brad | update HL design, sitemap for logging and usage analysis dashboard | 2: n/a; 5: no
| Joseph | UM site map and class diagram, user access control test plan | 2: UM class diagram, user access control test plan; 5: no
| Michael | logging pseudocode | 2: logging pseudocode; 5: no
Day 10 | Albert | update network diagram | 2: update network diagram; 5: no
| Audrey | UM sequence diagram, compile LL desgin UM | 2: update tech spec and site map, UAD test plan, BRD,UM site map; 5: no
| Brad | n/a | 2: n/a; 5: no
| Joseph | UM class diagram, user access control test plan | 2: UM site map and class diagram; 5: no
| Michael | logging pseudocode | 2: logging pseudocode; 5: no

## Sprint 4
Sprint 4
| Start Date | 2021-11-05 |  | Day of Sprint | Actual Effort |  |  | Day of Sprint | Forecast | Actual
| End Date | 2021-11-12 |  | 0 | 71 |  |  | 0 | 71 | 71
| Sprint Length | 8 |  | 1 | 69 |  |  | 1 | 62.125 | 69
| Team Size | 5 |  | 2 | 69 |  |  | 2 | 53.25 | 69
| Team Capacity | 80 |  | 3 | 69 |  |  | 3 | 44.375 | 69
| Total Sprint SP | 71 |  | 4 | 65.5 |  |  | 4 | 35.5 | 65.5
| SP/Day | 8.875 |  | 5 | 63.5 |  |  | 5 | 26.625 | 63.5
|  |  |  | 6 | 57.5 |  |  | 6 | 17.75 | 57.5
|  |  |  | 7 | 53.5 |  |  | 7 | 8.875 | 53.5
|  |  |  | 8 | 46.5 |  |  | 8 | 0 | 46.5
|  |  |  | f | s | s | m | t | w | t | f
Who | Tasks | SP | Day of Sprint (hours worked)
|  |  | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8
Albert
| Logging test plan | 4 | 0 | 1 | 0 | 0 | 2 | 0 | 1.5 | 1 | 1
| UM interfaces to other components | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| UM Feature Pseudocode | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SP Decrement |  |  | 0 | 0.5 | 0 | 0 | 1 | 0 | 1 | 0.5 | 0.5
Audrey
| UM test plan | 4 | 0 | 1 | 0 | 0 | 1.5 | 0 | 1.5 | 2.5 | 1
| UM sequence diagram | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0.5 | 2.5
| Compile UM LL Design Document | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5
SP Decrement |  |  | 0 | 0.5 | 0 | 0 | 0.5 | 0 | 1 | 1.5 | 3.5
Brad
| Logging Business Requirements | 4 | 0 | 1 | 0 | 0.25 | 1 | 0 | 1 | 0 | 0
| Logging class diagram | 8 | 0 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 2.5
| Logging interfaces to other components | 2 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 1.75
SP Decrement |  |  | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 2
Joseph
| UM Business Requirements | 4 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0
| UM Site Map | 3 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1
| UM class diagram (UML) | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1
SP Decrement |  |  | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1
Michael
| Logging behavioral diagram | 8 | 0 | 0 | 0 | 0 | 3 | 2 | 3 | 2 | 0
| Logging Feature Pseudocode | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Compile Logging LL Design Document | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SP Decrement |  |  | 0 | 0 | 0 | 0 | 1 | 1 | 2 | 1 | 0
Daily Scrum Meeting
Day of Sprint | Who | What did you work on Yesterday? | Day of Sprint (hours worked) 2: What are you working on today?; Day of Sprint (hours worked) 5: Are You Blocked?
Day 1 | Albert | n/a | Day of Sprint (hours worked) 2: logging test plan; Day of Sprint (hours worked) 5: No
| Audrey | n/a | Day of Sprint (hours worked) 2: um test plan; Day of Sprint (hours worked) 5: no
| Brad | n/a | Day of Sprint (hours worked) 2: Logging business requirements; Day of Sprint (hours worked) 5: No
| Joseph | n/a | Day of Sprint (hours worked) 2: Um business requirements; Day of Sprint (hours worked) 5: no
| Michael | n/a | Day of Sprint (hours worked) 2: n/a; Day of Sprint (hours worked) 5: yes
Day 2 | Albert | logging test plan | Day of Sprint (hours worked) 2: n/a; Day of Sprint (hours worked) 5: No
| Audrey | um test plan | Day of Sprint (hours worked) 2: n/a; Day of Sprint (hours worked) 5: no
| Brad | Logging business requirements | Day of Sprint (hours worked) 2: n/a; Day of Sprint (hours worked) 5: No
| Joseph | Um business requirements | Day of Sprint (hours worked) 2: UM business requirements; Day of Sprint (hours worked) 5: No
| Michael | n/a | Day of Sprint (hours worked) 2: n/a; Day of Sprint (hours worked) 5: yes
Day 3 | Albert | n/a | Day of Sprint (hours worked) 2: n/a; Day of Sprint (hours worked) 5: Yes
| Audrey | n/a | Day of Sprint (hours worked) 2: n/a; Day of Sprint (hours worked) 5: no
| Brad | n/a | Day of Sprint (hours worked) 2: Logging business requirements; Day of Sprint (hours worked) 5: No
| Joseph | UM business requirements | Day of Sprint (hours worked) 2: UM Business Requirments; Day of Sprint (hours worked) 5: No
| Michael | n/a | Day of Sprint (hours worked) 2: Logging Behavioral Diagram; Day of Sprint (hours worked) 5: yes
Day 4 | Albert | n/a | Day of Sprint (hours worked) 2: logging test plan; Day of Sprint (hours worked) 5: No
| Audrey | n/a | Day of Sprint (hours worked) 2: um test plan; Day of Sprint (hours worked) 5: no
| Brad | Logging business requirements | Day of Sprint (hours worked) 2: Logging business requirements; Day of Sprint (hours worked) 5: No
| Joseph | UM Business Requirments | Day of Sprint (hours worked) 2: UM Business Requirments, UM site map; Day of Sprint (hours worked) 5: No
| Michael | Logging Behavioral Diagram | Day of Sprint (hours worked) 2: Logging Behavioral Diagram; Day of Sprint (hours worked) 5: no
Day 5 | Albert | logging test plan | bar: Day of Sprint (hours worked) 5
| Audrey | um test plan | Day of Sprint (hours worked) 2: n/a; Day of Sprint (hours worked) 5: no
| Brad | Logging business requirements | Day of Sprint (hours worked) 2: n/a; Day of Sprint (hours worked) 5: no
| Joseph | UM Business Requirments, UM site map | Day of Sprint (hours worked) 2: UM Business Requirments, UM site map; Day of Sprint (hours worked) 5: No
| Michael | Logging Behavioral Diagram | Day of Sprint (hours worked) 2: Logging Behavioral Diagram; Day of Sprint (hours worked) 5: no
Day 6 | Albert | n/a | Day of Sprint (hours worked) 2: logging test plan; Day of Sprint (hours worked) 5: no
| Audrey | n/a | Day of Sprint (hours worked) 2: um test plan, um sequence diagram; Day of Sprint (hours worked) 5: no
| Brad | n/a | Day of Sprint (hours worked) 2: logging: class info, LL design; Day of Sprint (hours worked) 5: no
| Joseph | UM Business Requirments, UM site map | Day of Sprint (hours worked) 2: UM site map, class design; Day of Sprint (hours worked) 5: no
| Michael | Logging Behavioral Diagram | Day of Sprint (hours worked) 2: logging behavioral diagram; Day of Sprint (hours worked) 5: no
Day 7 | Albert | logging test plan | Day of Sprint (hours worked) 2: logging test plan; Day of Sprint (hours worked) 5: no
| Audrey | um test plan, um sequence diagram | Day of Sprint (hours worked) 2: um test plan, um sequence diagram; Day of Sprint (hours worked) 5: yes
| Brad | logging: class info, LL design | Day of Sprint (hours worked) 2: n/a; Day of Sprint (hours worked) 5: no
| Joseph | UM site map, class design | Day of Sprint (hours worked) 2: UM site map, class design; Day of Sprint (hours worked) 5: no
| Michael | logging behavioral diagram | Day of Sprint (hours worked) 2: logging behavioral diagram; Day of Sprint (hours worked) 5: no
Day 8 | Albert | logging test plan | Day of Sprint (hours worked) 2: logging test plan; Day of Sprint (hours worked) 5: no
| Audrey | um test plan, um sequence diagram | Day of Sprint (hours worked) 2: um test plan, um sequence diagram, LL desgin; Day of Sprint (hours worked) 5: yes
| Brad | n/a | Day of Sprint (hours worked) 2: logging: LL design & class info; Day of Sprint (hours worked) 5: no
| Joseph | UM site map, class design | Day of Sprint (hours worked) 2: UM site map, class design; Day of Sprint (hours worked) 5: no
| Michael | logging behavioral diagram | Day of Sprint (hours worked) 2: n/a; Day of Sprint (hours worked) 5: no

## Sprint 3
Sprint 3 | milestone 2
| Start Date | 2021-10-21 |  | Day of Sprint | Actual Effort |  |  | Day of Sprint | Forecast | Actual
| End Date | 2021-10-26 |  | 0 | 72 |  |  | 0 | 72 | 72
| Sprint Length | 6 |  | 1 | 70 |  |  | 1 | 60 | 70
| Team Size | 5 |  | 2 | 60 |  |  | 2 | 48 | 60
| Team Capacity | 90 |  | 3 | 53.5 |  |  | 3 | 36 | 53.5
| Total Sprint SP | 72 |  | 4 | 37.5 |  |  | 4 | 24 | 37.5
| SP/Day | 12 |  | 5 | 20 |  |  | 5 | 12 | 20
|  |  |  | 6 | 0 |  |  | 6 | 0 | 0
|  |  |  | th | f | s | s | m | t
Who | Tasks | SP | Day of Sprint (hours worked)
|  |  | 0 | 1 | 2 | 3 | 4 | 5 | 6
Albert
| Test case datastudent discounts, careers | 2 | 0 | 0 | 0 | 0 | 4 | 1 | 0
| IPs/URLs of external servers | 4 | 0 | 0 | 2 | 3 | 2 | 2 | 0
| Network Diagram: 3rd party services & servers | 4 | 0 | 0 | 0 | 0 | 2 | 2 | 0
| Schedule Sprints | 2 | 0 | 0 | 0 | 0 | 0 | 1 | 0
| Generate Roadmap from schedule | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 4
SP Decrement |  |  | 0 | 0 | 1 | 1 | 4 | 4 | 4
Audrey
| Test case data: matching, messaging | 2 | 0 | 0 | 2 | 1 | 2 | 0 | 0
| Network Diagram: Requests | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 3
| Determine critical path tasks | 4 | 0 | 0 | 0 | 1 | 2 | 2 | 3
| Test plan: testing schedule | 4 | 0 | 0 | 0 | 0.5 | 0 | 1.5 | 2
SP Decrement |  |  | 0 | 0 | 1 | 2 | 4 | 3 | 4
Brad
| Choose server provider | 4 | 0 | 1.5 | 1 | 0 | 0 | 0 | 0
| Test case data: schedules, classes | 2 | 0 | 0 | 2 | 0.5 | 2.75 | 0 | 0
| Determine feature development order | 4 | 0 | 0 | 0 | 0 | 2 | 2 | 0.5
| Validate schedule with team | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0.5
| Risk Identification | 3 | 0 | 0 | 0.5 | 0 | 0 | 0.75 | 0
| Other | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2
SP Decrement |  |  | 0 | 2 | 3 | 0.5 | 3 | 4.5 | 1
Joseph
| Information gathering: aid, careers, schedule of classes | 4 | 0 | 0 | 4 | 1.5 | 1 | 0 | 0
| Test case data: aid | 2 | 0 | 0 | 2 | 2 | 1.5 | 1.5 | 2
| Network Diagram: Node system specs | 2 | 0 | 0 | 0.5 | 1.5 | 1 | 1.5 | 2
| Schedule Project Milestones | 2 | 0 | 0 | 0 | 0 | 0.5 | 0.5 | 1.5
| Progression and Regression Testing details | 4 | 0 | 0 | 0 | 0 | 0 | 1.5 | 2
SP Decrement |  |  | 0 | 0 | 4 | 2 | 2 | 2 | 4
Michael
| Test case data: course rating, registration, login, logout | 2 | 0 | 0 | 2 | 1 | 0 | 2 | 0
| Network Diagram: Responses | 4 | 0 | 0 | 0 | 0 | 2 | 2 | 0
| Plan deployment process | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 4
| Detail testing environment | 4 | 0 | 0 | 0 | 0 | 0 | 2 | 3
| Risk Mitigation | 2 | 0 | 0 | 0 | 0 | 2 | 0 | 3
SP Decrement |  |  | 0 | 0 | 1 | 1 | 3 | 4 | 7
Daily Scrum Meeting
Day of Sprint | Who | What did you work on Yesterday? |  |  | What are you working on today? |  |  | Are You Blocked?
Day 1 | Albert | n/a |  |  | n/a |  |  | no
| Audrey | n/a |  |  | n/a |  |  | no
| Brad | n/a |  |  | choose service provider |  |  | no
| Joseph | n/a |  |  | n/a |  |  | no
| Michael | n/a |  |  | n/a |  |  | no
Day 2 | Albert | n/a |  |  | ip/urls |  |  | no
| Audrey | n/a |  |  | test cases |  |  | no
| Brad | choose service provider |  |  | choose service provider, test cases, risk identification |  |  | no
| Joseph | n/a | [5 empty] | no
| Michael | n/a |  |  | test cases |  |  | no
Day 3 | Albert | ip/urls |  |  | test cases, network diagram |  |  | no
| Audrey | test cases |  |  | test cases, gnatt chart |  |  | no
| Brad | choose service provider, test cases, risk identification |  |  | test cases |  |  | no
| Joseph | [6 empty] | no
| Michael | test cases |  |  | test cases |  |  | no
Day 4 | Albert | test cases, network diagram |  |  | test cases, network diagram |  |  | no
| Audrey | test cases, gnatt chart |  |  | test cases, critical path |  |  | no
| Brad | test cases |  |  | test cases, feature development order |  |  | no
| Joseph |  |  |  | test cases, phone call, emails, research specs |  |  | no
| Michael | test cases |  |  | test cases, looking at risk identification |  |  | no
Day 5 | Albert | test cases, network diagram |  |  | schedule sprint, network diagram |  |  | yes
| Audrey | test cases, critical path |  |  | testing scedule, critical path, requests |  |  | no
| Brad | test cases, feature development order |  |  | more feature development order, risk, validate schedule |  |  | no
| Joseph | test cases, phone call, emails, research specs |  |  | test cases, specs, emails |  |  | yes
| Michael | test cases, looking at risk identification |  |  | test cases, risk mitagation |  |  | no
Day 6 | Albert | schedule sprint, network diagram |  |  | roadmap |  |  | no
| Audrey | testing scedule, critical path, requests |  |  | requests, critical path, testing schedule |  |  | no
| Brad | more feature development order, risk, validate schedule |  |  | feature development order, validate schedule, other |  |  | no
| Joseph | test cases, specs, emails | [5 empty] | no
| Michael | test cases, risk mitagation |  |  | plan deployment process, testing enviornment, risk mitagation |  |  | no

## Story Point Breakdown (hidden)
Sprint 0 | total = 30
SP
| Proposal |  |  | 30
|  | Features | 24
|  | Needs/Problems | 2
|  | Goals/Solution | 2
|  | Obstacles & Solutions | 2
30
Sprint 1 | total = 35
SP
| BRD |  |  | 37
|  | Summary, Glossary, Appendix | 3
|  | Requirements | 18
|  | Processes | 14
|  | In and out of scope | 2
| Tech Spec |  |  | 4
|  | OS | 1
|  | Product | 2
|  | Project | 1
| Site Map |  |  | 8
|  | Design | 5
|  | Errors | 3
| HL Design |  |  | 7
|  | Software | 3.5
|  | Hardware | 3.5
56
Sprint 2 | total =
SP

## Sprint 2
Sprint 2 | test plan
| Start Date | 2021-10-13 |  | Day of Sprint | Actual Effort |  |  | Day of Sprint | Forecast | Actual Effort
| End Date | 2021-10-18 |  | 0 | 30 |  |  | 0 | 30 | 30
| Sprint Length | 6 |  | 1 | 30 |  |  | 1 | 25 | 30
| Team Size | 5 |  | 2 | 30 |  |  | 2 | 20 | 30
| Team Capacity | 30 |  | 3 | 22 |  |  | 3 | 15 | 22
| Total Sprint SP | 30 |  | 4 | 16 |  |  | 4 | 10 | 16
| SP/Day | 5 |  | 5 | 6 |  |  | 5 | 5 | 6
|  |  |  | 6 | 0 |  |  | 6 | 0 | 0
|  |  |  | w | th | f | s | s | m
Who | Tasks | SP | Day of Sprint (hours worked)
|  |  | 0 | 1 | 2 | 3 | 4 | 5 | 6
Albert
| Test cases: Discounts | 3 | 0 | 0 | 0 | 0 | 2 | 1 | 0
| Test cases: Careers | 3 | 0 | 0 | 0 | 0 | 1 | 2 | 3
SP Decrement |  |  | 0 | 0 | 0 | 0 | 2 | 2 | 2
Audrey
| Test cases: Matching | 3 | 0 | 0 | 0 | 4 | 1 | 1 | 1
| Test cases: Messaging | 3 | 0 | 0 | 0 | 0 | 2 | 1 | 1
SP Decrement |  |  | 0 | 0 | 0 | 3 | 2 | 1 | 0
Brad
| Test cases: Schedule Building | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 1
| Test cases: Schedule of Classes | 3 | 0 | 0 | 0 | 0 | 0 | 1 | 1
SP Decrement |  |  | 0 | 0 | 0 | 1 | 0 | 3 | 2
Joseph
| Phone calls: career center | 1 | 0 | 0 | 0 | 2 | 0 | 0 | 1
| Phone calls: financial aid | 1 | 0 | 0 | 0 | 2 | 0 | 0 | 1
| Phone calls: David Brown (SoC) | 1 | 0 | 0 | 0 | 3 | 0.5 | 0 | 1
| Test cases: Aid | 3 | 0 | 0 | 0 | 1 | 0 | 1 | 1
SP Decrement |  |  | 0 | 0 | 0 | 3 | 1 | 1 | 1
Michael
| Test cases: Course Difficulty | 3 | 0 | 0 | 0 | 0 | 0 | 2 | 1
| Test cases: Registration | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0
| Test cases: Login | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0
| Test cases: Logout | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
SP Decrement |  |  | 0 | 0 | 0 | 1 | 1 | 3 | 1
Daily Scrum Meeting
Day of Sprint | Who | What did you work on Yesterday? |  |  | What are you working on today? |  |  | Are You Blocked?
Day 1 | Albert | n/a |  |  | n/a |  |  | no
| Audrey | n/a |  |  | n/a |  |  | no
| Brad | n/a |  |  | n/a |  |  | no
| Joseph | n/a |  |  | n/a |  |  | no
| Michael | n/a |  |  | n/a |  |  | no
Day 2 | Albert | n/a |  |  | n/a |  |  | no
| Audrey | n/a |  |  | n/a |  |  | no
| Brad | n/a |  |  | n/a |  |  | no
| Joseph | n/a |  |  | n/a |  |  | no
| Michael | n/a |  |  | n/a |  |  | no
Day 3 | Albert | n/a |  |  | n/a |  |  | no
| Audrey | n/a |  |  | match test cases |  |  | no
| Brad | n/a |  |  | schedule builder test cases |  |  | no
| Joseph | n/a |  |  | phone calls, aid test cases |  |  | yes
| Michael | n/a |  |  | registration test cases |  |  | no
Day 4 | Albert | n/a |  |  | career opps, student discounts test cases |  |  | no
| Audrey | match test cases |  |  | messaging, matching test cases |  |  | no
| Brad | schedule builder test cases |  |  | n/a |  |  | no
| Joseph | phone calls, aid test cases |  |  | phone calls |  |  | yes
| Michael | registration test cases |  |  | login test cases |  |  | no
Day 5 | Albert | career opps, student discounts test cases |  |  | discounts, careers test cases |  |  | yes
| Audrey | messaging, matching test cases |  |  | messaging, matching test cases |  |  | no
| Brad | n/a |  |  | schedule building, schedule of classes test cases |  |  | no
| Joseph | phone calls |  |  | aid test cases |  |  | yes
| Michael | login test cases |  |  | course reviews, logout test cases |  |  | no
Day 6 | Albert | discounts, careers test cases |  |  | careers test cases |  |  | no
| Audrey | messaging, matching test cases |  |  | messaging, matching test cases |  |  | no
| Brad | schedule building, schedule of classes test cases |  |  | schedule building, schedule of classes test cases |  |  | no
| Joseph | aid test cases |  |  | aid test cases, phone calls |  |  | no
| Michael | course reviews, logout test cases |  |  | course reviews test cases |  |  | no

## Sprint 1
Sprint 1 | milestone 1
| Start Date | 2021-09-29 |  | Day of Sprint | Actual Effort |  | Day of Sprint | Forecast | Actual Effort
| End Date | 2021-10-05 |  | 0 | 56.5 |  | 0 | 56.5 | 56.5
| Sprint Length | 7 |  | 1 | 53 |  | 1 | 48.4286 | 52
| Team Size | 5 |  | 2 | 53 |  | 2 | 40.3571 | 52
| Team Capacity | 60 |  | 3 | 45 |  | 3 | 32.2857 | 44
| Total Sprint SP | 56.5 |  | 4 | 40 |  | 4 | 24.2143 | 38
| SP/Day | 8.0714 |  | 5 | 26 |  | 5 | 16.1429 | 25
|  |  |  | 6 | 15 |  | 6 | 8.0714 | 14
|  |  |  | 7 | 0 |  | 7 | 0 | 0
Who | Tasks | SP | Day of Sprint (hours worked)
|  |  | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7
Albert
| Process - Student Discounts | 2 | 0 | 1 | 0 | 1 | 0 | 0 | 1 | 0
| Process - Career Opp | 2 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1
| Requirements - Student Discounts | 2 | 0 | 1 | 0 | 0 | 2 | 2 | 1 | 1
| Requirements - Career Opps | 2 | 0 | 0 | 0 | 1 | 1 | 2 | 0 | 1.5
| View - Student Discounts | 0.5 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0.5
| View - Career Opps | 0.5 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0
| OS Requirement | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2
SP Decrement |  |  | 0 | 1 | 0 | 2 | 1 | 2 | 1 | 3
Audrey
| Glossary | 0.5 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0
| Document Version | 0.5 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0
| In Scope | 1 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 0
| Process - Matching | 2 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1
| Requirements - Matching | 2 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1
| View - Matching | 0.5 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1
| Error Hangling | 4 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 2
| Project Requirements | 1.5 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1
SP Decrement |  |  | 0 | 1 | 0 | 2 | 1 | 3 | 3 | 2
Brad
| Process - Comparison | 2 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0
| Process - Builder | 2 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0
| Requirements - Comparison | 2 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 1
| Requirements - Builder | 2 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 2
| Requirements - Messaging | 2 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0
| View - Comparison | 0.5 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1
| View - Messaging | 0.5 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0
| View - Builder | 0.5 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1
| Hardware | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1
| Software | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1
| Choosing Hardware and Software | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0
SP Decrement |  |  | 0 | 1 | 0 | 1 | 2 | 5 | 4 | 5.5
Joseph
| Executive Summary | 0.5 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0
| Project Description | 0.5 | 0 | 0.5 | 0 | 0.5 | 0 | 0 | 0 | 0
| Process - Aid | 2 | 0 | 1 | 0 | 1.5 | 1 | 2 | 2 | 2
| Requirement - Aid | 2 | 0 | 1 | 0 | 0 | 2 | 1 | 2 | 2
| View - Aid | 0.5 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 2
SP Decrement |  |  | 0 | 0.5 | 0 | 1 | 1 | 1 | 1 | 1
Michael
| Out of Scope | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1
| Process - Course Difficulty | 2 | 0 | 2 | 0 | 1 | 1 | 0 | 1 | 1
| Requirements - Course Difficulty | 2 | 0 | 1 | 0 | 2 | 1 | 0 | 1 | 2
| Requirements - Schedule of Classes | 2 | 0 | 0 | 0 | 2 | 1 | 2 | 0 | 0
| Requirements - Core | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0
| View - Schule of Classes | 0.5 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0
| View - Course Difficulty | 0.5 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 1
| Product Requirements | 1.5 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0
SP Decrement |  |  | 0 | 1 | 0 | 2 | 1 | 2 | 2 | 2.5

## Sprint 0
Sprint 0 | proposal | [5 empty] | Day of Sprint | Forecast | Actual Effort
| Start Date | 2021-09-22 |  | Day of Sprint | Actual Effort |  | 0 | 33 | 33
| End Date | 2021-09-27 |  | 0 | 33 |  | 1 | 27.5 | 29
| Sprint Length | 6 |  | 1 | 29 |  | 2 | 22 | 29
| Team Size | 5 |  | 2 | 29 |  | 3 | 16.5 | 19
| Team Capacity | 50 |  | 3 | 19 |  | 4 | 11 | 16
| Total Sprint SP | 33 |  | 4 | 16 |  | 5 | 5.5 | 10
| SP/Day | 5.5 |  | 5 | 10 |  | 6 | 0 | 5
|  |  |  | 6 | 5
Who | Tasks | SP | Day of Sprint (hours worked)
|  |  | 0 | 1 | 2 | 3 | 4 | 5 | 6
Albert
| Obstacles & Solutions | 2 | 0 | 2 | 0 | 1 | 1 | 0 | 1
| Feature: Class Opp | 3 | 0 | 0 | 0 | 0 | 0 | 2 | 2
| Featue: Student Discounts | 3 | 0 | 0 | 0 | 0 | 3 | 1 | 0
SP Decrement |  |  | 0 | 1 | 0 | 0 | 3 | 1.5 | 2.5
Audrey
| Introduction | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 1
| Feature: Matching | 3 | 0 | 0 | 1 | 4 | 1 | 4 | 4
SP Decrement |  |  | 0 | 1 | 0 | 2 | 0 | 0.5 | 0.5
Brad
| Feature: Builder | 3 | 0 | 2 | 0 | 2 | 1 | 2 | 2
| Feature: Comparison | 3 | 0 | 0 | 0 | 2 | 2 | 2 | 2
| Feaure: Matching | 3 | 0 | 0 | 0 | 2 | 0 | 0 | 1
SP Decrement |  |  |  | 1 | 0 | 3 | 0 | 2 | 3
Joseph
| Goals/Solution | 1 | 0 | 1 | 0 | 2 | 0 | 1 | 0
| Feature: Aid | 3 | 0 | 0 | 0 | 4 | 1 | 4 | 5
SP Decrement |  |  | 0 | 0 | 0 | 2 | 2 | 0 | 0
Michael
| Needs/Problems | 2 | 0 | 0 | 0 | 1 | 0 | 0 | 1
| Feature: Course Diff | 3 | 0 | 1 | 0 | 4 | 0 | 2 | 2
| Feature: Schedule of Class | 3 | 0 | 0 | 0 | 1 | 1 | 2 | 2
SP Decrement |  |  | 0 | 1 | 0 | 3 | 0 | 2 | 2

## Kanban Board (hidden)
Sprint 2 | Assigned | To Do | In Progress | Blocked | Done
| Joseph |  |  |  | Phone calls: career center
| Joseph |  |  |  | Phone calls: financial aid
| Joseph |  |  |  | Phone calls: David Brown (schedule of classes)
| Brad |  |  |  | Test cases: Schedule Building
| Albert |  |  |  | Test cases: Discounts
| Audrey |  |  |  | Test cases: Matching
| Joseph |  |  |  | Test cases: Aid
| Michael |  |  |  | Test cases: Course Difficulty
| Albert |  |  |  | Test cases: Careers
| Michael |  |  |  | Test cases: Schedule of Classes
| Audrey |  |  |  | Test cases: Messaging
| Michael |  |  |  | Test cases: Registration
| Michael |  |  |  | Test cases: Login
| Michael |  |  |  | Test cases: Logout
Sprint 3 | Assigned | To Do | In Progress | Blocked | Done
| Albert |  |  |  | Test case data: student discounts, careers
| Audrey |  |  |  | Test case data: matching, messaging
| Brad |  |  |  | Test case data: schedules, classes
| Joseph |  |  |  | Test case data: aid
| Michael |  |  |  | Test case data: course rating, registration, login, logout
| Audrey |  |  |  | Test plan: testing schedule
| Michael |  |  |  | Detail testing environment
| Joseph |  |  |  | Progression and Regression Testing details
| Joseph |  |  |  | Information gathering: aid, careers, schedule of classes
| Brad |  |  |  | Network Diagram: Choose server provider
| Joseph |  |  |  | Network Diagram: Node system specs
| Albert |  |  |  | Network Diagram: IPs/URLs of external servers
| Audrey |  |  |  | Network Diagram: Requests
| Michael |  |  |  | Network Diagram: Responses
| Albert |  |  |  | Network Diagram: 3rd party services & servers
| Brad |  |  |  | Determine feature development order
| Audrey |  |  |  | Determine critical path tasks
| Michael |  |  |  | Plan deployment process
| Brad |  |  |  | Risk Identification
| Michael |  |  |  | Risk Mitigation
| Joseph |  |  |  | Schedule Project Milestones
| Albert |  |  |  | Schedule Sprints
| Brad |  |  |  | Validate schedule with team
| Albert |  |  |  | Generate Roadmap from schedule